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	Impact6
Discriminatory and harmful social norms are uprooted to achieve fair and just gender relations in line with global norms and standards on gender equality and women's empowerment
	Related UN-Women SP Impact Area: SP Outcome 1 :  A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented
Related UNDAF/ CCPD priority: Area 1-4
Related national development priorities:

	
	
	
	Year
2019
	Year
2020
	Total

	Outcome 6.1
National stakeholders work together in a coordinated manner to translate national and international norms and standards into action which transforms attitudes and behaviors discriminating against women and girls

Related SP Outcome/Output:
The capacity of governments and stakeholders is strengthened to assess progress in implementation of the Beijing Platform for Action, and other global normative and policy frameworks

Indicator 6.1A:  Ranking of Indonesia in Global Gender Gap Report

Targets: 
Value: 0
Notes: At least no drop (no number because the number of countries in the report changes
Target Year: 2019
Value: 8
Target Year: 2020

Baseline: 
Value: 9 Year: 2018
Source: Global Gender Gap Report

Indicator 6.1B:  Percentage of women in Parliament

Targets: 
Value: 18%
Notes: in 2019 election
Target Year: 2019
Value: 20%
Target Year: 2020

Baseline: 
Value: 17% Year: 2014
Note: 2014 election
Source: Indonesian Parliament

Indicator 6.1C:  Women's labor force participation

Targets: 
Value: 53%
Target Year: 2019
Value: 55%
Target Year: 2020

Baseline: 
Value: 53% Year: 2018
Source: National Bureau of Statistics

Indicator 6.1D:  Level of government's engagement in global  normative & policy frameworks (CEDAW, BPFA, CSW) with UN Women support

Targets: 
Value: 0
Notes: UN Women supports government in all four process
Target Year: 2019
Value: 1
Notes: BPFA Report submitted in 2019 (tbc-under writing) Annual CSW participatiion in 2020
Target Year: 2020

Baseline: 
Value: 0 Year: 2012
Note: Indonesia's latest report to the Committee was in 2012, the report to the UPR was in 2017, BPFA report submitted in 2014, annual CSW participation by the government
Source: UN Women monitoring data in MS, respective reports


	Output 6.1.1
Knowledge on the impacts and detrimental effects of discriminatory social norms on women's empowerment is expanded through research, studies, reviews, advocacy material and pilot projects
	Indicator 6.1.1A:  Number of UN Women-supported products (research, studies, advocacy material, etc.) addressing impacts of discriminatory social norms on women's empowerment

Targets: 
Value: 5
Target Year: 2019
Value: 5
Target Year: 2020
Value: 5
Target Year: 2020

Baseline: 
Value: 6 Year: 2018
Source: UN Women monitoring data

Indicator 6.1.1B:  Evidence of the use of UN Women-supported products addressing impacts of discriminatory social norms on women's empowerment (like for instance website downloads, citations, emails confirming use, etc.)

Targets: 
Value: Yes
Target Year: 2019
Value: Yes
Target Year: 2020
Value: Yes
Target Year: 2020

Baseline: 
Value: No Year: 2018
Source: website statistics, papers/publications, letters/emails/minutes, number of retweets/ reshare


	113,000.00
(core)

150,000.00
(non-core)


	123,000.00
(core)

0.00
(non-core)


	236,000.00
(core)

150,000.00
(non-core)

	
	Output 6.1.2
UN Women establishes and manages a coordinated multi-stakeholder advocacy platform on changing social norms to help unify and drive gender discourse towards greater understanding of gender equality for all
	Indicator 6.1.2A:  Existence of a Statute of the advocacy platform with objectives, members, methods of work

Targets: 
Value: Yes
Target Year: 2019
Value: Yes
Target Year: 2020
Value: Yes
Target Year: 2020

Baseline: 
Value: No Year: 2018
Source: Minutes of approval meeting, the Statute

Indicator 6.1.2B:  Number of initiatives addressing discriminatory social norms implemented/initiated by the advocacy platform

Targets: 
Value: 1
Target Year: 2019
Value: 2
Target Year: 2020
Value: 2
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source:  Documents supporting the initiatives, articles, UN Women data


	90,000.00
(core)

0.00
(non-core)


	102,000.00
(core)

150,000.00
(non-core)


	192,000.00
(core)

150,000.00
(non-core)

	
	Output 6.1.3
Duty bearers in vertical and horizontal structures of government are enabled to apply national and international norms and standards in their respective areas of competence for gender transformative governance
	Indicator 6.1.3A:  Number of government bodies supported by UN Women which address gender equality issues in their area of competence in line with national and international norms and standards

Targets: 
Value: 2
Target Year: 2019
Value: 2
Target Year: 2020
Value: 1
Target Year: 2020

Baseline: 
Value: 2 Year: 2018
Source: Ministerial communication, policy documents

Indicator 6.1.3B:  Number of improvements in gender responsiveness of government action introduced as a result of UN Women support

Targets: 
Value: 1
Target Year: 2019
Value: 1
Target Year: 2020
Value: 1
Target Year: 2020

Baseline: 
Value: 2 Year: 2018
Notes: Two national strategies on GRB
Source: UN Women monitoring data, government reports


	26,000.00
(core)

0.00
(non-core)


	20,000.00
(core)

0.00
(non-core)


	46,000.00
(core)

0.00
(non-core)

	
	Output 6.1.4
Rights holders including CSOs, media, academia, and communities are equipped to engage in a meaningful mobilization for transformation of gender norms towards a just, inclusive and peaceful society
	Indicator 6.1.4A:  Number of tools/initiatives designed by UN Women to support rights holders in the mobilization for transformation of gender norms

Targets: 
Value: 5
Target Year: 2019
Value: 5
Target Year: 2020
Value: 0
Target Year: 2020

Baseline: 
Value: 5 Year: 2018
Source:  Campaign tools, knowledge products, talk shows

Indicator 6.1.4B:  Number of initiatives implemented by rights holders supported by UN Women that mobilized for transformation of gender norms

Targets: 
Value: 1
Target Year: 2019
Value: 2
Target Year: 2020
Value: 0
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Notes: National CEDAW network
Source: UN Women and responsible parties' report


	0.00
(core)

667,962.00
(non-core)


	0.00
(core)

0.00
(non-core)


	0.00
(core)

667,962.00
(non-core)

	
	Output 6.1.5
More men engage in interventions to transform social norms towards gender justice, including ending VAWG
	Indicator 6.1.5A:  Number of men champions for gender equality supported by UN Women

Targets: 
Value: 3
Target Year: 2019
Value: 2
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Notes: President Jokowi is a global He4she Champion
Source: UN Women data, articles, He4She Campaign

Indicator 6.1.5B:  Number of initiatives/events addressing the need to change gender social norms with active participation of men supporting the change

Targets: 
Value: 5
Target Year: 2019
Value: 2
Target Year: 2020

Baseline: 
Value: 5 Year: 2018
Source: UN Women articles, media monitoring, photo documentation


	45,572,000.00
(core)

0.00
(non-core)


	49,000.00
(core)

0.00
(non-core)


	45,621,000.00
(core)

0.00
(non-core)

	
	Output 6.1.7
National Statistical Bureau and other relevant authorities are capacitated to generate, manage, use and analyze gender statistics and other gender-relevant information to improve effectiveness of interventions and increase accountability, with a focus on SDGs
	Indicator 6.1.7A:  Number of UN Women supported interventions (tools, reviews, trainings, etc.) aimed to improve generation, management, use or analysis of gender statistics and other gender-relevant information and data

Targets: 
Value: 1
Target Year: 2019
Value: 1
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: Government communication, UN Women reports, media

Indicator 6.1.7B:  Number of strategies/plans/internal regulatory documents/tools produced by the national statistics bureau or other authorities with UN Women support that use gender statistics or other gender-specific information or data

Targets: 
Value: 1
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: Government communication, UN Women reports, media


	8,000.00
(core)

0.00
(non-core)


	10,000.00
(core)

0.00
(non-core)


	18,000.00
(core)

0.00
(non-core)

	
	Output 6.1.8
Private sector is engaged to identify and transform business practices which hamper women's economic empowerment
	Indicator 6.1.8A:  Number of women's entrepreneurs trained on women's economic empowerment to digital platform in selected areas

Targets: 
Value: 5000
Target Year: 2019
Value: 5000
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: needs assessment on required skill by women's enrepreneurs


	10,000.00
(core)

276,188.00
(non-core)


	10,000.00
(core)

0.00
(non-core)


	20,000.00
(core)

276,188.00
(non-core)

	
	Output 6.1.9
Communities in East Java have an even stronger commitment to values that undermine the message of violent extremism
	Indicator 6.1.9A:  Number of communities in east java develop community action plans for gender-responsive PVE with capacity-building support on Human Security Approach

Targets: 
Value: 4
Target Year: 2020
Value: 4
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Source: Monitoring report

Indicator 6.1.9B:  A platform for sharing community-based solutions for PVE that are gender-responsive including good practices and lessons learned established

Targets: 
Value: 1
Target Year: 2020
Value: 1
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Source: monitoring report


	0.00
(core)

0.00
(non-core)


	0.00
(core)

87,273.00
(non-core)


	0.00
(core)

87,273.00
(non-core)

	
	Output 6.1.10
Youth in East Java are more capable of generating alternative narratives that confront and undermine the messages of violent extremists
	Indicator 6.1.10A:  At least one gender-responsive approach to generating alternative narrative to counter radicalization and violent extremism lead by youth targeting new and social media is developed

Targets: 
Value: 1
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Source: Monitoring Report, website


	0.00
(core)

0.00
(non-core)


	0.00
(core)

49,023.00
(non-core)


	0.00
(core)

49,023.00
(non-core)

	
	Output 6.1.12
Institutions and systems have increased capacity to promote tolerance and discourage violent extremism among the children and relatives of those convicted or accused of terrorism offences, including travel to support terrorist organisations.
	Indicator 6.1.12A:  A prototype (behavioral insight) to promote tolerance at the community level among youth and educators is developed to support institutional capacity building for countering and preventing violent extremism.

Targets: 
Value: 3
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Source: Monitoring Report


	0.00
(core)

0.00
(non-core)


	0.00
(core)

7,344.00
(non-core)


	0.00
(core)

7,344.00
(non-core)

	
	Output 6.1.13
High-quality knowledge product and/or research on the root causes of violent extremism with a human security lens in Indonesia, including East Java is made available
	Indicator 6.1.13A:  4 evidence-based research studies are developed to identify the root causes of violent extremism in East Java through a human security lens

Targets: 
Value: 4
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Source: Progress Report


	0.00
(core)

0.00
(non-core)


	0.00
(core)

20,000.00
(non-core)


	0.00
(core)

20,000.00
(non-core)

	
	Output 6.1.14
Policymakers have a better appreciation for and knowledge of the human security approach and the manner in which it can be usefully employed to prevent and counter violent extremism in Indonesia. (#6.3)
	Indicator 6.1.14A:  Number of policymakers at the community and national levels have access to a quality training module for C/PVE informed by community-level experiences and human security approach

Targets: 
Value: 40
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Source: progress report


	0.00
(core)

0.00
(non-core)


	0.00
(core)

37,889.00
(non-core)


	0.00
(core)

37,889.00
(non-core)

	Outcome 6.2
More women lead, participate and have access to business opportunities to advance sustainable and inclusive growth
 (Outcome 7)

Related SP Outcome/Output:
More women own, launch and/or better manage small and medium and large enterprises

Indicator 6.2A:  Number of national or sub-national policy frameworks promoting women-led SMEs and women entrepreneurs with UN Women support

Targets: 
Value: 2
Target Year: 2022

Baseline: 
Value: 0 Year: 2019
Source: Country Report

Indicator 6.2B:  Number of women entrepreneurs report having increased their capacity on managing their business and relevant soft skills with UN Women support

Targets: 
Value: 1000
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Note: Utilization of newly established digital learning platform
Source: Country Report

Indicator 6.2C:  Number of WEPs signatories reporting to have an action plan for WEPs implementation and/or case studies about WEPs implementation

Targets: 
Value: 5
Target Year: 2022

Baseline: 
Value: 0 Year: 2019
Source: Country Report


	Output 6.2.1
Knowledge: Women’s  networks, public institutions and the private sector in the EU and Indonesia share expertise and knowledge to advance an enabling business environment for women’s economic empowerment (output 1.1-global)
	Indicator 6.2.1A:  Percentage of readers of the platform who report having benefited from the shares (Suggested indicator by EUPIMS)

Targets: 
Value: 70%
Target Year: 2019
Value: 80%
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: Online Survey


	0.00
(core)

151,245.00
(non-core)


	0.00
(core)

116,646.00
(non-core)


	0.00
(core)

267,891.00
(non-core)

	
	Output 6.2.2
Capacity development and technical assistance: Women-owned business and entrepreneurs have increased capacity to engage with Indonesia government and private sector companies in policies and dialogues for advancement of women’s economic empowerment (output 2.1-global)
	Indicator 6.2.2A:  Number of processes related to state and sub- level policy dialogue on WEE which have been influenced by the project (Suggested indicator by EUPIMS)

Targets: 
Value: 1
Target Year: 2019
Value: 1
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Notes: Target to be refined during the inception phase
Source: Annual progress reports/final evaluation of the project


	0.00
(core)

75,917.00
(non-core)


	0.00
(core)

92,541.00
(non-core)


	0.00
(core)

168,458.00
(non-core)

	
	Output 6.2.3
Advocacy and representation: More private sector companies implement the WEPs, including the gender-sensitive business culture and practices in EU and Indonesia (Output 3.1-global)
	Indicator 6.2.3A:  number of WEPs signatories reporting to have an action plan for WEPs implementation and/or case studies about WEPs implementation

Targets: 
Value: 2
Notes: Companies with case studies
Target Year: 2019
Value: 5
Notes: Companies with Action Plans
Target Year: 2022
Value: 5
Target Year: 2020

Baseline: 
Value: 2 Year: 2018
Notes: Target to be refined during the inception phase. Figure includes each of individual multinational companies in different countries, such as ANZ Bank and Schneider Electric
Source: http://weprinciples.org/Site/Companies/#search  


	0.00
(core)

75,917.00
(non-core)


	0.00
(core)

97,544.00
(non-core)


	0.00
(core)

173,461.00
(non-core)

	Total Resources for outcome 6.1 (core and non-core)
	45,819,000.00
(core)

1,094,150.00
(non-core)
	314,000.00
(core)

351,529.00
(non-core)
	46,133,000.00
(core)

1,445,679.00
(non-core)

	Total Resources for outcome 6.2 (core and non-core)
	0.00
(core)

303,079.00
(non-core)
	0.00
(core)

306,731.00
(non-core)
	0.00
(core)

609,810.00
(non-core)

	Total Resources for impact area 6
	45,819,000.00
(core)

1,397,229.00
(non-core)
	314,000.00
(core)

658,260.00
(non-core)
	46,133,000.00
(core)

2,055,489.00
(non-core)

	Impact3
All women are safe and free from violence in private and public space
	Related UN-Women SP Impact Area: SP Outcome 4 :  All women and girls live a life free from all forms of violence 
Related UNDAF/ CCPD priority: Area 2 and 4
Related national development priorities:

	
	
	
	Year
2019
	Year
2020
	Total

	Outcome 3.1
Stronger mechanisms to prevent VAWG are established at national and sub-national level 
(Related SP outputs 11, 12)

Related SP Outcome/Output:
More countries and stakeholders are better able to prevent violence against women and girls and deliver essential services to victims and survivors

Indicator 3.1A:  Number of institutions supported by UN Women that develop strategies/policies/internal guidelines addressing VAWG

Targets: 
Value: 1
Notes: Additional 1
Target Year: 2019
Value: 5
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Source: UN Women reports

Indicator 3.1B:  Number of authorities/local governments that address elimination of violence against women and girls in public spaces through the transformation of social norms

Targets: 
Value: 2
Notes: Additional 2
Target Year: 2019
Value: 2
Target Year: 2020

Baseline: 
Value: 2 Year: 2018
Source: UN Women reports


	Output 3.1.1
Service providers from government and non-government stakeholders on VAW are able to utilize gender-sensitive approaches to prevent and respond to violence against women migrant workers and trafficking
	Indicator 3.1.1D:  Number of women migrants who receive assistance from frontline service providers.

Targets: 
Value: 50
Target Year: 2019
Value: 100
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: N/A

Indicator 3.1.1E:  Number of women migrants who are provided with information by networks.

Targets: 
Value: 400
Target Year: 2019
Value: 600
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: User registries quantitative calculation based on technical progress reports of implementing partner

Indicator 3.1.1F:  Number persons reached through campaign to address VAW, trafficking and gender based discrimination of women migrant workers.

Targets: 
Value: 100
Target Year: 2019
Value: 500
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: Quantitative calculation based on campaign events and products.

Indicator 3.1.1G:  Number of referral mechanisms for follow-up services for women migrants by front -line service providers.

Targets: 
Value: 0
Target Year: 2019
Value: 1
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: Quantitative calculation based on technical progress report of implementing partner

Indicator 3.1.1H:  Number of users of community-based and women-led networks supported by UN Women active in preventing VAW and trafficking.

Targets: 
Value: 100
Target Year: 2019
Value: 200
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: User registries quantitative calculation based on technical progress reports of implementing partner

Indicator 3.1.1I:  Number of front-line service providers trained to handle women's protection/trafficking issues in a coordinated manner

Targets: 
Value: 50
Target Year: 2019
Value: 100
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: Quantitative calculation based on technical progress reports of implementing partners


	0.00
(core)

396,932.00
(non-core)


	0.00
(core)

226,527.00
(non-core)


	0.00
(core)

623,459.00
(non-core)

	
	Output 3.1.3
Ministry of Health is supported to mainstream gender and violence prevention in HIV prevention policies
	Indicator 3.1.3A:  Number of MOH policies/policy guidance on HIV that address gender and violence prevention

Targets: 
Value: 1
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Notes: National Plan on HIV 2015-2019
Source: Ministry of Health


	1,000.00
(core)

75,000.00
(non-core)


	1,000.00
(core)

0.00
(non-core)


	2,000.00
(core)

75,000.00
(non-core)

	
	Output 3.1.4
Women's groups engaged in HIV prevention and response have better capacity to emphasize the role of VAWG in HIV prevention
	Indicator 3.1.4A:  Number of women's groups supported by UN Women with capacity development interventions aiming to increase understanding the role of VAWG in HIV prevention

Targets: 
Value: 2
Target Year: 2019
Value: 1
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Source: Indonesian "Positive Network" activity reports

Indicator 3.1.4B:  Number of government initiatives/documents to which the supported women's groups contribute advocacy information on the role of VAWG in HIV prevention

Targets: 
Value: 1
Target Year: 2019
Value: 1
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Source: UN Women


	1,000.00
(core)

95,439.00
(non-core)


	1,000.00
(core)

0.00
(non-core)


	2,000.00
(core)

95,439.00
(non-core)

	
	Output 3.1.5
City governments are supported to design and implement urban plans which provide safety for women and girls in public spaces
	Indicator 3.1.5A:  Number of evidence-based reports on safety and security of women and girls in public spaces to inform urban planning that were made available with UN Women support

Targets: 
Value: 1
Target Year: 2019
Value: 1
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Notes: Safety Audit Jakarta
Source: UN Women reports, scoping studies

Indicator 3.1.5B:  Number of urban plans produced with UN Women support that address safety issues for women and girls

Targets: 
Value: 1
Target Year: 2020

Baseline: 
Value: 0 Year: 2018
Source: UN Women reports, city planning documents


	15,000.00
(core)

0.00
(non-core)


	20,000.00
(core)

0.00
(non-core)


	35,000.00
(core)

0.00
(non-core)

	Outcome 3.2
Response to VAWG addresses the impacts of violence in line with women's and girls' needs and ensures that perpetrators are held accountable
(Related SP output 11)

Related SP Outcome/Output:
More countries and stakeholders are better able to prevent violence against women and girls and deliver essential services to victims and survivors

Indicator 3.2A:  Number of institutions and organizations supported by UN Women that improve their internal instructions/guidelines/protocols/standard operating procedures on the provision of quality services to victims and survivors

Targets: 
Value: 1
Notes: 1 additional
Target Year: 2019
Value: 3
Notes: Through SAF Project, guidelines for quality service for victims and survivors will be supported
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Source: UN Women reports


	Output 3.2.1
Law enforcement agencies, including judges, have the capacity, skills, tools and procedures to implement the law on DV and law on SV in a way that responds to women's and girls' needs and international standards
	Indicator 3.2.1A:  Number of tools and procedures for implementation of DV/SV laws developed by law enforcement agencies supported by UN Women

Targets: 
Value: 1
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Notes: Framework for the DV law evaluation
Source: UN Women reports

Indicator 3.2.1B:  Number of capacity development initiatives provided by UN Women to law enforcement agencies in support of capacity to implement DV/SV laws

Targets: 
Value: 1
Target Year: 2020

Baseline: 
Value: 2 Year: 2018
Source: UN Women report and documents


	15,000.00
(core)

0.00
(non-core)


	20,000.00
(core)

0.00
(non-core)


	35,000.00
(core)

0.00
(non-core)

	
	Output 3.2.4
Service providers are supported to provide quality sustainable services to women and girls-survivors of violence
	Indicator 3.2.4A:  Number of service providers supported
Baseline: 1 - each province has a governmental service provider (P2TP2A)

Targets: 
Value: 1
Target Year: 2019
Value: 1
Target Year: 2020

Baseline: 
Value: 1 Year: 2018
Notes: Each province has a governmental service provider  (P2TP2A)
Source:  P2TP2A and UN Women reports

Indicator 3.2.4B:  Quality of the services provided by the supported providers based on defined criteria

Targets: 
Value: survey mid 2020 of at least one P2TP2A with who UN Women works
Target Year: 2020

Baseline: 
Value: komnas perempuan baseline on quality services Year: 2018
Source: UN Women survey


	8,000.00
(core)

0.00
(non-core)


	10,000.00
(core)

0.00
(non-core)


	18,000.00
(core)

0.00
(non-core)

	
	Output 3.2.5
Grassroots women’s organizations and community-based women’s organizations are empowered and well position to document, monitor, liaise and facilitate interactions with formal and informal justice providers, and their resilience is enhanced to build a just and sustainable future.
	Indicator 3.2.5A:  Number of cases involving women have been addressed by Pokjas.

Targets: 
Value: 0
Target Year: 2020
Value: 1
Target Year: 2020
Value: 13
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Source: 1

Indicator 3.2.5B:  Numbers of exchanges between community bases system and formal justice and service providers conducted

Targets: 
Value: 1
Target Year: 2020
Value: 1
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Source: 1

Indicator 3.2.5C:  Number of women who have actively been involved in human rights monitoring and documentation through the online platform supported by the project

Targets: 
Value: 1
Target Year: 2020
Value: 1
Target Year: 2020
Value: 98
Target Year: 2020
Value: 60
Target Year: 2020

Baseline: 
Value: 0 Year: 2019
Source: 1


	0.00
(core)

0.00
(non-core)


	0.00
(core)

100,000.00
(non-core)


	0.00
(core)

100,000.00
(non-core)

	Total Resources for outcome 3.1 (core and non-core)
	17,000.00
(core)

567,371.00
(non-core)
	22,000.00
(core)

226,527.00
(non-core)
	39,000.00
(core)

793,898.00
(non-core)

	Total Resources for outcome 3.2 (core and non-core)
	23,000.00
(core)

0.00
(non-core)
	30,000.00
(core)

100,000.00
(non-core)
	53,000.00
(core)

100,000.00
(non-core)

	Total Resources for impact area 3
	40,000.00
(core)

567,371.00
(non-core)
	52,000.00
(core)

326,527.00
(non-core)
	92,000.00
(core)

893,898.00
(non-core)
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