UN Women Strategic Note 2019-2023

UN WOMEN Cambodia COUNTRY OFFICE

SN REPORT 2020

The report includes:

Development results framework (DRF)

Report Date: 5/5/2020

| Impact6 A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented |  | Related UN-Women SP Impact Area: SP Outcome 1 : A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented Related UNDAF/ CCPD priority: Outcome 4: Accountability and Participation; Outcome 2: Expanding Economic Opportunities Related national development priorities: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year 2019 | Year 2020 | Year 2021 | Year 2022 | Year 2023 | Total |
| Outcome 6.1 The RGC resources, coordinates and transparently monitors implementation of international commitments to GE&WE, in consultation with rights holders including Young women and LGBTIQ persons. Related SP Outcome/Output: The capacity of governments and stakeholders is strengthened to assess progress in implementation of the Beijing Platform for Action, and other global normative and policy frameworks Indicator 6.1A: Number of selected laws and policies that have been adopted, amended and implemented to comply with international norms and standards with UN Women support. Targets: Value: 4 Notes: Refers to compliance with recommendations of CEDAW and commitments under Beijing PfA, SDGs. (DV, National Programme for Promotion of Women Leadership in civil service, labour migration policy, sectoral policy-MOE) Target Year: 2023 Baseline: Value: 0 Year: 2018 Source: CCO Annual Report Indicator 6.1B: Number of key government ministries able to report annually on gender budget allocations. Targets: Value: 5 Notes: Ministries/institutions (MOE, MCS, MOEYS, NCDDS, MOWA) have gender statement Target Year: 2023 Baseline: Value: 0 Year: 2018 Source: CNCW Annual Report Indicator 6.1C: Number of new national gender indicators adopted and monitored in line with SDG5 Targets: Value: 2 Notes: 2 new indicators: Gender-adjusted wage gap; Unpaid care work. Target Year: 2023 Baseline: Value: 0 Year: 2018 Source: Cambodian SDG Indicator Framework; Cambodia Socio-Economic Survey (2020) | Output 6.1.3 Young women and marginalised women, as well as LGBTIQ persons, have the capacity, networks and space to hold duty bearers to account on GE&WE commitments. | Indicator 6.1.3A: Percentage of Youth Leadership Academy (YLA) participants reported to integrate feminist leadership principles into their daily life Targets: Value: 70% Target Year: 2020 Baseline: Value: 0% Year: 2019 Source: CCO Annual Report Indicator 6.1.3B: Number of joint CSO and activist-lead initiatives on GE & WE commitments supported by UNW Targets: Value: 4 Target Year: 2020 Baseline: Value: 4 Year: 2019 Notes: Notes: In 2019- IWD joint effort while CCO connected women artists to a group of women CSO and MOWA, LGBTIQ dialogue x 2, 16 Days, #LoveisDiversity Source: CCO Annual Report Source: Capacity Needs Assessment Report Indicator 6.1.3C: Number of inter-generational dialogues conducted through CCO's support to build undestanding of women's issues across generation and strengthen inter-general coalition. Targets: Value: 3 Target Year: 2020 Baseline: Value: 1 Year: 2019 Source: CCO Annual Report Indicator 6.1.3D: Number of action learning of YLA participants conducted to address negative social and gender norms Targets: Value: 8 Target Year: 2020 Baseline: Value: 4 Year: 2019 Source: CCO Annual Report Indicator 6.1.3E: Number of advocacy events conducted by grassroots HIV affected women's groups to raise livelihood issue and health care concerns for HIV affected people, including women and children Targets: Value: 2 Target Year: 2020 Baseline: Value: 2 Year: 2019 Source: CCO Report | 156,655.00 (core) 104,000.00 (non-core) | 151,069.00 (core) 10,630.00 (non-core) | 200,462.00 (core) 315,000.00 (non-core) | 160,462.00 (core) 344,000.00 (non-core) | 160,462.00 (core) 0.00 (non-core) | 829,110.00 (core) 773,630.00 (non-core) |
|  | Output 6.1.4 Output 6.1.2 Strengthened capacity of key government bodies, including Ministries and the Judiciary, to implement the CEDAW, CSW, Beijing PFA and SDGs | Indicator 6.1.4A: Indicator 1.1.1a: Number of dialogues with government women leaders conducted to advocate for gender responsive budgeting and gender statistics. Targets: Value: 3 Target Year: 2020 Baseline: Value: 3 Year: 2019 Source: CCO Report Indicator 6.1.4B: Indicator 1.1.1b: Number of action plan for implementation of new CEDAW Concluding Observations through UN Women support to CNCW. Targets: Value: 1 Notes: CNCW Consultations Target Year: 2020 Baseline: Value: 0 Year: 2019 Source: CCO Report Indicator 6.1.4C: Indicator 1.1.1.c: Percentage of trainees from key government institutions demonstrated increased understanding on the concepts of GRB and gender statistics through UN Women support Targets: Value: 70% Target Year: 2020 Baseline: Value: 0% Year: 2019 Source: CCO Report | 0.00 (core) 0.00 (non-core) | 143,931.00 (core) 0.00 (non-core) | 0.00 (core) 0.00 (non-core) | 0.00 (core) 0.00 (non-core) | 0.00 (core) 0.00 (non-core) | 143,931.00 (core) 0.00 (non-core) |
| Total Resources for outcome 6.1 (core and non-core) |  |  | 156,655.00 (core) 104,000.00 (non-core) | 295,000.00 (core) 10,630.00 (non-core) | 200,462.00 (core) 315,000.00 (non-core) | 160,462.00 (core) 344,000.00 (non-core) | 160,462.00 (core) 0.00 (non-core) | 973,041.00 (core) 773,630.00 (non-core) |
| Total Resources for impact area 6 |  |  | 156,655.00 (core) 104,000.00 (non-core) | 295,000.00 (core) 10,630.00 (non-core) | 200,462.00 (core) 315,000.00 (non-core) | 160,462.00 (core) 344,000.00 (non-core) | 160,462.00 (core) 0.00 (non-core) | 973,041.00 (core) 773,630.00 (non-core) |
| Impact4 Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action |  | Related UN-Women SP Impact Area: SP Outcome 5 : Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action. Related UNDAF/ CCPD priority: Outcome 3: Sustainable Living Related national development priorities: |  |  |  |  |  |  |
|  |  |  | Year 2019 | Year 2020 | Year 2021 | Year 2022 | Year 2023 | Total |
| Outcome 4.1 SN Outcome 4: National and sub-national responses to climate change and Disaster Risk Reduction incorporate and address the priorities and needs of all women in Cambodia. Related SP Outcome/Output: More women play a great role in and are better served by disaster risk management processes Indicator 4.1A: Number of climate change/DRR related sectoral policies and action plans which have enhanced responsiveness to gender and human rights. Targets: Value: 4 Target Year: 2022 Value: 4 Target Year: 2022 Baseline: Value: 8 Year: 2018 Note: The baseline is set based on the mapping report prepared under the EmPower project, according to which at least 8 national climate change/DRR/energy policies already include, to some extent, gender and human rights considerations Source: Project evaluation reports and national level policies Indicator 4.1B: Number of assessments or strategic evaluations use gendered evidence and data on climate and disaster risks and impacts. Targets: Value: 3 Notes: The national assessments on gender equality, climate vulnerability and disaster risks, national gender risk profiles, reports on mainstreaming of gender equality into national climate change and DRR actions will be prepared. Target Year: 2022 Baseline: Value: 0 Year: 2018 Note: Refer to the chapter on Gender and Climate And DRR in the Cambodia Gender Assessment 2014. Source: Cambodia Gender Assessment 2019, Government assessment reports and evaluations Indicator 4.1C: Number of capacity building events on gender equality and women’s rights in climate change and DRR that target officials, decision makers and women leaders . Targets: Value: 5 Notes: Capacity building and coaching/mentoring on gender and women rights in climate change actions and DRR. Target Year: 2022 Baseline: Value: 0 Year: 2018 Note: Currently existing capacity building programmes for officials and decision makers do not focus on the intersect of climate change, DRR and gender. Source: Training programmes, curricula and modules; and post training reports | Output 4.1.1 RGC and key stakeholders have capacity to generate, analyse and use sex, age and diversity disaggregated data to inform disaster and climate change risk analysis and actions. | Indicator 4.1.1A: Number of government ministries/committees (MOE/NCSD, MOWA, MRD, MAFF, NCSDD-s and NCDM) that apply gender analysis and SADDD to climate and disaster risk profiling Targets: Value: 1 Target Year: 2020 Baseline: Value: 0 Year: 2019 Source: Project Progress report | 11,956.00 (core) 0.00 (non-core) | 0.00 (core) 132,340.00 (non-core) | 35,956.00 (core) 110,432.00 (non-core) | 35,456.00 (core) 210,432.00 (non-core) | 0.00 (core) 0.00 (non-core) | 83,368.00 (core) 453,204.00 (non-core) |
|  | Output 4.1.2 National climate change and DRR Regulatory and policy frameworks and climate change financing fulfil and protect human rights and gender equality commitments. | Indicator 4.1.2A: Number of policy papers/technical briefs mainstreamed gender analyses and technical inputs by key CC/DRR government institutions Targets: Value: 4 Target Year: 2020 Baseline: Value: 2 Year: 2019 Notes: Focus on support to key government institutions (MoE/NCSD, NCDM, MAFF, MRD) when project is being implemented. Source: Project progress report Indicator 4.1.2B: Percentage of government officials, women leaders trained report increased knowledge, skills and leadership to mainstreaming gender, human rights into climate change and DRR action. Targets: Value: 70% Target Year: 2020 Baseline: Value: 0 Year: 2019 Source: Progress program report | 0.00 (core) 58,310.00 (non-core) | 0.00 (core) 81,521.00 (non-core) | 0.00 (core) 34,000.00 (non-core) | 0.00 (core) 84,000.00 (non-core) | 0.00 (core) 0.00 (non-core) | 0.00 (core) 257,831.00 (non-core) |
|  | Output 4.1.3 Women and marginalised groups have capacity to meaningfully participate in, influence and lead climate change and DRR decision-making processes. | Indicator 4.1.3C: Number of consultations between government ministries or committees working on-climate change or DRR and CSOs/ gender advocates. Targets: Value: 2 Target Year: 2020 Baseline: Value: 0 Year: 2019 Source: Project progress report, consultation report Indicator 4.1.3D: Percentage of civil society representatives involved in the project who are able to lead and engage with the government and regional bodies on gender in climate change and DRR policy dialogue. Targets: Value: 55% Target Year: 2019 Value: 70% Target Year: 2020 Baseline: Value: 40% Year: 2018 Source: CSO consultation March 2018 (Baseline) and Project progress report | 0.00 (core) 108,171.00 (non-core) | 0.00 (core) 106,326.00 (non-core) | 0.00 (core) 51,000.00 (non-core) | 0.00 (core) 101,000.00 (non-core) | 0.00 (core) 0.00 (non-core) | 0.00 (core) 366,497.00 (non-core) |
| Total Resources for outcome 4.1 (core and non-core) |  |  | 11,956.00 (core) 166,481.00 (non-core) | 0.00 (core) 320,187.00 (non-core) | 35,956.00 (core) 195,432.00 (non-core) | 35,456.00 (core) 395,432.00 (non-core) | 0.00 (core) 0.00 (non-core) | 83,368.00 (core) 1,077,532.00 (non-core) |
| Total Resources for impact area 4 |  |  | 11,956.00 (core) 166,481.00 (non-core) | 0.00 (core) 320,187.00 (non-core) | 35,956.00 (core) 195,432.00 (non-core) | 35,456.00 (core) 395,432.00 (non-core) | 0.00 (core) 0.00 (non-core) | 83,368.00 (core) 1,077,532.00 (non-core) |
| Impact3 Women, girls and LGBTIQ persons in Cambodia live free from gender-based violence; (Aligned with Global SP Outcome 4) |  | Related UN-Women SP Impact Area: SP Outcome 4 : All women and girls live a life free from all forms of violence Related UNDAF/ CCPD priority: Outcome 1: Expanding Social Opportunities; Outcome 2: Expanding Economic Opportunities; and Outcome 4: Accountability and Participation Related national development priorities: |  |  |  |  |  |  |
|  |  |  | Year 2019 | Year 2020 | Year 2021 | Year 2022 | Year 2023 | Total |
| Outcome 3.1 Cambodia has an enabling environment to better prevent, respond and prosecute all forms of gender-based violence [aligns to UN Women SP 2018-2021 Output 11] Related SP Outcome/Output: More cities and other settings have safe and empowering public spaces for women and girls Indicator 3.1A: Number of Laws, policies and protocols revised and/or adopted which support the prosecution and coordinated response around GBV which align with international standards Targets: Value: 8 Notes: 8: (1) Revised DV Law tabled by Government for consideration; and (2) its Explanatory Notes with clear definitions for sexual harassment and gender discrimination; (3) VAW Mediation Guidelines; (4) VAW MSS; (5) VAW Bench Book; (6) 3rd Labour Migration Policy; (7) Guideline on Dispute Resolution for Migrant Workers; and (8) Employment Contract for Migrants. Target Year: 2023 Baseline: Value: 6 Year: 2018 Note: 6: DV Law; Explanatory Notes for the DV Law; Draft VAW Bench Book; Draft VAW Mediation Guideline; and Draft VAW MSS; Labour Migration Policy MOV: Report of Cambodia National Council for Women (CNCW) and MOWA, and TWGG-GBV. Source: Report of Cambodia National Council for Women (CNCW) and MOWA, and TWGG-GBV Indicator 3.1B: Percentage increase of budget allocation to Annual Operational Plan (AOP) for the 3rd NAPVAW implementation [UN Women SP 2018-2021 Output 12.2] Targets: Value: +50% (USD 5.5 Million) Notes: Annual Operational Plan (AOP) for the 3rd NAPVAW 2019-2023 implementation Target Year: 2023 Baseline: Value: USD 3.7 Million Year: 2017 Note: Annual Operational Plan (AOP) for the 2nd NAPVAW 2017 implementation Source: TWGG-GBV Report | Output 3.1.1 The RGC has improved capacity to adopt, implement and monitor GBV legislation, policies and standards. | Indicator 3.1.1A: The 3rd NAPVAW implementation monitored and reported through the Technical Working Group on Gender-GBV (TWGG-GBV). [UN Women SP 2018-2021 Output 11.1] Targets: Value: 1 Notes: Annual report of 3rd NAPVAW implementation Target Year: 2020 Baseline: Value: 0 Year: 2019 Notes: Annual report of 3rd NAPVAW implementation Source: MOWA Report Indicator 3.1.1B: Number of RGC Line Ministries contributed to developing, reviewing and adopting laws, policies and strategies addressing GBV through consultation with gender and LGBTIQ advocates. [UN Women SP 2018-2021 Output 11.3] Targets: Value: +1 Notes: Relevant RGC Line Ministries Target Year: 2019 Value: +1 Notes: Ministry of Economic and Finance Target Year: 2020 Baseline: Value: 15 Year: 2017 Notes: Relevant RGC Line Ministries Source: UN Women report | 44,500.00 (core) 428,318.00 (non-core) | 0.00 (core) 129,487.00 (non-core) | 60,000.00 (core) 87,500.00 (non-core) | 60,000.00 (core) 187,500.00 (non-core) | 60,000.00 (core) 187,500.00 (non-core) | 224,500.00 (core) 1,020,305.00 (non-core) |
|  | Output 3.1.2 Young women and men, including LGBTIQ youth, in selected communities, schools and other settings understand and challenge harmful gender norms, including GBV and harassment in public spaces. | Indicator 3.1.2B: Number of new marginalized groups targeted in campaigns led by UN Women. [UN Women SP 2018-2021 Output 11.2] Targets: Value: 2 Notes: Incremental target over the baseline (Garment Factory, and Women Migrant) Target Year: 2019 Value: 6 Target Year: 2020 Baseline: Value: 6 Year: 2017 Notes: 1. Community people; 2. Uniformed services (police and military personnel); 3. University students; 4. Survivors of SGBV during the Khmer Rouge regime; 5. People with disabilities (run by CWCC’s Promoting Women’s Dignity, funded by UNTF); 6. LGBTIQ people. Source: UN Women Report Indicator 3.1.2C: Number of participant (disaggregated by sex) engaged in public awareness campaign focused on GBV against women migrant workers, using women’s voices and stories. [UN Women SP 2018-2021 Output 11.2] Targets: Value: 10000 Notes: Participant directly involved 10000 Target Year: 2019 Value: 10000 Notes: Participant directly involved 10000 Target Year: 2020 Baseline: Value: 5000 Year: 2017 Notes: 16 days campaign 's activities organized across the country directly involved over 5,000 people, 174,000 people were reached through traditional and social media Source: UN Women report | 10,000.00 (core) 20,000.00 (non-core) | 0.00 (core) 0.00 (non-core) | 10,000.00 (core) 240,000.00 (non-core) | 10,000.00 (core) 240,000.00 (non-core) | 10,000.00 (core) 320,000.00 (non-core) | 40,000.00 (core) 820,000.00 (non-core) |
|  | Output 3.1.3 Legal actors, workers’ representatives, trade union representatives and CSO staff are able to advocate for and implement women-centred justice, including zero tolerance for sexual harassment. | Indicator 3.1.3A: Percentage of Feminist Jurisprudence initiative participants report actions taken to integrate Feminist Jurisprudence principles including CEDAW into their practice (disaggregated by sex and role). [UN Women SP 2018-2021 Outcome 4; Indicator 1] Targets: Value: +10% Notes: Post training follow up including through Gender Responsive Core Groups mentoring and Significant change stories. Target Year: 2019 Value: +10% Target Year: 2020 Baseline: Value: 0% Year: 2018 Notes: To be determined by pre-test (interview) in Q4-2018 Source: UN Women Report | 10,000.00 (core) 35,000.00 (non-core) | 0.00 (core) 0.00 (non-core) | 0.00 (core) 325,000.00 (non-core) | 0.00 (core) 250,000.00 (non-core) | 0.00 (core) 300,000.00 (non-core) | 10,000.00 (core) 910,000.00 (non-core) |
| Outcome 3.2 Women, girls and LGBTIQ persons who experience violence are empowered to use available, accessible and quality essential services and recover from violence. [UN Women SP 2018-2021 Output 11] Related SP Outcome/Output: More countries and stakeholders are better able to prevent violence against women and girls and deliver essential services to victims and survivors Indicator 3.2A: Proportion of women age 15-49 who have ever experienced physical and sexual violence who seek services. Targets: Value: +10% Notes: Women age 15-49 who have ever experienced physical and sexual violence who seek help Target Year: 2020 Baseline: Value: 42.6% Year: 2015 Note: Women age 15-49 who have ever experienced physical and sexual violence who seek help Source: Cambodia DHS of National Institute of Statistic, Ministry of Planning | Output 3.2.1 GBV service providers (Health, Police, Justice, and Social Services) have capacity to deliver inclusive, quality and accessible essential services to survivors, including marginalised women and LGBTIQ persons. | Indicator 3.2.1A: Percentage of trained GBV service providers (Health, Police, Justice, and Social Services) with increased knowledge to deliver inclusive quality and accessible essential services to survivors, including marginalised women and LGBTIQ. [UN Women SP 2018-2021 Output 11.4] Targets: Value: 50% Notes: 15% incremental target over the baseline Target Year: 2019 Value: 55% Notes: 20% increased over baseline Target Year: 2020 Baseline: Value: 35% Year: 2017 Notes: 35%, very strong increased in knowledge on multi-sectoral response for VAWG/GBV survivors Source: UN Women report Indicator 3.2.1B: Percentage of trained judiciary and police with strengthened capacity to deliver justice for survivors of GBV in the formal and informal justice systems. [UN Women SP 2018-2021 Output 11.4] Targets: Value: 83% Notes: Pre Test and Post Test Target Year: 2019 Value: 90% Notes: Increased over baseline Target Year: 2020 Baseline: Value: 77% Year: 2017 Notes: Pre Test and Post Test Source: UN Women report Indicator 3.2.1C: Percentage of GBV survivors in target areas with increased knowledge of referral procedures and available services. [UN Women SP 2018-2021 Output 11.4] Targets: Value: +20% Notes: 20% increase over the baseline in 2019 Target Year: 2019 Value: 20% Notes: Increased over baseline Target Year: 2020 Baseline: Value: 0% Year: 2018 Notes: Baseline to be determined under DFAT-ACCESS programme in late 2019 and Q1-2020 Source: Final evaluation of 2nd NAPVAW, MoWA. | 0.00 (core) 80,729.00 (non-core) | 0.00 (core) 116,272.00 (non-core) | 0.00 (core) 195,000.00 (non-core) | 0.00 (core) 190,000.00 (non-core) | 0.00 (core) 225,000.00 (non-core) | 0.00 (core) 807,001.00 (non-core) |
|  | Output 3.2.2 Ministry of Women's Affairs (MOWA), Ministry of Labour and Vocational Training (MOLVT) and relevant line ministries effectively supports referral and coordination networks at national and sub-national level. | Indicator 3.2.2A: Number of national and sub-national working groups on multi-sectoral service response to GBV established and strengthened. [UN Women SP 2018-2021 Output 11.4] Targets: Value: +2 Notes: Sub-national working group on multi-sectoral service response to GBV in 2 new locations. Target Year: 2019 Value: +4 Notes: New established in Siem Reap under UN Women and ACCESS's partner included LAC and CWCC in Siem Reap and Kampong Speu Target Year: 2020 Baseline: Value: 7 Year: 2018 Notes: TWGG-GBV at national level; Sub-national working groups at Provincial level and in 2 districts in Kampong Speu and Preah Sihanouk Province. Source: UN Women Report Indicator 3.2.2B: Percentage of sub-national working group members on multi-sectoral service response to GBV reporting an increased understanding on service coordination, referral, case management and documenting VAW administrative data. [UN Women SP 2018-2021 Output 11.4] Targets: Value: 70% Notes: 70% in 2019 (Results are consolidated incrementally) Target Year: 2019 Value: 80% Notes: Results are consolidated incrementally Target Year: 2020 Baseline: Value: 0% Year: 2018 Notes: Baseline to be conducted under DFAT-ACCESS programme in late 2019 and Q1-2020 Source: Capacity Assessment Report of sub-national working group on multi-sectoral service response to GBV. Indicator 3.2.2C: Increased percentage of GBV cases managed multi-sectorally according to Case Management Guidelines [UN Women SP 2018-2021 Output 11.4] Targets: Value: 10% Notes: 10% yearly incremental target over the baseline Target Year: 2019 Value: 20% Notes: Increased over baseline Target Year: 2020 Baseline: Value: 0% Year: 2018 Notes: Baseline to be collected under DFAT-ACCESS programme in late 2019 and Q1-2020 Source: Baseline to be collected by 2018 | 0.00 (core) 127,849.00 (non-core) | 0.00 (core) 62,300.00 (non-core) | 0.00 (core) 145,000.00 (non-core) | 0.00 (core) 215,000.00 (non-core) | 0.00 (core) 550,000.00 (non-core) | 0.00 (core) 1,100,149.00 (non-core) |
|  | Output 3.2.3 Ministry of Women's Affairs (MOWA), Ministry of Labour and Vocational Training (MOLVT) and relevant line ministries have capacity to develop, implement and monitor policies and programmes to prevent and respond to GBV against migrant workers with participation of civil society and private sector. | Indicator 3.2.3A: Number of women migrants who access support services (Health, Police, Justice, and Social Services) for survivors of violence and trafficking. [UN Women SP 2018-2021 Output 11.4] Targets: Value: 100 Notes: Data to be collected in Safe and Fair’s target provinces only (Phnom Penh, Banteay Meanchey, Battambang, Kampong Thom, Siem Reap, Kampong Cham, Prey Veng, Kampot and Preah Sihanouk) Target Year: 2019 Value: 300 Target Year: 2020 Baseline: Value: 0 Year: 2018 Notes: Baseline is zero under Safe and Fair project Source: UN Women and ILO Safe and Fair Report Indicator 3.2.3B: # of laws and policies adopted or amended with UN Women inputs on rights-based and survivor-centred approaches. Targets: Value: 1 Target Year: 2019 Value: 1 Target Year: 2020 Baseline: Value: 0 Year: 2018 Source: Report Indicator 3.2.3C: # of countries with dedicated national strategies/action plans on eliminating VAW, which include women migrants. Targets: Value: 0 Target Year: 2019 Value: 1 Target Year: 2020 Baseline: Value: 0 Year: 2018 Notes: Cambodia is expected to be one of the countries with strategies/plans of action on eliminating VAW. Source: Annual report Indicator 3.2.3D: # of information systems strengthened for women migrants who access support services (health, welfare, police, justice) for survivors of violence and trafficking. Targets: Value: 0 Target Year: 2019 Value: 1 Notes: Cambodia expects to have two information systems for the whole life cycle of Safe and Fair Programme Target Year: 2020 Baseline: Value: 0 Year: 2018 Source: Annual report Indicator 3.2.3E: # of referral mechanisms for follow-up services for women migrants by front-line service providers. Targets: Value: 0 Target Year: 2019 Value: 1 Notes: Cambodia expects to have two referral mechanisms Target Year: 2020 Baseline: Value: 0 Year: 2018 Source: Annual report Indicator 3.2.3F: # of users of community-based and women-led networks supported by UN Women active in preventing VAW and trafficking Targets: Value: 30 Target Year: 2019 Value: 90 Target Year: 2020 Baseline: Value: 0 Year: 2018 Notes: 300 users for the whole programme life cycle Source: Annual report Indicator 3.2.3G: # of women migrants who are provided with information by networks. Targets: Value: 200 Target Year: 2019 Value: 450 Target Year: 2020 Baseline: Value: 0 Year: 2018 Notes: 1500 for the whole programme life cycle. Source: Annual report Indicator 3.2.3H: # of women migrants who receive assistance from front-line service providers Targets: Value: 100 Target Year: 2019 Value: 300 Target Year: 2020 Baseline: Value: 0 Year: 2018 Source: Annual report Indicator 3.2.3I: # of front-line service providers trained to handle women’s protection/trafficking issues in a coordinated manner Targets: Value: 30 Target Year: 2019 Value: 60 Target Year: 2020 Baseline: Value: 0 Year: 2018 Notes: Cambodia is required to have at least 60 service providers trained. Source: Annual report Indicator 3.2.3J: # of joint task forces (linking, for example, criminal justice, labour, immigration and VAW) established on women’s protection/trafficking. Targets: Value: 2 Target Year: 2019 Value: 2 Target Year: 2020 Baseline: Value: 0 Year: 2018 Notes: Cambodia is required to have established at least one joint task force by 2020 Source: Annual report Indicator 3.2.3K: # of research studies and knowledge materials produced focusing on safe and fair labour migration, and violence against migrant women Targets: Value: 2 Target Year: 2019 Value: 2 Target Year: 2020 Baseline: Value: 0 Year: 2018 Notes: Cambodia is required to produce at least 2 knowledge products per year. The target for the whole programme cycle is 10. Source: Annual report Indicator 3.2.3L: # of ASEAN countries collecting data on violence against migrant women (administrative or prevalence data) Targets: Value: 0 Target Year: 2019 Value: Target Year: 2020 Baseline: Value: 0 Year: 2018 Notes: Cambodia is required to be one of the countries collecting data on violence against women migrant workers. Source: Annual report Indicator 3.2.3M: # persons reached through campaigns to address VAW, trafficking and gender based discrimination of women migrant workers. Targets: Value: 2000 Target Year: 2019 Value: 2000 Target Year: 2020 Baseline: Value: 0 Year: 2018 Notes: No target has been set for this indicator. But Safe and Fair Cambodia will try to reach 20000 people. Source: Annual report | 0.00 (core) 353,546.00 (non-core) | 0.00 (core) 411,036.00 (non-core) | 0.00 (core) 284,003.00 (non-core) | 0.00 (core) 270,186.00 (non-core) | 0.00 (core) 0.00 (non-core) | 0.00 (core) 1,318,771.00 (non-core) |
| Total Resources for outcome 3.1 (core and non-core) |  |  | 64,500.00 (core) 483,318.00 (non-core) | 0.00 (core) 129,487.00 (non-core) | 70,000.00 (core) 652,500.00 (non-core) | 70,000.00 (core) 677,500.00 (non-core) | 70,000.00 (core) 807,500.00 (non-core) | 274,500.00 (core) 2,750,305.00 (non-core) |
| Total Resources for outcome 3.2 (core and non-core) |  |  | 0.00 (core) 562,124.00 (non-core) | 0.00 (core) 589,608.00 (non-core) | 0.00 (core) 624,003.00 (non-core) | 0.00 (core) 675,186.00 (non-core) | 0.00 (core) 775,000.00 (non-core) | 0.00 (core) 3,225,921.00 (non-core) |
| Total Resources for impact area 3 |  |  | 64,500.00 (core) 1,045,442.00 (non-core) | 0.00 (core) 719,095.00 (non-core) | 70,000.00 (core) 1,276,503.00 (non-core) | 70,000.00 (core) 1,352,686.00 (non-core) | 70,000.00 (core) 1,582,500.00 (non-core) | 274,500.00 (core) 5,976,226.00 (non-core) |