

UN Women Strategic Note 2019-2023

**UN WOMEN Burundi COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact4 This strategic outcome focuses on SDGs 1, 3, 4, 5, and 16. The focus will be on three areas:  1. More commitments on women, peace and security are implemented by Member States and the UN system, and more gender equality advocates influence peace and security processes. 2. More women play a greater role and are better served by humanitarian response and recovery efforts. 3. More women play a greater role in and are better served by disaster risk management processes.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: The strategic outcome is related to 2019-2023 UNDAF Vision: Eliminate poverty in all its forms and reduce inequalities and vulnerabilities in Burundi through a sustained resilience approach. It aspires to ensure the prosperity and well-being of women and men, while protecting the planet and strengthening the foundations of peace. It is related to UNDAF pillar 1 (person / inclusion - dignity – equality) & pillar 4 (prosperity / transformation – sustainability)pillar and two UNDAF outcomes: 1.Outcome 3: By 2023 more women, youth and vulnerable groups are integrated at the socio-economic, political and social welfare levels. 2; Outcome 5: By 2023, national and decentralized authorities adopt and implement mechanisms for crisis and disaster risk management and prevention, sustainable management of natural resources (water, land, forest), mitigation and adaptation to Climate Change and Ecosystem Protection to Enhance Community Resilience Related national development priorities:** | | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Year 2023** | **Total** |
| **Outcome 4.1 An environment for the implementation of WPS commitment is enable in Burundi through the participation and influence of key governmental and non governmental stakeholders  Related SP Outcome/Output:**   **Indicator 4.1A:** Proportion of women Peace mediators providing information to and influencing local security structures to prevent and resolve conflicts **Targets:  Value:** 80% **Notes:** Women’ mediators report **Target Year:** 2010 **Value:** 80% **Target Year:** 2020 **Value:** 60% **Notes:** Women'mediators report **Target Year:** 2021 **Baseline:  Value:** 40% **Year:** 2019 **Note:** Women’ mediators report **Source:** Reports from gender ministry  **Indicator 4.1B:** % of NAP 1325 provisions that are incorporated and budgeted in national security, defense, home affairs and local development and policies **Targets:  Value:** 20 **Notes:** Survey and activity reports **Target Year:** 2023 **Value:** 20 **Notes:** SURVEY AND ACTIVITY REPORT **Target Year:** 2020 **Value:** 30 **Notes:** Survey and activity reports **Target Year:** 2021 **Baseline:  Value:** 20 **Year:** 2019 **Note:** Survey and activity reports **Source:** Survey and activity reports | **Output 4.1.1 Capacities of key Government departments , Parliamentarians, UN Agencies, CSOs and gender advocates strengthened to lead implementation of accountability frameworks on WPS as well as gender responsive budgeting, COVID 19 prevention, response and recovery Plans.** | **Indicator 4.1.1A:** Number of strategic advocacy events, dialogues etc, led by trained Women Parliamentarians and other gender advocates towards implementation of the NAP 1325 and NGP to prevent and resolve conflicts **Targets:  Value:** 12 **Notes:** 6 more advocacy events: 3 led by Women Parliamentarians, 3 led gender advocates **Target Year:** 2019 **Value:** 18 **Notes:** 6 more advocacy events **Target Year:** 2020 **Value:** 30 **Notes:** 6 more advocacy events **Target Year:** 2022 **Value:** 30 **Notes:** ongoing advocacy event **Target Year:** 2023 **Value:** 30 **Notes:** 6 more advocacy and awareness raising events with the Parliament ( newly elected women leaders at all levels and middle level appointed women in the administration (ministries) on GEWE **Target Year:** 2021 **Value:** 30 **Notes:** 6 more advocacy and awareness raising events with the Parliament ( newly elected women leaders at all levels and middle level appointed women in the administration (ministries) on GEWE **Target Year:** 2021 **Value:** 30 **Target Year:** 2022 **Baseline:  Value:** 24 **Year:** 2021 **Notes:** 6 more in 2020 (1 Advocacy for Women in Parliament on women effective leadership and networking, 2 strategic advocacy events for the promotion of women in community elections on women organization, and political parties , 3 strategic events for women leaders on women empowerment and leadership with OPDAD, CIFL, ... ) **Source:** Partners's reports  **Indicator 4.1.1B:** Number of gender responsive budgets and/or strategies developed by national institutions to implement conflict prevention and conflict resolution commitments in accordance with the National Action Plan (NAP) on Res1325 and the National Gender Policy **Targets:  Value:** 4 **Notes:** 1 more Ministry : Ministry Agriculture and Environment **Target Year:** 2020 **Value:** 5 **Notes:** 1 more Ministry **Target Year:** 2021 **Value:** 6 **Notes:** 1 more Ministry **Target Year:** 2022 **Value:** 3 **Notes:** 1 more: Home Affairs Ministry and Local development **Target Year:** 2019 **Value:** 7 **Notes:** Ministry of National defense and veterans, Ministry of Education, Ministry of Security, Ministry Agriculture and Environment, Home Affairs and International cooperation Ministry **Target Year:** 2023 **Value:** 4 **Notes:** 1 more ministry **Target Year:** 2020 **Value:** 4 **Notes:** One more: Ministry of Agriculture **Target Year:** 2021 **Value:** 7 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2021 **Notes:** 2 Ministries of Gender and ministry of Home affairs and local development **Source:** Activity Reports of those mechanisms  **Indicator 4.1.1C:** Number of Regional/Global Women and Peace Networks/movements in which Burundi women advocates and WPM participate in **Targets:  Value:** 7 **Target Year:** 2020 **Value:** 8 **Target Year:** 2021 **Value:** 10 **Target Year:** 2022 **Baseline:  Value:** 8 **Year:** 2021 **Notes:** FEMWISE, African women leaders, Regional women forum/ICGLR **Source:** Partners ‘reports | 30,000.00 (core)  220,483.00 (non-core) | 30,000.00 (core)  200,000.00 (non-core) | 30,000.00 (core)  200,000.00 (non-core) | 30,000.00 (core)  200,000.00 (non-core) | 30,000.00 (core)  210,000.00 (non-core) | 150,000.00 (core)  1,030,483.00 (non-core) |
| **Output 4.1.2 Women’s rights and peace organizations, including women peace mediators have capacities,resources and opportunities to lead, participate in local structures for conflict prevention, conflict resolution, peacebuilding as well as local response to Covid19 pandemic (localization of the WPS agenda)** | **Indicator 4.1.2A:** Number of trained Women mediators and other community leaders participating substantially in peace and recovery processes at local level. **Targets:  Value:** 500 **Notes:** WPM (250) women leaders in administration and others from CSO (250) **Target Year:** 2019 **Value:** 700 **Notes:** WPM (350) women leaders in administration and others from CSO (350) **Target Year:** 2022 **Value:** 3000 **Notes:** 200 more Women Peace mediators, women leaders in administration, elected women and 200 others from CSO + 2600 from the 4 previous year **Target Year:** 2023 **Value:** 800 **Target Year:** 2021 **Value:** 800 **Target Year:** 2021 **Value:** 1000 **Target Year:** 2022 **Value:** 3000 **Target Year:** 2023 **Baseline:  Value:** 5000 **Year:** 2021 **Notes:** 534 Women Peace mediators (WPM) and 314 women leaders in administration  Target reached and surpassed in 2021. 5000 Women leaders capacitated **Source:** Women Peace Network Report   **Indicator 4.1.2B:** % of local peace and security structures receiving and integrating women’s early warning information to prevent and resolve conflicts **Targets:  Value:** 20% **Notes:** Communal council **Target Year:** 2019 **Value:** 20% **Notes:** Continue with communal council **Target Year:** 2020 **Value:** 40% **Notes:** Mixt committee of local security **Target Year:** 2021 **Value:** 60% **Notes:** 20% more General assembly at hill level +60% Communal security council, Mixt committee of local security, Communal council and local planning structures **Target Year:** 2022 **Value:** 80% **Notes:** Local planning structures **Target Year:** 2023 **Value:** 60% **Target Year:** 2022 **Value:** 60% **Target Year:** 2022 **Value:** 60% **Target Year:** 2022 **Baseline:  Value:** 40% **Year:** 2021 **Notes:** 1 Communal Security Council **Source:** WPM reports  **Indicator 4.1.2C:** % of increase in women's participation at hill level governance mechanism **Targets:  Value:** 20% **Target Year:** 2020 **Value:** 20% **Notes:** CENI report **Target Year:** 2021 **Value:** 20% **Target Year:** 2023 **Baseline:  Value:** 17% **Year:** 2021 **Notes:** Indicator that can no longer be reported because the election period has passed **Source:** rapport des élections   **Indicator 4.1.2D:** Number of women and girls participating in COVID 19 prevention, capacity building initiatives implemented with support from UN Women **Targets:  Value:** 250 **Notes:** les rapports du bureau ONU Femmes **Target Year:** 2020 **Value:** 500 **Target Year:** 2022 **Baseline:  Value:** 500 **Year:** 2021 **Notes:** rapports ONU femmes  indicator reached and surpassed for 2021 **Source:** Les rapports du bureau ONU femmes | 5,194.00 (core)  1,465,954.00 (non-core) | 35,194.00 (core)  810,620.00 (non-core) | 35,194.00 (core)  539,815.00 (non-core) | 35,194.00 (core)  539,815.00 (non-core) | 35,194.00 (core)  539,815.00 (non-core) | 145,970.00 (core)  3,896,019.00 (non-core) |
| **Output 4.1.3 The UNDS in Burundi has capacities and ressources to integrate GEWE in policy advice and cooperation frameworks** | **Indicator 4.1.3A:** Number of UNCT SWAP Scorecard recommandations implemented **Targets:  Value:** 10 **Notes:** GTG progress reports on implementation of the Gender Scorecard Action plan **Target Year:** 2022 **Baseline:  Value:** 5 **Year:** 2021 **Source:** Gender score card action plan  **Indicator 4.1.3B:** Existence of a Burundi Country Gender Equality Profile **Targets:  Value:** yes **Target Year:** 2022 **Baseline:  Value:** no **Year:** 2021 **Source:** UNW annual report   **Indicator 4.1.3C:** Existence of a joint program on the Common Chapter integrating gender issues with UN Women, UNDP, UNICEF, UNFPA **Targets:  Value:** yes **Target Year:** 2022 **Baseline:  Value:** no **Year:** 2021 **Source:** UNCT meeting | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) |
| **Outcome 4.2 Women, including those in refugees/ IDPS camps and other vulnerable situations, experience enhanced safety, security, physical and mental health, and their human rights respected in conformity with ratified regional and international instruments  Related SP Outcome/Output:**   **Indicator 4.2A:** Number of communities and media houses implementing strategies to eliminate gender stereotypes and negative social norms **Targets:  Value:** 7 **Target Year:** 2010 **Value:** 27 **Target Year:** 2021 **Value:** 29 **Target Year:** 2020 **Value:** 13 **Target Year:** 2019 **Baseline:  Value:** 13 **Year:** 2019 **Note:** UN Women report **Source:** Reports from communities and media  **Indicator 4.2B:** % of VAW victims and survivors using coordinated EVAW referral mechanisms **Targets:  Value:** 60 **Notes:** Ministry of gender Annual Report **Target Year:** 2023 **Value:** 35 **Notes:** Ministry of gender Annual Report & One stop center report **Target Year:** 2021 **Value:** 30 **Target Year:** 2020 **Value:** 29 **Target Year:** 2019 **Baseline:  Value:** 30 **Year:** 2020 **Note:** Ministry of Gender Annual Report **Source:** Ministry of Gender Annual Report | **Output 4.2.1 Women, girls, men and boys at community level, media and community leaders are mobilized in favor of respectful relationships and gender equality for peaceful co-existence and fight against Covid 19.** | **Indicator 4.2.1B:** Number of media and community organizations programs focusing on modifying gender stereotypes, promoting respectful relationships and gender equality taking in account COVID-19 context, including in IDP and refugee camps **Targets:  Value:** 11 **Notes:** 5 more **Target Year:** 2019 **Value:** 27 **Notes:** 16 more **Target Year:** 2020 **Value:** 27 **Notes:** Ongoing **Target Year:** 2021 **Value:** 27 **Notes:** On going activities **Target Year:** 2022 **Value:** 27 **Notes:** ongoing activities **Target Year:** 2023 **Value:** 27 **Notes:** Ongoing activities with the same community organizations and media **Target Year:** 2021 **Value:** 27 **Notes:** Ongoing activities with the same community organizations and media **Target Year:** 2022 **Baseline:  Value:** 27 **Year:** 2021 **Notes:** 6 Community networks against VAWG, 3 media services (Isanganiro, National Radio, Iijwi ry’amahoro) **Source:** Women mediators reports  **Indicator 4.2.1C:** Existence of a National Strategy on Social and behavioral change to address negative social norms, elaborated with UNW support. **Targets:  Value:** yes **Notes:** Activity report /Gender Ministry **Target Year:** 2019 **Value:** yes **Notes:** target reached **Target Year:** 2020 **Value:** Yes **Notes:** Target reached **Target Year:** 2021 **Value:** YES **Notes:** target reached **Target Year:** 2022 **Baseline:  Value:** yes **Year:** 2021 **Notes:** Activity report /Gender Ministry **Source:** Activity reports from gender clubs   **Indicator 4.2.1D:** Number of gender and youth inclusive community spaces (youth clubs, peace huts, etc) leading inter-generational EVAW, COVID-19, conflict prevention and conflict resolution initiatives, created and supported by UN women **Targets:  Value:** 12 **Notes:** Activity report **Target Year:** 2019 **Value:** 12 **Notes:** Activity report **Target Year:** 2020 **Value:** 18 **Notes:** Activity report **Target Year:** 2021 **Value:** 40 **Notes:** 10 new youth clubs /Activity report **Target Year:** 2022 **Value:** 42 **Notes:** Activity report **Target Year:** 2023 **Baseline:  Value:** 30 **Year:** 2021 **Source:** Activity report   **Indicator 4.2.1E:** Number of provinces with access to timely and accurate information on COVID-19 from UN Women **Targets:  Value:** 15 **Notes:** target reached **Target Year:** 2021 **Value:** 17 **Notes:** ongoing activities / Target reached **Target Year:** 2022 **Value:** 10 **Notes:** The target refers to the population of 10 out of 18 provinces of the country t **Target Year:** 2023 **Baseline:  Value:** 13 **Year:** 2021 **Source:** Radio reports | 25,000.00 (core)  215,000.00 (non-core) | 25,000.00 (core)  150,000.00 (non-core) | 25,000.00 (core)  150,000.00 (non-core) | 0.00 (core)  245,000.00 (non-core) | 25,000.00 (core)  150,000.00 (non-core) | 100,000.00 (core)  910,000.00 (non-core) |
| **Output 4.2.2 Law enforcement, Defense, justice and social services are capacitated to provide quality, effective and coordinated services to victims and survivors of VAWG including those affected by elections and COVID-19** | **Indicator 4.2.2A:** Number of structures demonstrating appropriate VAWG case management skills in line with agreed SoPs. **Targets:  Value:** 6 **Notes:** 3 more **Target Year:** 2019 **Value:** 8 **Notes:** 2 more **Target Year:** 2021 **Value:** 10 **Notes:** 2 more **Target Year:** 2022 **Value:** 12 **Notes:** ongoing activity **Target Year:** 2023 **Value:** 8 **Notes:** An assesment on sectoral services related to health, security, judicial, decentralized services (CDFC) will inform the status of compliance with aggreeded SOPs **Target Year:** 2020 **Baseline:  Value:** 8 **Year:** 2021 **Notes:** Activity reports **Source:** Assesment report   **Indicator 4.2.2B:** Number of women victims or survivors benefiting from coordinated EVAW referral mechanisms **Targets:  Value:** 966 **Notes:** Activity report **Target Year:** 2020 **Value:** 1195 **Notes:** 10% MORE **Target Year:** 2021 **Value:** 1971 **Notes:** on going monitoring **Target Year:** 2023 **Value:** 1669 **Notes:** Données collectées au Centre Humura **Target Year:** 2022 **Baseline:  Value:** 1518 **Year:** 2021 **Notes:** Activity report /Centre Humura/ from January to September 2018 **Source:** Activity report /Centre Humura/ from January to September 2019  **Indicator 4.2.2C:** Number of media productions on gender-sensitive early warnings and fight against COVID-19 initiatives, in collaboration with women mediators' initiatives disseminated by UNW support **Targets:  Value:** 50 **Notes:** 50 more productions **Target Year:** 2019 **Value:** 70 **Notes:** 70 more productions **Target Year:** 2020 **Value:** 95 **Notes:** 70 more productions **Target Year:** 2021 **Value:** 150 **Notes:** 60 more productions **Target Year:** 2022 **Value:** 300 **Notes:** 3 more media ( to be selected) will be involved to make production on gender sensitive early warning conflicts **Target Year:** 2023 **Value:** 70 **Target Year:** 2021 **Value:** 150 **Target Year:** 2022 **Baseline:  Value:** 100 **Year:** 2021 **Notes:** 60 media productions made by 2 media ( IJWI RYUMUKENYEZI ( voice of the woman & ISANGANIRO **Source:** annual reports | 25,000.00 (core)  250,000.00 (non-core) | 25,000.00 (core)  150,000.00 (non-core) | 25,000.00 (core)  150,000.00 (non-core) | 5,000.00 (core)  140,400.00 (non-core) | 15,000.00 (core)  100,000.00 (non-core) | 95,000.00 (core)  790,400.00 (non-core) |
| **Output 4.2.3 National and community decision-makers have the capacities and resources to enforce and account for women and girls’ human rights in line with ratified regional and international standards.** | **Indicator 4.2.3A:** Number of Police, Prosecutors, Judges and informal justice personnel with skills and capacities to administer justice for women and girls **Targets:  Value:** 900 **Target Year:** 2022 **Value:** 900 **Target Year:** 2023 **Value:** 900 **Target Year:** 2022 **Value:** 800 **Target Year:** 2022 **Baseline:  Value:** 591 **Year:** 2021 **Notes:** Activity reports/Justice and Security Ministry **Source:** Activity reports/Justice and Security Ministry   **Indicator 4.2.3B:** Existence of a National multi-sectoral CEDAW/Women’s Rights Reporting Committee producing quality and timely periodic women’s rights reports and monitoring implementation of recommendations, in line with regional/global guidelines (CEDAW/UNSCR 1325/Beijing Platform/SDGEA, etc **Targets:  Value:** YES **Notes:** The national committee existe **Target Year:** 2019 **Value:** yes **Notes:** The national committee exists **Target Year:** 2020 **Value:** yes **Notes:** The national committee continue his mission on reporting, follow up all due reporting from national normative framework and disseminating recommendations related to them. **Target Year:** 2023 **Value:** yes **Target Year:** 2021 **Value:** YES **Notes:** Target reached **Target Year:** 2022 **Baseline:  Value:** yes **Year:** 2021 **Source:** ACTIVITY REPORT   **Indicator 4.2.3C:** Number of campaigns and other social mobilization events organized on women’s rights per year. **Targets:  Value:** 2 **Notes:** 2 campaigns in 2019 and 1 campaign per year on women’ rights. **Target Year:** 2019 **Value:** 1 **Notes:** 1 campaign on identified issue **Target Year:** 2022 **Value:** 5 **Notes:** 5 campaigns at all **Target Year:** 2023 **Value:** 3 **Notes:** 1 campaign on Generation Equality **Target Year:** 2020 **Value:** 4 **Target Year:** 2021 **Value:** 3 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2021 **Source:** Activity report | 30,000.00 (core)  199,107.00 (non-core) | 30,000.00 (core)  199,107.00 (non-core) | 30,000.00 (core)  199,107.00 (non-core) | 30,000.00 (core)  199,107.00 (non-core) | 25,000.00 (core)  165,000.00 (non-core) | 145,000.00 (core)  961,428.00 (non-core) |
| **Outcome 4.3 Women and girls participate in and benefit from socio-economic recovery opportunities in the context of peace and resilience-building  Related SP Outcome/Output:**   **Indicator 4.3A:** Percentage of women having access to financial, social and economic services tailored to their needs in UN Women project areas **Targets:  Value:** 20 **Notes:** Survey and activity reports of previous project with UNDP **Target Year:** 2023 **Value:** 10 **Notes:** Survey and activity reports **Target Year:** 2021 **Value:** 7.9 **Target Year:** 2020 **Baseline:  Value:** 7.9 **Year:** 2019 **Note:** Survey and activity reports of previous project with UNDP **Source:** Survey and activity reports of previous project with UNDP  **Indicator 4.3B:** Number of households that have reduced chronic malnutrition with UN Women's Support **Targets:  Value:** 50000 **Notes:** ISTEEBU/Agricultural Survey **Target Year:** 2023 **Value:** 5000 **Notes:** ISTEEBU **Target Year:** 2021 **Value:** 0 **Target Year:** 2019 **Value:** 0 **Target Year:** 2020 **Baseline:  Value:** 0 **Year:** 2018 **Note:** ISTEEBU/Agricultural Survey **Source:** ISTEEBU/DHS report | **Output 4.3.2 A critical mass of women farmers and women entrepreneurs have the capacities to participate in and benefit from climate resilient agriculture value chains (production, aggregation & marketing) in normal, humanitarian and Covid-19 contexts.** | **Indicator 4.3.2A:** Number of women farmers’ cooperatives created or strengthened, accessing land and technology for improved productivity of maize and rice, with UNW’s support **Targets:  Value:** 100 **Notes:** Security Ministry (1) , National defense Ministry (2) , Justice Ministry (3) , Gitega (4) and Bubanza (5) communal structures **Target Year:** 2023 **Value:** 9 **Notes:** 2 news cooperatives by each of the 3 provinces (Bubanza, Bujumbura Rural, Cibitoke) A cooperative is formed by several groups/associations **Target Year:** 2019 **Value:** 9 **Notes:** ongoing **Target Year:** 2020 **Value:** 91 **Notes:** The number have been reached **Target Year:** 2021 **Value:** 100 **Notes:** Even reached, UN women still going on setting other cooperatives as it is the priority of the governement. **Target Year:** 2022 **Value:** 100 **Notes:** 9 more cooperatives **Target Year:** 2022 **Baseline:  Value:** 91 **Year:** 2021 **Notes:** Number Cooperatives previously set up **Source:** Activity reports  **Indicator 4.3.2B:** Number of micro finance/banks institutions implementing traditional and innovative financing products to support women farmers, with UNW support. **Targets:  Value:** 1 **Notes:** all the 4 financial institutions must participle to valid the mechanism operationalization **Target Year:** 2019 **Value:** 2 **Notes:** partnership signed to give credits and others financial services **Target Year:** 2020 **Value:** 2 **Notes:** Ongoing/Access to credit **Target Year:** 2021 **Value:** 6 **Notes:** 2 commercial banks & 2 Microfinance institutions **Target Year:** 2023 **Value:** 4 **Notes:** 2 more institutions **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** $ 568 000 put by UN WOMEN at the disposal of Central Bank of Burundi for women’ groups since 2013 to improve their access to credit **Source:** Joint Agreement- Ministry of Gender, UNW and Central Bank   **Indicator 4.3.2C:** Existence of a Burundi Women trading network in agri-products internally and with other countries **Targets:  Value:** NO **Target Year:** 2019 **Value:** NO **Target Year:** 2020 **Value:** NO **Target Year:** 2021 **Value:** Yes **Target Year:** 2022 **Value:** Yes **Target Year:** 2023 **Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2021 **Notes:** new initiative **Source:** activity reports | 28,084.00 (core)  320,000.00 (non-core) | 30,000.00 (core)  375,000.00 (non-core) | 30,000.00 (core)  375,000.00 (non-core) | 75,607.00 (core)  294,200.00 (non-core) | 80,000.00 (core)  150,000.00 (non-core) | 243,691.00 (core)  1,514,200.00 (non-core) |
| **Output 4.3.3 Women leaders and female heads of households promote women's voice and leadership in the production, transformation, marketing and consumption of nutritious local foods products in UNWOMEN project areas.** | **Indicator 4.3.3A:** Number of women/girls and boys with capacities to transform and add value to local food products for household consumption . **Targets:  Value:** 1000 **Notes:** 500 more to be trained **Target Year:** 2023 **Value:** 500 **Notes:** 500 to be trained **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Activity reports  **Indicator 4.3.3C:** Number of national policies/strategies/programmes on nutrition integrating gender aspects. **Targets:  Value:** 2 **Notes:** One more policy document is adopted **Target Year:** 2022 **Value:** 1 **Notes:** One more policy document is adopted **Target Year:** 2021 **Value:** 4 **Notes:** Two more policy document is adopted **Target Year:** 2023 **Baseline:  Value:** 2 **Year:** 2022 **Source:** Activity reports | 65,194.00 (core)  234,863.00 (non-core) | 65,194.00 (core)  232,363.00 (non-core) | 65,194.00 (core)  232,363.00 (non-core) | 2,000.00 (core)  129,600.00 (non-core) | 60,000.00 (core)  150,000.00 (non-core) | 257,582.00 (core)  979,189.00 (non-core) |
| **Output 4.3.4 Women and girls who are IDPs, returnees, victims/survivors of VAW have the capacities to participate in and benefit from recovery and resilience responses in humanitarian including Covid -19 context as well as regain their dignity in real time.** | **Indicator 4.3.4A:** Number of women and girls affected by natural disaster assisted with dignity kits in humanitarian and Covid-19 response. **Targets:  Value:** 0 **Notes:** UN Women will continue sport the victims **Target Year:** 2019 **Value:** 3000 **Notes:** Ongoing **Target Year:** 2020 **Value:** 6000 **Notes:** The target have been reached but as natural disasters often occur, UN Women will continue providing support to the affected peoples (women, girls, poeple with disabilities, children, ...). **Target Year:** 2021 **Value:** 8000 **Notes:** On going **Target Year:** 2022 **Value:** 10000 **Notes:** On going **Target Year:** 2023 **Baseline:  Value:** 6000 **Year:** 2021 **Source:** Activity reports  **Indicator 4.3.4B:** Number of humanitarian actors and women leaders members of the mixt security committee participate in Covid-19 recovery and resilience plan. **Targets:  Value:** 0 **Target Year:** 2020 **Value:** 146 **Notes:** On going **Target Year:** 2021 **Value:** 246 **Notes:** Ongoing **Target Year:** 2022 **Value:** 346 **Notes:** Ongoing **Target Year:** 2023 **Baseline:  Value:** 146 **Year:** 2021 **Source:** Activity reports  **Indicator 4.3.4C:** Number of women and girls affected by natural disasters involved in income generating activities **Targets:  Value:** 1000 **Notes:** UN Women supported 1000 women to integrate VSLA and start income generating activities for victims of gatumba flooding **Target Year:** 2020 **Value:** 1000 **Notes:** Ongoing **Target Year:** 2021 **Value:** 2000 **Notes:** Un Women will continue supporting womens victim of natural disasters **Target Year:** 2022 **Value:** 3000 **Notes:** Ongoing **Target Year:** 2023 **Baseline:  Value:** 1000 **Year:** 2021 **Source:** Activity reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 2,000.00 (core)  117,280.00 (non-core) | 50,000.00 (core)  100,000.00 (non-core) | 52,000.00 (core)  217,280.00 (non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | | | 35,194.00 (core)  1,686,437.00 (non-core) | 65,194.00 (core)  1,010,620.00 (non-core) | 65,194.00 (core)  739,815.00 (non-core) | 65,194.00 (core)  739,815.00 (non-core) | 65,194.00 (core)  749,815.00 (non-core) | 295,970.00 (core)  4,926,502.00 (non-core) |
| **Total Resources for outcome 4.2 (core and non-core)** | | | 80,000.00 (core)  664,107.00 (non-core) | 80,000.00 (core)  499,107.00 (non-core) | 80,000.00 (core)  499,107.00 (non-core) | 35,000.00 (core)  584,507.00 (non-core) | 65,000.00 (core)  415,000.00 (non-core) | 340,000.00 (core)  2,661,828.00 (non-core) |
| **Total Resources for outcome 4.3 (core and non-core)** | | | 93,278.00 (core)  554,863.00 (non-core) | 95,194.00 (core)  607,363.00 (non-core) | 95,194.00 (core)  607,363.00 (non-core) | 79,607.00 (core)  541,080.00 (non-core) | 190,000.00 (core)  400,000.00 (non-core) | 553,273.00 (core)  2,710,669.00 (non-core) |
| **Total Resources for impact area 4** | | | 208,472.00 (core)  2,905,407.00 (non-core) | 240,388.00 (core)  2,117,090.00 (non-core) | 240,388.00 (core)  1,846,285.00 (non-core) | 179,801.00 (core)  1,865,402.00 (non-core) | 320,194.00 (core)  1,564,815.00 (non-core) | 1,189,243.00 (core)  10,298,999.00 (non-core) |