

UN Women Strategic Note 2022-2026

**UN WOMEN Bangladesh COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |
| --- | --- |
| **Impact1Women and girls in Bangladesh will be empowered to realise their human rights across the humanitarian-development continuum** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: The people of Bangladesh – especially the most vulnerable and marginalized – contribute to and benefit equitably from the integrated social, environmental and economic dimensions of sustainable and inclusive development under the 8th Five Year Plan, leading to achievement of the 2030 Agenda, its SDGs and the country’s Perspective Plan for 2021-2041Related national development priorities:** |
|  |  |  | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Year2026** | **Total** |
| **Outcome 1.1By 2026, more people in Bangladesh, particularly the most vulnerable and marginalized from all gender and social groups and those from lagging districts benefit from sustainable livelihood and decent work opportunities resulting from responsible, inclusive, sustainable, green, and equitable economic developmentRelated SP Outcome/Output:****Indicator 1.1A:** The number of national and/or local multi-sectoral policies and/or action plans that are adopted with a focus on gender equality (0.1.5)**Targets: Value:** 4**Target Year:** 2026**Value:** 0**Target Year:** 2022**Value:** 1**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Source:** National policies/plan **Indicator 1.1B:** The number of innovative financing instruments developed with gender equality objectives (0.2.4)**Targets: Value:** 2**Target Year:** 2026**Value:** 0**Target Year:** 2022**Value:** 1**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Source:** National documents, databases and programmes | **Output 1.1.1The government, at both the national and sub-national levels, has enhanced capacities to draft laws, policies and practices promoting inclusive and resilient women’s economic empowerment, gender-responsive green growth and decent work (including addressing unpaid care and domestic work and supporting informal sector workers), with support from UN Women** | **Indicator 1.1.1A:** The number of partners (MoWCA, MoLE, MoEWOE, BMET, etc) that have an increased capacity to formulate policies, laws and action plans with a focus on gender-responsive, inclusive and sustainable economic development, with UN Women’s support (0.1.e)**Targets: Value:** 4**Target Year:** 2026**Value:** 1**Target Year:** 2022**Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Notes:** MoEWOE**Source:** National and/or local WEE polices, laws and action plans available on various ministry websites**Indicator 1.1.1B:** A roadmap to address unpaid and domestic care work available with MoWCA and MoLE, with support from UN Women**Targets: Value:** Yes**Target Year:** 2026**Value:** No**Target Year:** 2022**Value:** Yes**Target Year:** 2023**Baseline: Value:** No **Year:** 2021**Source:** Roadmap on the MoWCA website **Indicator 1.1.1C:** The number of multi-stakeholder dialogue processes aimed at promoting the engagement of the governments with CSOs and other partners to advance inclusive women’s economic empowerment (0.1.h)**Targets: Value:** 10**Target Year:** 2026**Value:** 5**Target Year:** 2022**Value:** 5**Target Year:** 2023**Baseline: Value:** 3 **Year:** 2021**Source:** Report/ meeting minutes from partners**Indicator 1.1.1D:** The number of policies/strategies supported to advance gender-responsive and inclusive economic growth and resilience (i.e. increased decent work and green businesses opportunities for women, youth and other vulnerable groups) (CF indicators (SP1, output 1-1) led by UN Women:1.1.1)**Targets: Value:** 2**Target Year:** 2026**Value:** 1**Target Year:** 2022**Value:** 1**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Source:** Policies/strategies on the Ministry of Expatriates’ Welfare and Overseas Employment’s website | 49,075.00(core)0.00(non-core) | 40,300.00(core)0.00(non-core) | 65,000.00(core)0.00(non-core) | 60,000.00(core)0.00(non-core) | 65,000.00(core)0.00(non-core) | 279,375.00(core)0.00(non-core) |
| **Output 1.1.2Women workers, employees and entrepreneurs, in particular migrant workers, internally displaced women, WWDs and indigenous women, have enhanced knowledge, capacities and agency to demand and benefit from gender-responsive public and private services and skills for green jobs and decent work opportunities at home and abroad, and to influence related policies, regulations and practices (i.e. the national social protection system, renewable energy and low carbon technology).** | **Indicator 1.1.2A:** The number of women workers who receive gender-responsive services (i.e. capacity development services and economic opportunities) and support vulnerable women workers in enhancing access to decent work at home and abroad (0.4.d)**Targets: Value:** 15000**Target Year:** 2026**Value:** 4500**Target Year:** 2022**Value:** 7000**Target Year:** 2023**Baseline: Value:** 2000 **Year:** 2021**Notes:** women workers (returnee migrant workers and tea garden workers)**Source:** Impact assessment report from partner**Indicator 1.1.2B:** The number of dialogues and/or platforms supported that enable participation and the effective engagement of gender equality advocates, workers rights' organizations and CSOs working on GEWE, in government policy and legislative decision-making processes (0.5c).**Targets: Value:** 12**Notes:** 10 dialogues and 2 Platforms**Target Year:** 2026**Value:** 7**Target Year:** 2022**Value:** 9**Target Year:** 2023**Baseline: Value:** 5 **Year:** 2021**Notes:** 4 dialogues and 1 platform (Gender Monitoring Network)**Source:** Partner reports**Indicator 1.1.2C:** A charter of demands to advocate and demand for WEE, prepared by women’s organizations, with the goal of influencing policies and laws. (0.5.b).**Targets: Value:** Yes**Target Year:** 2026**Value:** No**Target Year:** 2022**Value:** No**Target Year:** 2023**Baseline: Value:** No **Year:** 2021**Source:** A charter of demand made available on UN Women’s website | 25,000.00(core)200,000.00(non-core) | 30,000.00(core)200,000.00(non-core) | 33,000.00(core)0.00(non-core) | 38,000.00(core)0.00(non-core) | 38,000.00(core)0.00(non-core) | 164,000.00(core)400,000.00(non-core) |
| **Output 1.1.3Women-led or women-oriented enterprises cottage, micro, small and medium enterprises, with an enhanced capacity to implement gender-responsive and green business policies, practices and services** | **Indicator 1.1.3A:** The number of enterprises, including women-led or women-oriented enterprises (especially those with a majority female workforce, suppliers or consumers) especially SMEs that have received services (i.e. capacity development services and advisory services) on WEPs (04.a).**Targets: Value:** 20**Notes:** Enterprises**Target Year:** 2026**Value:** 4**Notes:** Enterprises**Target Year:** 2022**Value:** 9**Notes:** Enterprises**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Notes:** Enterprises**Source:** Partner reports**Indicator 1.1.3B:** The number of participants from enterprises, especially women-led or women-oriented enterprises, who have increased knowledge on the WEPs, especially among those with a majority female workforce, suppliers or consumers**Targets: Value:** 80**Notes:** Participants**Target Year:** 2022**Value:** 380**Notes:** Participants**Target Year:** 2026**Value:** 180**Notes:** Participants**Target Year:** 2023**Baseline: Value:** 20 **Year:** 2021**Notes:** Participants**Source:** Partner reports**Indicator 1.1.3C:** The number of enterprises that have gender-responsive and green action plans (focusing on green business products, services, operations and business models), especially among women-led or women-oriented enterprises or those with a majority female workforce, suppliers or consumers**Targets: Value:** 2**Notes:** Enterprises**Target Year:** 2022**Value:** 4**Notes:** Enterprises**Target Year:** 2023**Value:** 10**Notes:** Enterprises**Target Year:** 2026**Baseline: Value:** 0 **Year:** 2021**Notes:** Enterprises**Source:** Partner reports | 0.00(core)283,795.00(non-core) | 0.00(core)404,571.00(non-core) | 0.00(core)629,878.00(non-core) | 0.00(core)629,878.00(non-core) | 0.00(core)629,878.00(non-core) | 0.00(core)2,578,000.00(non-core) |
| **Outcome 1.2By 2026, ecosystems are healthier, and all people, in particular the most vulnerable and marginalized in both rural and urban settings, benefit from and contribute to, in a gender responsive manner, a cleaner environment, an enriched natural resource base, low carbon development, and are more resilient to climate change, shocks and disastersRelated SP Outcome/Output:****Indicator 1.2A:** The number of DRR and climate change-related policies and/or action plans that are gender-responsive after receiving UN Women’s support (0.1.5)**Targets: Value:** 6**Notes:** SOD, National Plan for Disaster Management 2021-2025, Climate Change Gender Action Plan, Department of Women Affair's Disaster Management Plan, Gender Guideline for BCCT, National Plan for Disaster Management 2026-2031**Target Year:** 2026**Value:** 4**Notes:** 2022 Target is 2. Since cumulative, so 2022 target stands baseline value (2) plus 2022 target (2) which is 4.**Target Year:** 2022**Value:** 5**Notes:** 2023 Target is 1. Since cumulative, so 2023 target stands baseline value (2) plus 2022 target (2) and 2023 target (1) which is 5.**Target Year:** 2023**Baseline: Value:** 2 **Year:** 2021**Note:** SOD and National Plan for Disaster Management 2021-2025**Source:** GoB circular**Indicator 1.2B:** The number of women’s capacity to cope with disasters and climatic shocks enhanced**Targets: Value:** 5700**Target Year:** 2026**Value:** 2700**Notes:** 2022 Target 0. Since cumulative so 2022 target remains the same as the baseline value.**Target Year:** 2022**Value:** 2900**Notes:** 2023 Target is 200. Since cumulative, so 2023 target stands baseline value (2700) plus 2023 target (200) which is 2900 in total.**Target Year:** 2023**Baseline: Value:** 2700 **Year:** 2021**Source:** Project Report | **Output 1.2.1Women, in particular the most vulnerable to climate change, natural disasters and environmental hazards, have the required knowledge and skills to lead and influence climate action, and have increased access to the relevant resources (i.e. resilient infrastructure and basic services, information, finance, capacity and technology) needed to adapt to and mitigate the effects of climate change and related disasters** | **Indicator 1.2.1A:** The number of disaster vulnerable women and girls supported by UN Women who have economic skills, goods, finance, information and other resources and services to withstand the effects of disasters and climatic events (04d)**Targets: Value:** 5200**Target Year:** 2026**Value:** 2700**Notes:** 2022 Target 0. Since cumulative so 2022 target remains the same as the baseline value.**Target Year:** 2022**Value:** 2900**Notes:** 2023 Target is 200. Since cumulative, so 2023 target stands baseline value (2700) plus 2023 target (200) which is 2900.**Target Year:** 2023**Baseline: Value:** 2700 **Year:** 2021**Source:** Partner reports**Indicator 1.2.1B:** The number of women and girls with increased leadership capacity to lead and participate in public life with regards DRR and CCA in their communities, with UN Women’s support (05e)**Targets: Value:** 6000**Target Year:** 2026**Value:** 2981**Notes:** 2022 Target 0. Since cumulative so 2022 target remains the same as the baseline value.**Target Year:** 2022**Value:** 3300**Notes:** 2023 Target is 319. Since cumulative, so 2023 target stands baseline value (2981) plus 2023 target (319) which is 3300.**Target Year:** 2023**Baseline: Value:** 2981 **Year:** 2021**Notes:** (2,700 Disaster vulnerable women + 155 women DMC member + 126 CSO representative)**Source:** Partner reports**Indicator 1.2.1C:** The number of CSOs, including women's rights organizations, accessing knowledge, tools and financing to effectively engage in policy advocacy and implement DRR, CCA and humanitarian actions to reduce risks and build resilience among women and girls (CF SP 3 Output 1 indicator)**Targets: Value:** 100**Target Year:** 2026**Value:** 56**Notes:** 2022 Target 0. Since cumulative so 2022 target same as the baseline value.**Target Year:** 2022**Value:** 76**Notes:** 2023 Target is 20. Since cumulative, so 2023 target stands baseline value (56) plus 2023 target (20) which is 76.**Target Year:** 2023**Baseline: Value:** 56 **Year:** 2021**Source:** Partner reports  | 0.00(core)88,000.00(non-core) | 40,000.00(core)300,000.00(non-core) | 40,000.00(core)700,000.00(non-core) | 40,000.00(core)800,000.00(non-core) | 40,000.00(core)600,000.00(non-core) | 160,000.00(core)2,488,000.00(non-core) |
| **Output 1.2.2National and local-level government institutions, CSOs and private sector actors are capacitated and supported with the necessary skills, knowledge and evidence to address GEWE and promote women’s leadership in DDR, CCA and resilience building** | **Indicator 1.2.2A:** Percentage of climate and disaster risk assessments and post-disaster need assessments that provide SADDD and deploy a gender analysis as an integral part of its assessment, with UN Women’s support (04a) (CF SP 3 Output 2 indicator).**Targets: Value:** 80%**Target Year:** 2026**Value:** 50%**Notes:** 2022 Target 0. Since cumulative so 2022 target remains the same as the baseline value.**Target Year:** 2022**Value:** 60%**Notes:** 2023 Target is 10%. Since cumulative, so 2023 target stands baseline value (50%) plus 2023 target (10%) which is 60%.**Target Year:** 2023**Baseline: Value:** 50% **Year:** 2021**Source:** Assessment reports by GoB **Indicator 1.2.2B:** The number of institutions that received support from UN Women to produce and implement gender-responsive policies, plans and strategies related to DRR and CCA. (07b)**Targets: Value:** 9**Notes:** MoDMR, DWA, MOWCA, LGED, Programming Division, BCCT, DoE, DDM, MoEFCC**Target Year:** 2026**Value:** 5**Target Year:** 2022**Value:** 6**Target Year:** 2023**Baseline: Value:** 5 **Year:** 2021**Notes:** MoDMR, DWA, MOWCA, LGED, Programming Division**Source:** Partner reports | 52,725.00(core)85,000.00(non-core) | 25,000.00(core)500,000.00(non-core) | 25,000.00(core)400,000.00(non-core) | 25,000.00(core)400,000.00(non-core) | 25,000.00(core)300,000.00(non-core) | 152,725.00(core)1,685,000.00(non-core) |
| **Output 1.2.3Multi-stakeholder, inter-sectoral and multi-level coordination groups, platforms, networks, and forums are supported and/or strengthened to effectively coordinate and oversee gender-responsive DRR and humanitarian actions** | **Indicator 1.2.3A:** The number of platforms and/or coalitions supported to enable the meaningful participation, effective and safe engagement of gender advocates and CSOs in decision-making to advance GEWE in DRR and humanitarian situations (05c)**Targets: Value:** 4**Target Year:** 2026**Value:** 1**Target Year:** 2022**Value:** 2**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** Partner reports  | 0.00(core)70,343.00(non-core) | 0.00(core)20,000.00(non-core) | 0.00(core)25,000.00(non-core) | 0.00(core)20,000.00(non-core) | 0.00(core)20,000.00(non-core) | 0.00(core)155,343.00(non-core) |
| **Outcome 1.3By 2026, more people, especially the most vulnerable, benefit from more equitable, non-discriminatory, gender-responsive, participatory, accountable governance and justice, in a peaceful and tolerant society governed by the rule of law.Related SP Outcome/Output:****Indicator 1.3A:** Existence of an adopted NAP WPS with monitoring and coordination mechanisms in place (0.1.7)**Targets: Value:** Yes**Target Year:** 2026**Value:** Yes**Target Year:** 2022**Value:** Yes**Target Year:** 2023**Baseline: Value:** No **Year:** 2020**Source:** Coordination Group Meeting minutes/NAP WPS annual report**Indicator 1.3B:** The number of CSOs participating in the coordination and monitoring mechanism to implement the NAP WPS (0.5.4)**Targets: Value:** 2**Target Year:** 2026**Value:** 2**Target Year:** 2022**Value:** 2**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Source:** Coordination Group meeting minutes/NAP WPS annual report | **Output 1.3.1Government institutions have strengthened capacities to promote and implement CEDAW general recommendations, concluding observations 2016 and the WPS agenda (including the NAP on UNSCR 1325) to realize gender equality, non-discrimination and the empowerment of women and promote peace and social cohesion** | **Indicator 1.3.1A:** The existence of functional multi-stakeholder coordination group supported by UN Women to promote the engagement of the government and civil society partners to advance the WPS agenda (the creation of a NAP WPS coordination mechanism) (0.1.h)**Targets: Value:** Yes**Target Year:** 2026**Value:** Yes**Target Year:** 2022**Value:** Yes**Target Year:** 2023**Baseline: Value:** No **Year:** 2021**Source:** Coordination Group meeting minutes **Indicator 1.3.1B:** Existence of a functional consultative platform for the NAP WPS that enables meaningful, effective and safe participation and engagement among gender advocates and CSOs working on GEWE in decision-making to advance WPS agenda (0.5.c)**Targets: Value:** Yes**Target Year:** 2026**Value:** Yes**Target Year:** 2022**Value:** Yes**Target Year:** 2023**Baseline: Value:** No **Year:** 2021**Source:** Partner reports**Indicator 1.3.1C:** The number of ministries with increased knowledge/capacities to advance GEWE through national and/or local multi-sectoral strategies, policies and/or action plans (0.1.e) (CF Output indicator under SP4)**Targets: Value:** 5**Notes:** (MoE, MoLJ, MoF and LGD**Target Year:** 2026**Value:** 2**Target Year:** 2022**Value:** 3**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Notes:** MOWCA**Source:** Partner reports | 70,000.00(core)126,272.00(non-core) | 80,000.00(core)134,745.00(non-core) | 100,000.00(core)135,745.00(non-core) | 90,000.00(core)134,746.00(non-core) | 90,000.00(core)136,746.00(non-core) | 430,000.00(core)668,254.00(non-core) |
| **Output 1.3.2Women’s groups and youth groups have strengthened skills and knowledge to promote positive social norms in support of women’s human rights and to build resilient, cohesive and peaceful societies** | **Indicator 1.3.2A:** The number of CSOs, including women's rights, community-based, religious and youth organizations, that have strengthened capacity to exercise their leadership role and participate in citizen engagement activities to build resilient, cohesive and peaceful, gender-equal societies. (0.5.d)**Targets: Value:** 56**Target Year:** 2026**Value:** 40**Target Year:** 2022**Value:** 44**Target Year:** 2023**Baseline: Value:** 36 **Year:** 2021**Source:** Partner reports**Indicator 1.3.2B:** The number of women from excluded groups (ethnic minorities, WWDs, etc) and young women who have increased leadership skills and capacities to build resilient, cohesive and peaceful gender-equal societies (0.5.e)**Targets: Value:** 4375**Target Year:** 2026**Value:** 2680**Target Year:** 2022**Value:** 2880**Target Year:** 2023**Baseline: Value:** 2480 **Year:** 2020**Source:** Partner reports  | 0.00(core)76,272.00(non-core) | 0.00(core)134,745.00(non-core) | 0.00(core)134,746.00(non-core) | 0.00(core)134,746.00(non-core) | 0.00(core)134,746.00(non-core) | 0.00(core)615,255.00(non-core) |
| **Outcome 1.4By 2026, women, girls and gender diverse people benefit from an environment in which they are empowered to exercise their rights, agency and decision-making power over all aspects of their lives and are free from all forms of discrimination, violence and harmful norms and practicesRelated SP Outcome/Output:****Indicator 1.4A:** Percentage of UNCT-SWAP Gender Equality Scorecard requirements met or exceeded by UNCT Bangladesh in the past four years (derived from QCPR indicator 1.4.15) (0.7.2)**Targets: Value:** 60%**Target Year:** 2026**Value:** 26.6%**Target Year:** 2022**Value:** 26.6%**Target Year:** 2023**Baseline: Value:** 26.6% **Year:** 2021**Note:** 4 out of 15 indicators met/exceeded requirements in 2019 comprehensive review**Source:** Scorecard Annual and comprehensive reports**Indicator 1.4B:** SDG 5.1.1: The existence of legal frameworks to promote, enforce and monitor equality and non-discrimination on the basis of sex (UNFPA,UNICEF, UNDP, UNAIDS) (0.1.3)**Targets: Value:** Yes**Target Year:** 2026**Value:** No**Target Year:** 2022**Value:** No**Target Year:** 2023**Baseline: Value:** No **Year:** 2021**Source:** Annual report **Indicator 1.4C:** Percentage of national budget allocated to GEWE out of the total budget (0.2.3) (Similar to CF indicator 5.c)**Targets: Value:** 35%**Target Year:** 2026**Value:** 32%**Target Year:** 2022**Value:** 32%**Target Year:** 2023**Baseline: Value:** 32% **Year:** 2021**Source:** Gender Budget Report-Finance Division**Indicator 1.4D:** The number of government institutions demonstrating a use of gender statistics, analysis and policy research. (0.6.3)**Targets: Value:** 3**Target Year:** 2026**Value:** 1**Target Year:** 2022**Value:** 2**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** Annual report**Indicator 1.4E:** The number of institutions putting policies and practices I place to address gender-based discrimination, GBV and/or combat gender stereotypes (0.3.2)**Targets: Value:** 10**Target Year:** 2026**Value:** 5**Target Year:** 2022**Value:** 6**Target Year:** 2023**Baseline: Value:** 4 **Year:** 2021**Note:** NAP VAWC, SH Policy Comilla University, DC Cumilla, Victoria College**Source:** Project report | **Output 1.4.1Government institutions have strengthened capacities to mainstream GEWE into public policies, laws, plans, financing strategies, institutional frameworks and data collection processes, in line with global GE standards, including for VAW prevention and reduction** | **Indicator 1.4.1A:** The number of institutions that have increased capacity/knowledge with UN Women’s support to design and implement non-discriminatory and gender-responsive institutional reforms, strategies and policies (0.1.f) (CF indicator 5.1.4)**Targets: Value:** 9**Notes:** 3 DC office in Comilla, Bogura, Patuakhali, 2 UPs, UGC, 2 factories, 1 Chamber of Commerce and industry**Target Year:** 2022**Value:** 10**Notes:** 3 DC Office Cumilla, Bogura, Patuakhali, 2 UPs, UGC, 3 factories, 1 Chambers of Commerce and Industry**Target Year:** 2023**Value:** 13**Notes:** Police, Judiciary, Union Parishad, Factories, District Commissioners Office, Chambers of Commerce and Industry CCI.**Target Year:** 2026**Baseline: Value:** 7 **Year:** 2021**Notes:** 2 DC Comilla &Bogura 2 UP; UGC, 2 factories**Source:** Partner reports**Indicator 1.4.1B:** The number of national and local partners (women’s groups) with capacities to apply gender-responsive budgeting tools to their budget cycle with UN Women's support (0.2.c & 0.6.c) (CF indicator 5.1.6)**Targets: Value:** 26**Target Year:** 2022**Value:** 27**Target Year:** 2023**Value:** 30**Notes:** national ministries, division and local government organizations**Target Year:** 2026**Baseline: Value:** 25 **Year:** 2021**Notes:** national ministries and divisions**Source:** Partner reports**Indicator 1.4.1C:** # of gender finance assessments conducted**Targets: Value:** 2**Notes:** Development Finance Assessment and Financing Strategy for SDGs**Target Year:** 2026**Value:** 1**Target Year:** 2022**Value:** 1**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Source:** Partner report **Indicator 1.4.1D:** The number of gender data collection initiatives, including in emerging areas (VAW in humanitarian situations, gender and environment nexus, etc.), conducted or analysed with support of UN Women (0.6.c)**Targets: Value:** 1**Notes:** VAW/G prevalence survey**Target Year:** 2026**Value:** 0**Target Year:** 2022**Value:** 1**Notes:** VAWG prevalence survey**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Source:** Survey report | 86,657.00(core)784,423.00(non-core) | 12,000.00(core)1,606,396.00(non-core) | 47,000.00(core)700,000.00(non-core) | 47,000.00(core)500,000.00(non-core) | 47,000.00(core)500,000.00(non-core) | 239,657.00(core)4,090,819.00(non-core) |
| **Output 1.4.2Selected public sector service providers (law enforcement and judiciary) and civil society service providers have strengthened capacities to deliver high-quality and comprehensive gender-responsive and survivor-centred VAW services in line with international standards, with UN Women’s support.** | **Indicator 1.4.2A:** The number of institutions and partners who have strengthened capacities and knowledge to increase and improve the provision of essential and gender-responsive VAW services, goods and resources for women and girls in line with international norms and standards, with support from UN Women (0.4.a) (CF Indicator 5.1.5).**Targets: Value:** 2**Notes:** 1 Police Station (Dhaka) 1 Shelter based NGO**Target Year:** 2022**Value:** 3**Notes:** 1 Police Station, 1 Shelter based NGO , 1 Women Judges Association**Target Year:** 2023**Value:** 6**Notes:** (Tarango, Police, 3 Shelter based NGOs, Judiciary**Target Year:** 2026**Baseline: Value:** 1 **Year:** 2021**Notes:** Tarango**Source:** Partner reports | 10,000.00(core)12,400.00(non-core) | 10,000.00(core)50,000.00(non-core) | 10,000.00(core)175,000.00(non-core) | 10,000.00(core)175,000.00(non-core) | 10,000.00(core)175,000.00(non-core) | 50,000.00(core)587,400.00(non-core) |
| **Output 1.4.3Civil society, especially WLOs and youth networks, have strengthened capacities, budgets and access to platforms that facilitate their engagement with government actors and enable them to influence policies promoting GEWE and eliminating VAW.** | **Indicator 1.4.3A:** The number of dialogues, mechanisms and platforms created and sustained by gender advocates, youth networks and CSOs (with UN Women’s support) focused on meaningful participation and dialogue with the government to influence GEWE and VAW prevention policies (05 c) (CF indicator - 5.2.2).**Targets: Value:** 5**Notes:** CSAG, Rape law Coalition, domestic violence coalition, 1 National Policy Dialogues, 1 media network**Target Year:** 2022**Value:** 6**Notes:** CSAG, Rape law coalition, domestic violence coalition, 2 National Dialogue, 1 media network**Target Year:** 2023**Value:** 10**Notes:** CSAG, Rape law coalition, domestic violence coalition, National dialogues, shelter network**Target Year:** 2026**Baseline: Value:** 4 **Year:** 2021**Notes:** CSAG, Rape law coalition, domestic violence coalition+ 1 National Dialogue**Source:** Partner reports**Indicator 1.4.3B:** The number of CSOs, especially women’s rights organizations, that have strengthened capacity to exercise their leadership role in advancing the GEWE agenda, with UN Women’s support (05 d)**Targets: Value:** 16**Notes:** RPs of EVAW**Target Year:** 2022**Value:** 16**Notes:** RPs of EVAW**Target Year:** 2023**Value:** 20**Target Year:** 2026**Baseline: Value:** 12 **Year:** 2021**Source:** Quarterly/annual report | 20,000.00(core)64,250.00(non-core) | 10,000.00(core)175,000.00(non-core) | 10,000.00(core)67,500.00(non-core) | 10,000.00(core)67,500.00(non-core) | 10,000.00(core)67,500.00(non-core) | 60,000.00(core)441,750.00(non-core) |
| **Output 1.4.4The government, public and private Institutions and CSOs have strengthened capacities to adapt and/or implement evidence-driven strategies and to promote knowledge generation, coordination, advocacy and partnerships to advance social norms that prevent VAW** | **Indicator 1.4.4A:** The number of evidence and/or practice-based standardized approaches or models for social norms and individual behaviour change on VAW prevention and response, which UN Women partners are supported to utilise (03 a)**Targets: Value:** 4**Notes:** SASA, WSA,SOSJ, RESPECT**Target Year:** 2022**Value:** 4**Notes:** SASA, WSA,SOSJ, RESPECT**Target Year:** 2023**Value:** 5**Notes:** SASA, WSA, SOSJ, RESPECT framework on Prevention & Essential Service Package for women and girls subject to violence**Target Year:** 2026**Baseline: Value:** 3 **Year:** 2021**Notes:** 1 community based, SASA; 1 whole of school approach (WSA); 1 family based SOSJ**Source:** Partner reports**Indicator 1.4.4B:** The number of women and men reached through evidence- and practice-based VAW prevention interventions (0.3.f) (CF Indicator 5.2.1).**Targets: Value:** 7621**Notes:** 7621(3948 women, 3673men)**Target Year:** 2022**Value:** 9121**Notes:** 9121 (4948 women, 4173 men)**Target Year:** 2023**Value:** 15121**Notes:** 15,121 (7,500 women, 7,621 men)**Target Year:** 2026**Baseline: Value:** 5121 **Year:** 2021**Notes:** 2,948 women, 2,173 men**Source:** Partner reports | 0.00(core)285,534.00(non-core) | 10,000.00(core)285,885.00(non-core) | 10,000.00(core)347,500.00(non-core) | 10,000.00(core)347,500.00(non-core) | 10,000.00(core)347,500.00(non-core) | 40,000.00(core)1,613,919.00(non-core) |
| **Output 1.4.5The Bangladesh UNCT has increased access to technical assistance, capacity building support, and resources (incl. data/tools/guidance) to facilitate the full implementation of agreed-upon actions of the UNCT SWAP-GE Comprehensive Assessment, and enhance system-wide accountability and inter-agency coordination on GEWE through UN Women’s support** | **Indicator 1.4.5A:** The number of thematic interagency mechanisms/teams supported to effectively address gender mainstreaming in priority areas (0.7.a)**Targets: Value:** 10**Notes:** Target: 10 (GETG + UNSDCF Strategic Pillar 5+ MnE+ HR group+ Procurement group+ OMT+ 4 SP groups)**Target Year:** 2026**Value:** 7**Notes:** Target: 7 [GETG + UNSDCF Strategic Pillar 5+ MnE +HR subgroup +3 (OMT/Procurement subgroup+ SP1 and SP2 under JPF)]**Target Year:** 2022**Value:** 8**Notes:** Target: 8 [GETG + UNSDCF Strategic Pillar 5+ MnE +HR subgroup +3 (OMT/Procurement subgroup+ SP1 and SP2 under JPF)] + UNCG**Target Year:** 2023**Baseline: Value:** 4 **Year:** 2021**Notes:** Baseline: 4 (GETG + UNSDCF Strategic Pillar 5+ MnE +HR subgroup)**Source:** GETG AWP, Scorecard annual report and action plan**Indicator 1.4.5B:** The number of interagency products or services with a focus on GEWE, developed with the support of UN Women (0.7.c)**Targets: Value:** 15**Notes:** 1 PSHAA module, 1 IPV resource book, 1 PSHAA training, 1 CNA plan, 1 HR parity strategy, 1 GR procurement database, 1 CGEP, 1 Scorecard Action Plan, Services: 2 Training on GEM and MnE, 5 services from UNCT capacity building plan**Target Year:** 2026**Value:** 8**Notes:** Target: 8 [ 3 baseline: (1 PSHAA module, 1 IPV resource book, 1 PSHAA training) + 4 products (CNA plan, Gender parity strategy, GR Proc database, SSA Roaster) 1 service (training on GEM)**Target Year:** 2022**Value:** 12**Notes:** Target: 8 [ 3 baseline: (1 PSHAA module, 1 IPV resource book, 1 PSHAA training) + 2022 [4 products (CNA plan, Gender parity strategy, GR Proc database, SSA Roaster) 1 service (training on GEM) ] + 2 product (1 CGEP, 1 knowledge inventory) 2 service (training based on CNA) ]**Target Year:** 2023**Baseline: Value:** 3 **Year:** 2021**Notes:** 1 PSHAA module, 1 IPV resource book, 1 PSHAA training**Source:** GETG AWP, Scorecard Annual report **Indicator 1.4.5C:** The number of UN joint programmes related to gender equality in which UN Women participates as a Participating United Nations Organization (derived from QCPR indicator 1.4.17) (0.7.d)**Targets: Value:** 15**Notes:** NRP, IELD, WING, INFF4SDGs, Social protection for female tea garden workers, election project; NRP-2; JP with UNEP on Renewable energy and women farmers; GBV JP under UNSDCF JPF; GRG JP under UNSDCF JPF; Unpaid care economy with ILO; INFF4SDGs; WING; Reintegration migration project with ILO, IOM; joint PVE project with UNDP, UNOCT, UNODC, IOM, UN RCO**Target Year:** 2026**Value:** 8**Notes:** Target: 8 [6 baseline: (NRP, IELD, WING, INFF4SDGs, Social protection for female tea garden workers, Election)+ 2 (NRP2, Reintegration project with ILO)]**Target Year:** 2022**Value:** 9**Notes:** Target: 10 [6 baseline: (NRP, IELD, WING, INFF4SDGs, Social protection for female tea garden workers. Election Project)+ 2 (NRP2, Reintegration project with ILO) + (2 new projects under JPF) ]**Target Year:** 2023**Baseline: Value:** 6 **Year:** 2021**Notes:** NRP, IELD, WING, INFF4SDGs, Social protection for female tea garden workers, Election project**Source:** Project register, Prodocs, AWP annual reports | 50,054.00(core)0.00(non-core) | 60,254.00(core)0.00(non-core) | 50,254.00(core)0.00(non-core) | 55,254.00(core)0.00(non-core) | 45,254.00(core)0.00(non-core) | 261,070.00(core)0.00(non-core) |
| **Outcome 1.5By 2026 more women and girls are empowered by gender responsive enabling environment, to exercise their agency and decision-making with improved access to protection, education, and socio-economic opportunities.Related SP Outcome/Output:****Indicator 1.5A:** The number of women in Rohingya and host communities who access services provided by UN Women after experiencing violence or discrimination (0.4.1)**Targets: Value:** 278992 **Target Year:** 2026**Value:** 231289**Target Year:** 2022**Value:** 244192**Target Year:** 2023**Baseline: Value:** 168957 **Year:** 2021**Source:** Project progress reports | **Output 1.5.1Women and girls from both the Rohingya community and host community have increased capacities to participate meaningfully in decision making and access multi-sectorial services, protection, education, and socio-economic opportunities** | **Indicator 1.5.1A:** The number of women and girls who have access to skills/capacities, goods, resources and services through gender-responsive platforms, mechanisms and products supported by UN Women in the development/ humanitarian setting of Cox’s Bazar (04 d)**Targets: Value:** 278992**Target Year:** 2026**Value:** 231289**Target Year:** 2022**Value:** 244192**Target Year:** 2023**Baseline: Value:** 168957 **Year:** 2021**Source:** Partner reports | 62,327.00(core)3,372,379.00(non-core) | 0.00(core)2,196,736.00(non-core) | 62,000.00(core)600,000.00(non-core) | 62,000.00(core)600,000.00(non-core) | 62,000.00(core)600,000.00(non-core) | 248,327.00(core)7,369,115.00(non-core) |
| **Output 1.5.2Rohingya and host community women and WLOs have enhanced advocacy and leadership capacities to promote GEWE, GBV prevention and response, and social cohesion** | **Indicator 1.5.2A:** The number of local women groups/networks that have access to tools and resources to deliver and monitor the quality of services, resources and goods for women and girls in humanitarian, conflict and development settings (04 c)**Targets: Value:** 12**Notes:** Continued**Target Year:** 2026**Value:** 12**Target Year:** 2022**Value:** 12**Notes:** Continued**Target Year:** 2023**Baseline: Value:** 4 **Year:** 2021**Notes:** local women rights organizations and grassroots networks**Source:** Partner reports**Indicator 1.5.2B:** The number of Rohingya community women who have been trained and received peer support and mentorship in performing advanced leadership in their communities**Targets: Value:** 800**Notes:** Continued**Target Year:** 2026**Value:** 800**Target Year:** 2022**Value:** 800**Notes:** continued**Target Year:** 2023**Baseline: Value:** 50 **Year:** 2021**Source:** Partner reports | 0.00(core)1,229,317.00(non-core) | 0.00(core)50,000.00(non-core) | 0.00(core)500,000.00(non-core) | 0.00(core)500,000.00(non-core) | 0.00(core)500,000.00(non-core) | 0.00(core)2,779,317.00(non-core) |
| **Output 1.5.3Humanitarian actors’ (including WLOs) coordination mechanisms, leadership and gender-responsive programming capacities in Cox’s Bazar are enhanced** | **Indicator 1.5.3A:** The number of sectors/working groups with strengthened capacities and knowledge to increase and improve the provision of essential and gender-responsive services, goods and resources for women and girls (04 a)**Targets: Value:** 8**Notes:** as several sectors will be merged in the next phase in Rohingya response. There is an ongoing ISCG exercise to streamline the coordination mechanism in CXB.**Target Year:** 2026**Value:** 8**Notes:** as several sectors will be merged in the next phase in Rohingya response. There is an ongoing ISCG exercise to streamline the coordination mechanism in CXB**Target Year:** 2022**Value:** 8**Notes:** as several sectors will be merged in the next phase in Rohingya response. There is an ongoing ISCG exercise to streamline the coordination mechanism in CXB**Target Year:** 2023**Baseline: Value:** 9 **Year:** 2021**Notes:** sectors and their partners**Source:** Project progress report, assessment reports | 0.00(core)231,657.00(non-core) | 0.00(core)1,389,573.00(non-core) | 0.00(core)1,500,000.00(non-core) | 0.00(core)1,500,000.00(non-core) | 0.00(core)1,200,000.00(non-core) | 0.00(core)5,821,230.00(non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | 74,075.00(core)483,795.00(non-core) | 70,300.00(core)604,571.00(non-core) | 98,000.00(core)629,878.00(non-core) | 98,000.00(core)629,878.00(non-core) | 103,000.00(core)629,878.00(non-core) | 443,375.00(core)2,978,000.00(non-core) |
| **Total Resources for outcome 1.2 (core and non-core)** | 52,725.00(core)243,343.00(non-core) | 65,000.00(core)820,000.00(non-core) | 65,000.00(core)1,125,000.00(non-core) | 65,000.00(core)1,220,000.00(non-core) | 65,000.00(core)920,000.00(non-core) | 312,725.00(core)4,328,343.00(non-core) |
| **Total Resources for outcome 1.3 (core and non-core)** | 70,000.00(core)202,544.00(non-core) | 80,000.00(core)269,490.00(non-core) | 100,000.00(core)270,491.00(non-core) | 90,000.00(core)269,492.00(non-core) | 90,000.00(core)271,492.00(non-core) | 430,000.00(core)1,283,509.00(non-core) |
| **Total Resources for outcome 1.4 (core and non-core)** | 166,711.00(core)1,146,607.00(non-core) | 102,254.00(core)2,117,281.00(non-core) | 127,254.00(core)1,290,000.00(non-core) | 132,254.00(core)1,090,000.00(non-core) | 122,254.00(core)1,090,000.00(non-core) | 650,727.00(core)6,733,888.00(non-core) |
| **Total Resources for outcome 1.5 (core and non-core)** | 62,327.00(core)4,833,353.00(non-core) | 0.00(core)3,636,309.00(non-core) | 62,000.00(core)2,600,000.00(non-core) | 62,000.00(core)2,600,000.00(non-core) | 62,000.00(core)2,300,000.00(non-core) | 248,327.00(core)15,969,662.00(non-core) |
| **Total Resources for impact area 1** | 425,838.00(core)6,909,642.00(non-core) | 317,554.00(core)7,447,651.00(non-core) | 452,254.00(core)5,915,369.00(non-core) | 447,254.00(core)5,809,370.00(non-core) | 442,254.00(core)5,211,370.00(non-core) | 2,085,154.00(core)31,293,402.00(non-core) |