

UN Women Strategic Note 2018-2022

**UN WOMEN Bolivia COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact1 Gender-responsive and inclusive governance systems and institutions are key to ensuring the realization of women’s rights and the achievement of gender equality. Gender-response and inclusive governance depends on: ensuring gender equality is reflected in planning and budgeting; removing discriminatory laws and ensuring systems of recourse for women whose rights are not respected; giving women equal say in decision making processes; and ensuring that decision making is properly informed by evidence and data.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Outcome 4.2 of the UNDAF dedicated to increasing gender equality in Bolivia (in Spanish: Se ha fortalecido el ejercicio de los derechos de las mujeres, niñas, niños y adolescentes, promoviendo una vida sin violencia, la formulación e implementación de leyes, políticas y la provisión de servicios y presupuestos sensibles a género y derechos de la niñez, acorde con los compromisos internacionales que promueven la igualdad de género y generacional, la descolonización y la despatriarcalización). This outcome contributes in particular to SDGs 1, 5 and 10.  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 1.1 The State approves national legislation and implements public policies that promote intercultural and parity democracy and the full enjoyment of women’s rights, including indigenous women’s rights.  Related SP Outcome/Output:**   **Indicator 1.1A:** Number of legislative frameworks that promote gender balance in elections and decision-making bodies. **Targets:  Value:** 3 **Target Year:** 2019 **Value:** 3 **Target Year:** 2018 **Value:** 3 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Supreme Electoral Tribunal TSE  **Indicator 1.1B:** Number of gender equality reforms developed and/or being implemented by electoral stakeholders with UN-Women’s technical support **Targets:  Value:** 3 **Target Year:** 2018 **Value:** 3 **Target Year:** 2019 **Value:** 3 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Baseline:  Value:** 3 **Year:** 2017 **Source:** Observatory of Democratic Parity | **Output 1.1.1 Law 243 against harassment and gender-based political violence monitored and implemented** | **Indicator 1.1.1A:** Number of women leaders, candidates and aspirants with strengthened capacities to engage in political life, with UN-Women’s support. **Targets:  Value:** 2100 **Target Year:** 2021 **Value:** 1500 **Target Year:** 2018 **Value:** 1600 **Target Year:** 2019 **Value:** 1800 **Target Year:** 2019 **Value:** 1900 **Target Year:** 2020 **Value:** 2500 **Target Year:** 2022 **Baseline:  Value:** 1500 **Year:** 2016 **Source:** Women’s Organizations ACOBOL  **Indicator 1.1.1B:** Number of gender equality initiatives developed and/or being implemented by parliamentary bodies (Legislative Parliamentary Committees/ Women Caucus/ Speaker of Parliament’s Office/Secretariat of the Parliament), with UN-Women’s support. **Targets:  Value:** 3 **Target Year:** 2021 **Value:** 1 **Target Year:** 2018 **Value:** 1 **Target Year:** 2019 **Value:** 2 **Target Year:** 2020 **Value:** 2 **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2021 **Source:** Plurinational Legislative Assembly Official Gazette of the Plurinational State.   **Indicator 1.1.1C:** Number of initiatives developed and/or being implemented to monitor violence against women in politics, with UN-Women’s support. **Targets:  Value:** 3 **Target Year:** 2021 **Value:** 2 **Target Year:** 2018 **Value:** 2 **Target Year:** 2019 **Value:** 2 **Target Year:** 2020 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2017 **Source:** Plurinational Legislative Assembly | 0.00 (core)  1,000,000.00 (non-core) | 0.00 (core)  1,000,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 68,266.00 (core)  74,000.00 (non-core) | 98,000.00 (core)  197,733.00 (non-core) | 166,266.00 (core)  2,271,733.00 (non-core) |
| **Output 1.1.2 Enhanced capacities of female candidates and women politicians at national and local levels to apply leadership skills.** | **Indicator 1.1.2A:** Number of elected women and women politicians at the national and local level with the ability to apply leadership skills **Targets:  Value:** 65 **Target Year:** 2020 **Value:** 100 **Target Year:** 2021 **Value:** 200 **Target Year:** 2022 **Baseline:  Value:** 25 **Year:** 2017 **Source:** Women’s Organizations ACOBOL  **Indicator 1.1.2B:** Number of women leaders, candidates and aspirants with strengthened capacities to engage in political life, with UN-Women’s support **Targets:  Value:** 750 **Target Year:** 2020 **Value:** 1000 **Target Year:** 2021 **Value:** 1300 **Target Year:** 2022 **Baseline:  Value:** 250 **Year:** 2017 **Source:** Women’s Organizations (ACOBOL,AMADBOL)  **Indicator 1.1.2C:** Number of plural political dialogues incorporating the women's rights agenda in the electoral and Covid 19 response context **Targets:  Value:** 13 **Notes:** 1 National Event with guests 1 National Forum of Indigenous Women Candidates 1 National Forum of Young Candidates 9 Dialogue Forums in each Department **Target Year:** 2020 **Value:** 20 **Target Year:** 2021 **Value:** 25 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** NA **Source:** Memories of the Dialogues; Admin file Electoral Body | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 18,000.00 (core)  553,000.00 (non-core) | 2,000.00 (core)  152,984.00 (non-core) | 20,000.00 (core)  705,984.00 (non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | | | 0.00 (core)  1,000,000.00 (non-core) | 0.00 (core)  1,000,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 86,266.00 (core)  627,000.00 (non-core) | 100,000.00 (core)  350,717.00 (non-core) | 186,266.00 (core)  2,977,717.00 (non-core) |
| **Total Resources for impact area 1** | | | 0.00 (core)  1,000,000.00 (non-core) | 0.00 (core)  1,000,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 86,266.00 (core)  627,000.00 (non-core) | 100,000.00 (core)  350,717.00 (non-core) | 186,266.00 (core)  2,977,717.00 (non-core) |
| **Impact2 Women’s capacity to enjoy the rights, and support the rights of their families and communities, is fundamentally founded on their access to economic resources. Economic empowerment depends on an enabling policy environment that addresses issues such as unpaid care and access to land. It also requires opportunities for entrepreneurship and decent work that provides jobs, the opportunity to accumulate assets and enhanced income security. Women’s economic empowerment is key to attainment of all SDGs. UN-Women’s work in this areas is also guided by Agreed Conclusions of the CSW on this issue and the work of the Secretary- General’s High Level Panel on Women’s Economic Empowerment.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Outcome 4.2 of the UNDAF dedicated to increasing gender equality in Bolivia (in Spanish: Se ha fortalecido el ejercicio de los derechos de las mujeres, niñas, niños y adolescentes, promoviendo una vida sin violencia, la formulación e implementación de leyes, políticas y la provisión de servicios y presupuestos sensibles a género y derechos de la niñez, acorde con los compromisos internacionales que promueven la igualdad de género y generacional, la descolonización y la despatriarcalización). This outcome contributes in particular to SDGs 1, 5 and 10. Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 2.2 More Bolivian women, especially rural and indigenous women, have access to productive resources and assets, including access to renewable energy.  Related SP Outcome/Output:**   **Indicator 2.2A:** Number of new businesses led and managed by women **Targets:  Value:** 4 **Target Year:** 2021 **Value:** 1 **Target Year:** 2018 **Value:** 1 **Target Year:** 2019 **Value:** 1 **Target Year:** 2020 **Value:** 2 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Ministry of Productive Development and Plural Economy. SwissContact. RIMISP. | **Output 2.2.1 More policies promote decent work and social protection for women** | **Indicator 2.2.1A:** Number of women with increased access to appropriate technologies, machinery, fertilizers, improved seeds, pest control, etc. for sustainable agriculture. **Targets:  Value:** NA **Target Year:** 2021 **Value:** 15 **Target Year:** 2018 **Value:** 25 **Target Year:** 2019 **Value:** 150 **Target Year:** 2020 **Value:** 600 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Ministry of Productive Development and Plural Economy. SwissContact. RIMISP.   **Indicator 2.2.1B:** Percentage increase of women-led firms (medium scale & microenterprises) in rural areas targeted by the programme **Targets:  Value:** 20% **Target Year:** 2021 **Value:** 16% **Target Year:** 2018 **Value:** 16% **Target Year:** 2019 **Value:** 18% **Target Year:** 2020 **Value:** NA **Target Year:** 2022 **Baseline:  Value:** 15% **Year:** 2015 **Source:** INE: Economic Census Continuous Employment Survey, National Employment and Income Survey  **Indicator 2.2.1C:** Number of rural women supported to gain access, use and/or control of productive resources by UN-Women. **Targets:  Value:** NA **Target Year:** 2021 **Value:** 200 **Target Year:** 2018 **Value:** 600 **Target Year:** 2019 **Value:** 200 **Target Year:** 2020 **Value:** 100 **Target Year:** 2022 **Baseline:  Value:** 35 **Year:** 2017 **Source:** UN-Women’s Results Management System.  **Indicator 2.2.1D:** Number of women accessing financial services and products in response to the COVID 19 **Targets:  Value:** 100 **Target Year:** 2020 **Value:** 100 **Target Year:** 2022 **Baseline:  Value:** NA **Year:** 2019 **Source:** Administrative registry PROFIN  **Indicator 2.2.1E:** Number of women with strengthened capacities and skills to participate in the economy, including as entrepreneurs, with UN-Women’s support **Targets:  Value:** 150 **Target Year:** 2021 **Value:** 900 **Target Year:** 2022 **Baseline:  Value:** NA **Year:** 2020 **Source:** MTF Programme Reports  **Indicator 2.2.1F:** Number of legal, regulatory and/or policy frameworks in support of gender-responsive social protection systems that are developed and/or being implemented with support from UN-Women **Targets:  Value:** 1 **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Baseline:  Value:** o **Year:** 2020 **Source:** MPTF Proramme reports  **Indicator 2.2.1G:** Number of national and international signatories to the Women Empowerment Principles **Targets:  Value:** 50 **Target Year:** 2021 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 27 **Year:** 2019 **Source:** Global Compact Reports  **Indicator 2.2.1H:** Number of countries with strengthened capacities to undertake gender-responsive socio-economic impact assessments in response to the COVID-19 crisis, with a focus on at-risk populations **Targets:  Value:** 1 **Notes:** COVID 19 SP Indicator **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Baseline:  Value:** NA **Year:** 2020 **Source:** Servicio Plurinacional de la Mujer y Despatriarcalización | 35,000.00 (core)  985,703.00 (non-core) | 45,000.00 (core)  408,247.00 (non-core) | 45,000.00 (core)  350,000.00 (non-core) | 86,242.00 (core)  679,602.00 (non-core) | 67,500.00 (core)  2,113,953.00 (non-core) | 278,742.00 (core)  4,537,505.00 (non-core) |
| **Total Resources for outcome 2.2 (core and non-core)** | | | 35,000.00 (core)  985,703.00 (non-core) | 45,000.00 (core)  408,247.00 (non-core) | 45,000.00 (core)  350,000.00 (non-core) | 86,242.00 (core)  679,602.00 (non-core) | 67,500.00 (core)  2,113,953.00 (non-core) | 278,742.00 (core)  4,537,505.00 (non-core) |
| **Total Resources for impact area 2** | | | 35,000.00 (core)  985,703.00 (non-core) | 45,000.00 (core)  408,247.00 (non-core) | 45,000.00 (core)  350,000.00 (non-core) | 86,242.00 (core)  679,602.00 (non-core) | 67,500.00 (core)  2,113,953.00 (non-core) | 278,742.00 (core)  4,537,505.00 (non-core) |
| **Impact3 Prevalence of violence against women and girls remains alarmingly high. It destroys lives not only of those subjected to it, but also their families and communities. It places a strain on economies and societies. UN-Women’s work is also guided, inter alia, by the Agreed Conclusions of CSW 57. UN-Women works within the context of the Joint UN Prevention Framework** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Outcome 4.2 of the UNDAF dedicated to increasing gender equality in Bolivia (in Spanish: Se ha fortalecido el ejercicio de los derechos de las mujeres, niñas, niños y adolescentes, promoviendo una vida sin violencia, la formulación e implementación de leyes, políticas y la provisión de servicios y presupuestos sensibles a género y derechos de la niñez, acorde con los compromisos internacionales que promueven la igualdad de género y generacional, la descolonización y la despatriarcalización). This outcome contributes in particular to SDGs 1, 5 and 10. Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 3.1 Women victims of violence have increased access to quality essential services  Related SP Outcome/Output:**   **Indicator 3.1A:** Number of women who have experienced physical or sexual violence who seek help, at the police **Targets:  Value:** 74000 **Target Year:** 2021 **Value:** 25000 **Target Year:** 2018 **Value:** 25000 **Target Year:** 2019 **Value:** 25000 **Target Year:** 2020 **Baseline:  Value:** 46668 **Year:** 2017 **Source:** FELCV Prosecutor  SIPASSE  **Indicator 3.1C:** Number of guidelines, protocols, standard operating procedures (in line with best practices) on the provision of quality services for victims and survivors. **Targets:  Value:** 145 **Target Year:** 2021 **Value:** 35 **Target Year:** 2018 **Value:** 40 **Target Year:** 2019 **Value:** 40 **Target Year:** 2020 **Baseline:  Value:** 53 **Year:** 2017 **Source:** UN-Women’s Results Management System. | **Output 3.1.2 National legislation (the Comprehensive Law 348 to fight violence against women) and related policies implemented with UNW's technical assistance, advocacy and partnership building (including inter-agency coordination).** | **Indicator 3.1.2A:** Number of National Action Plans and Strategies to end violence against women that have a component that addresses social norms, attitudes, and behavior transformation, developed with UN-Women’s support. **Targets:  Value:** 3 **Target Year:** 2021 **Value:** 2 **Target Year:** 2018 **Value:** 2 **Target Year:** 2019 **Value:** 2 **Target Year:** 2020 **Value:** 4 **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2017 **Source:** Vice Ministry of equal opportunities reports and documents.  **Indicator 3.1.2B:** Number of guidelines, protocols, standard operating procedures (in line with best practices) on the provision of quality services for victims and survivors in the justice system in coordination with the Life without Violence Program (UNW-UNFPA). **Targets:  Value:** 2 **Target Year:** 2018 **Value:** 2 **Target Year:** 2019 **Value:** 2 **Target Year:** 2020 **Value:** 2 **Target Year:** 2021 **Value:** 4 **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2017 **Source:** Vice Ministry of equal opportunities reports and documents. Ministry of Justice  **Indicator 3.1.2C:** Number of countries that have adopted or strengthened legislation addressing violence against women and girls in private and public spaces that is (1) in line with best practices (2) is allocated a budget and (3) has an oversight mechanism for monitoring **Targets:  Value:** 1 **Notes:** Cualitative **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Baseline:  Value:** NA **Year:** 2020 **Source:** SDG Reports   **Indicator 3.1.2D:** Number of countries that have, with UN-Women’s support, put in place measures to address gender-based violence (GBV) during the COVID-19 pandemic, which:  a) integrate violence prevention and response into COVID-19 response plans b) raise awareness through advocacy and campaigns, with targeted messages to both women and men c) provide options for women to report abuse and seek help without alerting perpetrators d) ensure continued functioning of shelters for victims of violence and expand their capacity e) ensure women’s access to justice through police and justice response to address impunity of perpetrators and protect women and their children **Targets:  Value:** NA **Notes:** Cualitative **Target Year:** 2021 **Value:** NA **Target Year:** 2022 **Baseline:  Value:** NA **Year:** 2021 **Source:** Servicio Plurinacional de la Mujer y Despatriarcalización | 35,000.00 (core)  342,835.00 (non-core) | 44,000.00 (core)  117,074.00 (non-core) | 44,000.00 (core)  74,345.00 (non-core) | 17,165.00 (core)  102,036.00 (non-core) | 54,000.00 (core)  194,862.00 (non-core) | 194,165.00 (core)  831,152.00 (non-core) |
| **Output 3.1.5 More cities and other settings have safe and empowering public spaces for women and girls** | **Indicator 3.1.5A:** Number of safe cities/safe public spaces partnerships in place that promote women in decision-making positions **Targets:  Value:** 30 **Target Year:** 2018 **Value:** 40 **Target Year:** 2019 **Value:** 50 **Target Year:** 2020 **Value:** 65 **Target Year:** 2021 **Value:** 66 **Target Year:** 2022 **Baseline:  Value:** 10 **Year:** 2017 **Source:** Municipalities | 15,000.00 (core)  0.00 (non-core) | 15,000.00 (core)  0.00 (non-core) | 15,000.00 (core)  0.00 (non-core) | 12,500.00 (core)  33,500.00 (non-core) | 37,300.00 (core)  174,083.00 (non-core) | 94,800.00 (core)  207,583.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 50,000.00 (core)  342,835.00 (non-core) | 59,000.00 (core)  117,074.00 (non-core) | 59,000.00 (core)  74,345.00 (non-core) | 29,665.00 (core)  135,536.00 (non-core) | 91,300.00 (core)  368,945.00 (non-core) | 288,965.00 (core)  1,038,735.00 (non-core) |
| **Total Resources for impact area 3** | | | 50,000.00 (core)  342,835.00 (non-core) | 59,000.00 (core)  117,074.00 (non-core) | 59,000.00 (core)  74,345.00 (non-core) | 29,665.00 (core)  135,536.00 (non-core) | 91,300.00 (core)  368,945.00 (non-core) | 288,965.00 (core)  1,038,735.00 (non-core) |