

UN Women Strategic Note 2018-2022

**UN WOMEN Central African Republic COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact1 Governance and participation in public life** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: By 2021, political and administrative institutions and CSOs are promoting and frame the rule of law and good governance. Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 1.1 Central African women and girls of all ages fully participate, lead ans engage in political institutions and processes  Related SP Outcome/Output:**   **Indicator 1.1A:** Proportion of women in public decision-making positions **Targets:  Value:** 750 **Target Year:** 2020 **Value:** 1000 **Target Year:** 2021 **Value:** 35 **Target Year:** 2025 **Baseline:  Value:** 18 **Year:** 2021 **Source:** Office reports  **Indicator 1.1B:** Adoption of a national gender-sensitive budget **Targets:  Value:** 50 **Target Year:** 2020 **Value:** 50 **Target Year:** 2021 **Value:** 1 **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2021 **Source:** National budget amended ;  Office reports | **Output 1.1.1 Public actors, CSOs, women and girl leaders are able to advocate for an institutional framework conducive to women's leadership and political participation at local and national levels in CAR.** | **Indicator 1.1.1A:** Number of laws amended or adopted in accordance with the recommendations of the study on discriminatory laws **Targets:  Value:** 5 **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Office reports, RP reports; National Assembly Report  **Indicator 1.1.1B:** Number of violence against women during local elections **Targets:  Value:** 75 **Target Year:** 2020 **Value:** TBD **Target Year:** 2022 **Baseline:  Value:** TBD **Year:** 2021 **Source:** Office reports, RP reports  **Indicator 1.1.1C:** Number of public decision-makers and future managers who have to advocate for an institutional framework conducive to Women leadership and Political Participation at local and national level, with the support of UN Women country office. **Targets:  Value:** 2000 **Target Year:** 2022 **Baseline:  Value:** 889 **Year:** 2021 **Source:** Office report, | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  350,000.00 (non-core) | 0.00 (core)  350,000.00 (non-core) |
| **Output 1.1.3 More women of all ages have their capacities strengthened to fully participate, lead and engage in elecoral process** | **Indicator 1.1.3A:** Number of women leaders, candidates and aspirants with strengthened capacities to engage in electoral processes , with UN-Women’s support **Targets:  Value:** 1000 **Target Year:** 2022 **Baseline:  Value:** 889 **Year:** 2021 **Source:**  Activities reports  **Indicator 1.1.3B:** Number of people desagragate by sexe and age reached by civic education campaigns **Targets:  Value:** 3000 **Target Year:** 2022 **Baseline:  Value:** 00 **Year:** 2021 **Source:** Office reports, RP reports  **Indicator 1.1.3C:** Number of people benefiting from official documents **Targets:  Value:** 7000 **Target Year:** 2022 **Baseline:  Value:** 3500 **Year:** 2021 **Source:** Office report, RP activities report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  680,000.00 (non-core) | 0.00 (core)  680,000.00 (non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,030,000.00 (non-core) | 0.00 (core)  1,030,000.00 (non-core) |
| **Total Resources for impact area 1** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,030,000.00 (non-core) | 0.00 (core)  1,030,000.00 (non-core) |
| **Impact2 Women's Economic Empowerment** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: By 2021, political and administrative institutions, CSOs and the private sector implement programs and approaches that strengthen the resilience of urban and rural communities in the face of crises and climate change. Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 2.1 Rural women secure access to productive resources and engage in sustainable agriculture in Central Africa Republic  Related SP Outcome/Output:**   **Indicator 2.1A:** # of women beneficiaries of the project having increased their production and productivity and reduced their workload **Targets:  Value:** 1000 **Target Year:** 2020 **Value:** 1000 **Target Year:** 2021 **Value:** 1000 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** Activities report  **Indicator 2.1C:** Existence of the legal framework guaranteeing women's access to land and tenure security. **Targets:  Value:** yes **Target Year:** 2021 **Value:** yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2019 **Source:** Office report; final evaluation report | **Output 2.1.1 Women and girls have access to agricultural markets, services and products and have strengthened their capacities on organic farming and agroecology** | **Indicator 2.1.1C:** # of national actors mobilized to promote an environment protecting the rights of women and girls related to land **Targets:  Value:** 250 **Target Year:** 2020 **Value:** 250 **Target Year:** 2021 **Value:** 250 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** office report ; RP activities report; Final evaluation report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  639,193.00 (non-core) | 0.00 (core)  639,193.00 (non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  639,193.00 (non-core) | 0.00 (core)  639,193.00 (non-core) |
| **Total Resources for impact area 2** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  639,193.00 (non-core) | 0.00 (core)  639,193.00 (non-core) |
| **Impact4 Women Peace and Security, Humanitarian Action and Disastser Risk Reduction** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: By 2021, political and administrative institutions and CSOs promote and contribute to peacebuilding, security, national reconciliation and human rights Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 4.1 Women and girls affected by the conflict are supported for their recovery and play a role as actresses in peacebuilding  Related SP Outcome/Output:**   **Indicator 4.1A:** Percentage of women and youth, community leaders, reporting good mental health as a result of community-based psychological support mechanisms **Targets:  Value:** +30 **Target Year:** 2022 **Baseline:  Value:** TBD **Year:** 2021 **Source:** Project baseline study report; office annual report;  **Indicator 4.1B:** percentage of population ,disaggregated by sexe and age, who benefit of support community justice mechanisms in CAR, sensitive to psychosocial dimensions **Targets:  Value:** +30% **Target Year:** 2022 **Baseline:  Value:** TBD **Year:** 2021 **Source:** Office annual report | **Output 4.1.1 Women and girls, and particularly women leaders, are empowered to contribute to community reconciliation and national peacebuilding** | **Indicator 4.1.1A:** Availability of the status on existing formal and traditional justice mechanisms and their impact on the reconciliation process **Targets:  Value:** yes **Target Year:** 2022 **Baseline:  Value:** 00 **Year:** 2021 **Source:** Study report  **Indicator 4.1.1B:** Number of women community leaders who received psychosocial support through community based psychologists engaged in peacebuilding initiatives **Targets:  Value:** 60 **Target Year:** 2022 **Baseline:  Value:** 00 **Year:** 2021 **Source:** Office report; final evaluation report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 10,000.00 (core)  499,000.00 (non-core) | 10,000.00 (core)  499,000.00 (non-core) |
| **Output 4.1.4 Community justice mechanisms in CAR are inclusive, sensitive to psychosocial dimensions and contribute to social cohesion** |  | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  266,400.00 (non-core) | 0.00 (core)  266,400.00 (non-core) |
| **Output 4.1.5 Support the national architecture for the implementation of the Resolution 1325 on Women, Peace and Security, especially in defence and military sectors** |  | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 10,000.00 (core)  181,300.00 (non-core) | 10,000.00 (core)  181,300.00 (non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 20,000.00 (core)  946,700.00 (non-core) | 20,000.00 (core)  946,700.00 (non-core) |
| **Total Resources for impact area 4** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 20,000.00 (core)  946,700.00 (non-core) | 20,000.00 (core)  946,700.00 (non-core) |
| **Impact3 Ending violence against women** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: By 2021, the Central African populations, particularly the most vulnerable, or at risk of being so, will use basic social services in a sustainable manner, in particular health, education, social protection, water and sanitation according to quality standards. Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 3.1 Centralafrican state and stakeholders are better able to prevent violence against women and girls and deliver essential services to victims and survivors  Related SP Outcome/Output:**   **Indicator 3.1A:** Degree of women's confidence in formal justice and transitional justice. **Targets:  Value:** 60 **Target Year:** 2021 **Baseline:  Value:** 42 **Year:** 2019 **Source:** Office report ; final evaluation report | **Output 3.1.1 Community leaders, ex-combatants, justice actors and members of defence and security forces are sensitized on GBV prevention, Women and girl rights and HIV in CAR's conflicts areas.** | **Indicator 3.1.1A:** Number of justice actors trained on women's participation in justice mechanisms, transitional justice, protection of women's rights and prevention of GBV disaggregated by sexe, by age, by place of residence and by disabilities **Targets:  Value:** 900 **Target Year:** 2021 **Value:** 900 **Target Year:** 2022 **Baseline:  Value:** 700 **Year:** 2020 **Source:** UNW office report; RP report; final evaluation report  **Indicator 3.1.1D:** Number of victimes and survivors of GBV which recieve medical, psycosocial and recovery assistance with the technical and finacial support of UNW office. **Targets:  Value:** 2000 **Target Year:** 2021 **Value:** 2000 **Target Year:** 2022 **Baseline:  Value:** 1100 **Year:** 2020 **Source:** Office report, RP reports, final evaluation reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 192,823.00 (core)  283,770.00 (non-core) | 192,823.00 (core)  283,770.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 192,823.00 (core)  283,770.00 (non-core) | 192,823.00 (core)  283,770.00 (non-core) |
| **Total Resources for impact area 3** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 192,823.00 (core)  283,770.00 (non-core) | 192,823.00 (core)  283,770.00 (non-core) |