

UN Women Strategic Note 2022-2025

**UN WOMEN Guatemala COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |
| --- | --- |
| **Impact1Governance & Participation in Public Life (G&PPL). Women and girls fully and equally participate in leadership and decision-making and benefit from gender-responsive governance.** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: By 2025, the prioritized population will have greater access, under conditions of equality and security, to spaces for political, and civic participation at the national and local levels, promoting urban and rural development from different spaces.(UNSDCF Pillar 3. Strong institutions. Outcome 3.3.)Related national development priorities:** |
|  |  |  | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Total** |
| **Outcome 1.1By 2025, the prioritized population will have greater access, under conditions of equality and security, to spaces for political, and civic participation at the national and local levels, promoting urban and rural development from different spaces.(UNSDCF Pillar 3. Strong institutions. Outcome 3.3.)Related SP Outcome/Output:** | **Output 1.1.1: Women, Indigenous, Afro-descendant Garífuna and young women, and their organizations, increase their political participation as well as their capacities to influence relevant local and national decision-making processes.** | **Indicator 1.1.1A:** Number of women with strengthened capacities to participate and influence politics. Disaggregation by: (a) total, (b) youth women, (c). indigenous women.**Targets: Value:** 200**Notes:** 2021. (a) 200, (b) 50, (c) 100 2022. (a) 200, (b) 30, (c) 100 2023. (a) 200, (b) 30, (c) 100 2024. (a) 200, (b) 30, (c) 100 2025. (a) 200, (b) 30, (c) 100**Target Year:** 2025**Value:** 200**Target Year:** 2024**Value:** 200**Target Year:** 2023**Value:** 200**Target Year:** 2022**Baseline: Value:** 186 **Year:** 2020**Notes:** LB: (a) 186 (b) 45, (c) 100 in 2020**Source:** UN Women CO Guatemala | 132,054.00(core)223,008.00(non-core) | 130,646.00(core)171,113.00(non-core) | 30,924.00(core)354,248.00(non-core) | 30,924.00(core)364,000.00(non-core) | 324,548.00(core)1,112,369.00(non-core) |
| **Output 1.1.2: Gender equality mechanisms are strengthened and public institutions access knowledge products and technical assistance to prevent violence against women in spaces for political and electoral participation, to improve planning with a gender perspective, as well as to monitor investments that are gender-sensitive and with an ethnic marker.** | **Indicator 1.1.2A:** Number of public officials with greater capacities for gender-sensitive planning and monitoring of gender-sensitive investments.**Targets: Value:** 5**Notes:** 2021. 52022. 5. Accum. 102023. 5. Accum. 152024. 5. Accum. 202025. 5. Accum. 25**Target Year:** 2025**Value:** 5**Target Year:** 2024**Value:** 5**Target Year:** 2023**Value:** 5**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women CO Guatemala | 24,289.00(core)111,000.00(non-core) | 23,110.00(core)42,887.00(non-core) | 37,796.00(core)354,250.00(non-core) | 37,796.00(core)364,000.00(non-core) | 122,991.00(core)872,137.00(non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | 156,343.00(core)334,008.00(non-core) | 153,756.00(core)214,000.00(non-core) | 68,720.00(core)708,498.00(non-core) | 68,720.00(core)728,000.00(non-core) | 447,539.00(core)1,984,506.00(non-core) |
| **Total Resources for impact area 1** | 156,343.00(core)334,008.00(non-core) | 153,756.00(core)214,000.00(non-core) | 68,720.00(core)708,498.00(non-core) | 68,720.00(core)728,000.00(non-core) | 447,539.00(core)1,984,506.00(non-core) |
| **Impact2Economic Empowerment & Resilience (EE&R). Women have income security, decent work, and economic autonomy** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: By 2025, the Guatemalan State will increase the access of the prioritized population to decent work, productive means, and economic services at the national and local levels, adequate for competitiveness and the climate business, within a framework of inclusive, sustainable, socio-economic development. (UNSDCF Pillar 1. Economic development. Outcome 1.1.)Related national development priorities:** |
|  |  |  | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Total** |
| **Outcome 2.1By 2025, the Guatemalan State will increase the access of the prioritized population to decent work, productive means, and economic services at the national and local levels, adequate for competitiveness and the climate business, within a framework of inclusive, sustainable, socio-economic development. (UNSDCF Pillar 1. Economic development. Outcome 1.1.)Related SP Outcome/Output:****Indicator 2.1A:** Number of women who improve competitiveness and consolidate business thanks to the technical or financial support of UN Women.**Targets: Value:** 30**Notes:** LB. 0 in 20202021. 02022. 30. Accum. 302023. 40. Accum. 702024. 40. Accum. 1102025. 30. Accum. 140**Target Year:** 2025**Value:** 30**Target Year:** 2024**Value:** 30**Target Year:** 2023**Value:** 30**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women CO Guatemala**Indicator 2.1B:** Number of women accessing new opportunities for dignified and decent work thanks to the support of UN Women.**Targets: Value:** 20**Notes:** LB. 0 in 20202022. 202023. 20. Accum. 402024. 20. Accum. 602025. 20. Accum. 80**Target Year:** 2025**Value:** 20**Target Year:** 2024**Value:** 20**Target Year:** 2023**Value:** 20**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women Guatemala CO | **Output 2.1.1: Public and private institutions have improved the knowledge to design, implement and monitor policies, strategies, budgets for the generation of economic opportunities in business, entrepreneurship, and employment for women, and for the design and implementation of a comprehensive care system.** | **Indicator 2.1.1A:** Number of national or local public institutions that have improved the knowledge to design, implement, and monitor policies and budgets for the generation of economic opportunities in business, entrepreneurship, employment and care initiatives.**Targets: Value:** 1**Notes:** 2022. 12023. 1. Accum. 22024. 1. Accum. 32025. 1. Accum. 4**Target Year:** 2025**Value:** 1**Target Year:** 2023**Value:** 1**Target Year:** 2024**Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women Guatemala CO**Indicator 2.1.1B:** Number of private institutions that have improved their knowledge to design, implement initiatives and strategies for the generation of economic opportunities in business, entrepreneurship, employment and care initiatives.**Targets: Value:** 3**Notes:** 2022. 32023. 3. Accum. 62024. 3. Accum. 92025. 3. Accum. 12**Target Year:** 2025**Value:** 3**Target Year:** 2024**Value:** 3**Target Year:** 2023**Value:** 3**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women CO Guatemala | 62,017.00(core)438,582.00(non-core) | 63,876.00(core)431,257.00(non-core) | 39,821.00(core)262,145.00(non-core) | 39,821.00(core)269,360.00(non-core) | 205,535.00(core)1,401,344.00(non-core) |
| **Output 2.1.2: The most excluded women and rural women have access to technical education opportunities, business strengthening and market linkage services and financial resources for integration into the labor market, the development and growth of their businesses, and to generate conditions of economic resilience to ensure their livelihoods against the adverse effects of climate change.** | **Indicator 2.1.2A:** Number of women who have access to technical education opportunities and financial resources for integration into the labor market and the development and growth of their businesses.Disaggregation by: (a) total, (b) rural women.**Targets: Value:** 150**Notes:** 2022. (a) 150 (b) 100 2023. (a) 150 (b) 1002024. (a) 150 (b) 1002025. (a) 150 (b) 100**Target Year:** 2025**Value:** 150**Target Year:** 2024**Value:** 150**Target Year:** 2023**Value:** 150**Target Year:** 2022**Baseline: Value:** 150 **Year:** 2020**Notes:** LB: (a) 150 (b) 100 in 2020**Source:** UN Women CO Guatemala**Indicator 2.1.2B:** Number of women who access development models to generate conditions of economic resilience and ensure their livelihoods.Disaggregation by: (a) total, (b) rural women**Targets: Value:** 50**Notes:** 2022. (a) 50 (b) 352023. (a) 50 (b) 352024. (a) 50 (b) 352025. (a) 50 (b) 35**Target Year:** 2025**Value:** 50**Target Year:** 2024**Value:** 50**Target Year:** 2023**Value:** 50**Target Year:** 2022**Baseline: Value:** 50 **Year:** 2020**Notes:** LB: (a) 50 (b) 35 en 2020**Source:** UN Women CO Guatemala | 0.00(core)63,799.00(non-core) | 0.00(core)119,865.00(non-core) | 26,548.00(core)446,355.00(non-core) | 26,548.00(core)458,640.00(non-core) | 53,096.00(core)1,088,659.00(non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | 62,017.00(core)502,381.00(non-core) | 63,876.00(core)551,122.00(non-core) | 66,369.00(core)708,500.00(non-core) | 66,369.00(core)728,000.00(non-core) | 258,631.00(core)2,490,003.00(non-core) |
| **Total Resources for impact area 2** | 62,017.00(core)502,381.00(non-core) | 63,876.00(core)551,122.00(non-core) | 66,369.00(core)708,500.00(non-core) | 66,369.00(core)728,000.00(non-core) | 258,631.00(core)2,490,003.00(non-core) |
| **Impact3Ending Violence Against Women (EVAW). All women and girls live a life free from all forms of violence** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: By 2025, State institutions will improve access to justice, dignified and transformative reparation, comprehensive protection, and prevention of violence against women, youth, adolescents, and childhood.(UNSDCF Pillar 4. Peace, security and justice. Outcome 4.2.)Related national development priorities:** |
|  |  |  | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Total** |
| **Outcome 3.1By 2025, State institutions will improve access to justice, dignified and transformative reparation, comprehensive protection, and prevention of violence against women, youth, adolescents, and childhood.(UNSDCF Pillar 4. Peace, security and justice. Outcome 4.2.)Related SP Outcome/Output:** | **Output 3.1.1: The competent State institutions, at national and local level, improve their capacities to prevent and respond to women, girls, adolescents and survivors of violence, including better and greater access to comprehensive protection and essential services.** |  | 0.00(core)0.00(non-core) | 0.00(core)332,000.00(non-core) | 18,644.00(core)472,333.00(non-core) | 18,644.00(core)485,333.00(non-core) | 37,288.00(core)1,289,666.00(non-core) |
| **Output 3.1.2: Civil society women's organizations and survivors of violence against women enhance their capacities to demand their rights to essential services, comprehensive protection, justice and transformative reparation, and to promote processes of prevention of violence against women, girls, and adolescents through cultural changes and social norms.** |  | 0.00(core)0.00(non-core) | 0.00(core)118,000.00(non-core) | 9,322.00(core)236,166.00(non-core) | 9,322.00(core)242,666.00(non-core) | 18,644.00(core)596,832.00(non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | 0.00(core)0.00(non-core) | 0.00(core)450,000.00(non-core) | 27,966.00(core)708,499.00(non-core) | 27,966.00(core)727,999.00(non-core) | 55,932.00(core)1,886,498.00(non-core) |
| **Total Resources for impact area 3** | 0.00(core)0.00(non-core) | 0.00(core)450,000.00(non-core) | 27,966.00(core)708,499.00(non-core) | 27,966.00(core)727,999.00(non-core) | 55,932.00(core)1,886,498.00(non-core) |
| **Impact4Peace, Security, Humanitarian & Disaster Risk Reduction (PSH&DRR). Women and girls contribute to, and have influence in, building sustainable peace and resilience and benefit equally from the prevention of conflicts and disasters, and from humanitarian action** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: By 2025, the strengthened State institutions will increase citizen security, access to justice, and the transformation of conflicts, seeking greater coordination at the national and local levels. (UNSDCF Pillar 4. Peace, security and justice. Outcome 4.1.)Related national development priorities:** |
|  |  |  | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Total** |
| **Outcome 4.1By 2025, the strengthened State institutions will increase citizen security, access to justice, and the transformation of conflicts, seeking greater coordination at the national and local levels. (UNSDCF Pillar 4. Peace, security and justice. Outcome 4.1.)Related SP Outcome/Output:****Indicator 4.1A:** Number of VAW sentences issued by courts and tribunals specialized in femicide and other forms of VAW (UNSDCF Indicator 3.2.2)**Targets: Value:** No Available**Notes:** LB. No Available2021.2022.2023.2024. No Available2025. Note: (UNSDCF Indicator 3.2.2)Baseline and target not determined in UNSDCF**Target Year:** 2025**Value:** No Available**Target Year:** 2024**Value:** No Available**Target Year:** 2023**Value:** No Available**Target Year:** 2022**Baseline: Value:** No Available **Year:** 2021**Source:** UNSDCF Indicator 3.2.2 | **Output 4.1.1: State institutions consolidate their capacities and coordinate to develop initiatives for women's access to security, justice, transformative reparation; conflict transformation, sustaining peace and the rule of law.** | **Indicator 4.1.1A:** Number of State institutions strengthened to develop initiatives for women's access to security, justice, and dignified and transformative reparation; transformation of conflicts; peacekeeping, and/or the rule of law.**Targets: Value:** 1**Notes:** 2022. 1 Accum. 12023. 1 Accum. 22024. 1 Accum. 32025. 1 Accum. 4**Target Year:** 2025**Value:** 1**Target Year:** 2024**Value:** 1**Target Year:** 2023**Value:** 1**Target Year:** 2022**Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women CO Guatemala**Indicator 4.1.1B:** Number of public officials with strengthened capacities for the transformation of conflicts, peacekeeping, and the rule of law.**Targets: Value:** 10**Notes:** LB. 0 in 20202021. 10 2022. 10 Accum. 202023. 10 Accum. 302024. 10 Accum. 402025. 10 Accum. 50**Target Year:** 2025**Value:** 10**Target Year:** 2024**Value:** 10**Target Year:** 2023**Value:** 10**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women Guatemala CO | 11,109.00(core)466,869.00(non-core) | 11,441.00(core)278,404.00(non-core) | 15,307.00(core)513,663.00(non-core) | 15,307.00(core)527,800.00(non-core) | 53,164.00(core)1,786,736.00(non-core) |
| **Output 4.1.2: Women, indigenous women, and defenders lead initiatives for improved protection, access to justice, transformative reparation, sustaining peace and the rule of law.** | **Indicator 4.1.2A:** Number of initiatives led by civil society organizations and indigenous women's organizations, aimed at the protection, access to justice, and transformative reparation to contribute to peacekeeping efforts.**Targets: Value:** 2**Notes:** 2021. 02022. 22023. 2 Accum. 42024. 2 Accum. 62025. 2 Accum. 8**Target Year:** 2025**Value:** 2**Target Year:** 2024**Value:** 2**Target Year:** 2023**Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women CO Guatemala | 0.00(core)346,489.00(non-core) | 0.00(core)150,000.00(non-core) | 12,363.00(core)118,538.00(non-core) | 12,363.00(core)121,800.00(non-core) | 24,726.00(core)736,827.00(non-core) |
| **Output 4.1.3: More women participate and lead humanitarian response and post-disaster recovery interventions, applying the humanitarian - peace - development triple nexus.** |  | 13,053.00(core)81,593.00(non-core) | 13,444.00(core)72,884.00(non-core) | 6,918.00(core)158,050.00(non-core) | 6,918.00(core)162,400.00(non-core) | 40,333.00(core)474,927.00(non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | 24,162.00(core)894,951.00(non-core) | 24,885.00(core)501,288.00(non-core) | 34,588.00(core)790,251.00(non-core) | 34,588.00(core)812,000.00(non-core) | 118,223.00(core)2,998,490.00(non-core) |
| **Total Resources for impact area 4** | 24,162.00(core)894,951.00(non-core) | 24,885.00(core)501,288.00(non-core) | 34,588.00(core)790,251.00(non-core) | 34,588.00(core)812,000.00(non-core) | 118,223.00(core)2,998,490.00(non-core) |