

UN Women Strategic Note 2018-2022

**UN WOMEN Haiti COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact1 The UN Women's Political Participation Strategy aims to secure the participation of women in the elections in Haïti and to strengthen their political empowerment to enable them to participate in the development of policies for the reconstruction and stabilization of their countries** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Outcome 5: Public institutions and civil society improve the rule of law and decentralization for good governance at all levels of decision-making Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 1.2 Haïtian women, with a special focus on victims of violence, have increased access to justice services  Related SP Outcome/Output:**   **Indicator 1.2A:** Number of personnel of formal and informal justice institutions whose capacities to provide justice to women are strengthened, with UN-Women’s support **Targets:  Value:** 700 **Target Year:** 2021 **Value:** 100 **Target Year:** 2019 **Value:** 200 **Target Year:** 2020 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 300 **Year:** 2017 **Source:** UN-Women Report  (C)   **Indicator 1.2B:** Number of women accessing legal aid with UN-Women’s support **Targets:  Value:** 300 **Target Year:** 2021 **Value:** 250 **Target Year:** 2020 **Value:** 200 **Target Year:** 2019 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 300 **Year:** 2017 **Source:** UN-Women Report (A) | **Output 1.2.6 The DAP has a support framework for socio-economic reintegration** | **Indicator 1.2.6A:** A Memorandum of Understanding between the DAP and the INFP or another authority responsible for vocational training recognized by the Haitian state in prisons is concluded **Targets:  Value:** Yes **Notes:** Baseline survey in a early stage **Target Year:** 2021 **Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** UN Women Project Report  **Indicator 1.2.6B:** A Memorandum of Understanding between the DAP and the Ministry of Health (MSPP) allowing regular health monitoring of detainees and case referencing is concluded **Targets:  Value:** Yes **Target Year:** 2021 **Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** UN Women Project Report  **Indicator 1.2.6C:** % of vocational training curricula for inmates in prisons assessed by the INFP or another competent authority recognized by the Haitian state **Targets:  Value:** 10% **Target Year:** 2021 **Value:** 50% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2020 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** UN Women Project Report  **Indicator 1.2.6D:** Number of public advocacy activities implemented as part of the anti-stigmatization campaign for former detainees **Targets:  Value:** 2 **Notes:** Baseline survey in a early stage **Target Year:** 2021 **Value:** 4 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** UN Women Project Report  **Indicator 1.2.6E:** % of those targeted in social dialogue activities who report a better understanding of the impact of stigma **Targets:  Value:** 10% **Notes:** Baseline survey in a early stage **Target Year:** 2021 **Value:** 75% **Target Year:** 2022 **Baseline:  Value:** 60% (Social dialogue activities initiated in Saint-Marc and Croix-des-Bouquets) **Year:** 2019 **Notes:** This Data are retrieved from the Prodoc **Source:** UN Women Project Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  61,100.00 (non-core) | 0.00 (core)  61,100.00 (non-core) |
| **Output 1.2.7 Detainees in targeted prisons have improved access to hygiene and health and benefit from gender-sensitive conditions of detention in accordance with the measures identified in the Gender Directive** | **Indicator 1.2.7A:** Number of targeted prisons with space for pregnant and breastfeeding women **Targets:  Value:** 3 **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:**  Project report  **Indicator 1.2.7B:** Number of memorandums of Understanding between the DAP and the Health directorates of the 3 departments to facilitate the referencing and care of suffering detainees **Targets:  Value:** 5 **Notes:** Baseline survey in a early stage and target will be set in 2021 **Target Year:** 2021 **Value:** 3 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** This data are retrieved from the Prodoc. **Source:** Project report & Database  **Indicator 1.2.7C:** Percentage of newly admitted female detainees for whom an entry medical visit is performed **Targets:  Value:** 10% **Notes:** Target will be set while baseline resuts will be availlable in Q1 2021 **Target Year:** 2021 **Value:** 100% **Target Year:** 2022 **Baseline:  Value:** 58% **Year:** 2019 **Notes:** This data are retrieved from the Prodoc. **Source:** UN Women Project Report  **Indicator 1.2.7D:** Number of initiatives undertaken to ensure access to hygiene products in the 3 targeted prisons **Targets:  Value:** 3 **Notes:** Target will be modied while basesline's result available in Q1 2021 **Target Year:** 2021 **Value:** 2 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** This data are retrieved from the Prodoc. **Source:** UN Women Project Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  33,660.00 (non-core) | 0.00 (core)  33,660.00 (non-core) |
| **Outcome 1.4 The judicial system improves the efficiency of its procedures to reduce the delays in processing judicial cases  Related SP Outcome/Output:**   **Indicator 1.4A:** # of cases and # of alternative measures to the judicial process and to the detention used, disaggregated by sex, age, economic status and specifying whether they are in detention (police custody or preventive detention) **Targets:  Value:** 50 **Notes:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Target Year:** 2021 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Note:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4B:** Duration of the processing of cases involving vulnerable persons and benefiting from legal and judicial assistance **Targets:  Value:** 30 days **Notes:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Target Year:** 2021 **Value:** 30 days **Notes:** 30 days **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Note:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4C:** % satisfaction of beneficiaries and vulnerable people with their experience of justice and handling their case **Targets:  Value:** 80% **Notes:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Target Year:** 2021 **Value:** 80% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2020 **Note:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Source:** MJSP Reports, HNP, BAL and CNAL | **Output 1.4.1 All actors in the penal chain are better equipped and trained to use alternative measures to court proceedings and detention to reduce prolonged pretrial detention** | **Indicator 1.4.1A:** # of actors in the criminal justice system and trained civil society organizations using alternatives to detention **Targets:  Value:** 25 **Notes:** The estimated baseline and target values will be changed once the results are available. **Target Year:** 2021 **Value:** 25 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** Alternatives to detention for minors already provided for in the law, the new draft penal code and criminal procedure include alternatives to detention and preventive detention (pending in the senate), **Source:** Reports of the Ministry of Justice, press articles, internal reports, including monitoring and evalu  **Indicator 1.4.1B:** # of cases where these actors use alternative measures **Targets:  Value:** 50 **Notes:** The estimated baseline and target values will be changed once the results are available. **Target Year:** 2021 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** Alternatives to detention for minors already provided for in the law, the new draft penal code and criminal procedure include alternatives to detention and preventive detention (pending in the senate), **Source:** Reports of the Ministry of Justice, press articles, internal reports, including monitoring and evalu | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  43,000.00 (non-core) | 0.00 (core)  43,000.00 (non-core) |
| **Output 1.4.2 An increased number of civil servants in the justice system are trained in handling and filing complaints** | **Indicator 1.4.2A:** # of complaints processed by the civil servants in the justice system **Targets:  Value:** 25 **Notes:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Target Year:** 2021 **Value:** 25 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Source:** Internal and external reports, press articles, reports from civil society organizations, OPC reports  **Indicator 1.4.2B:** # of civil servants in the justice system trained in handling and filing complaints **Targets:  Value:** 50 **Notes:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Target Year:** 2021 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Source:** Internal and external reports, press articles, reports from civil society organizations, OPC reports  **Indicator 1.4.2C:** # of women, children and men with increased access to the repository and enhanced complaint handling **Targets:  Value:** Women: 50, Children: 25 and Men: 25 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** The Baseline study is ongoing, and the estimated baseline and target values will be changed once the results are available. **Source:** Internal and external reports, press articles, reports from civil society organizations, OPC reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  102,450.00 (non-core) | 0.00 (core)  102,450.00 (non-core) |
| **Output 1.4.4 The Legal Assistance Offices (BAL) are strengthened, structured, and staffed with competent staff and benefit technical support from the National Legal Assistance Council (CNAL) to provide legal and judicial assistance services.** | **Indicator 1.4.4A:** CNAL is set up and operational **Targets:  Value:** Yes **Notes:** CNAL is set up and operational **Target Year:** 2021 **Value:** Yes **Notes:** CNAL is set up and operational **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Notes:** Promulgation of the law on legal assistance in 2018 **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4.4B:** # of files processed by the CNAL **Targets:  Value:** 5 **Notes:** Once the baseline results are available (next January), the targets will be adjusted. **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** Once the baseline results are available (next January), the targets will be adjusted. **Source:** MJSP Reports, HNP, BAL and CNAL   **Indicator 1.4.4C:** # of operational legal clinics **Targets:  Value:** 3 **Notes:** 3 operational legal clinics **Target Year:** 2021 **Value:** 3 **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2018 **Notes:** 1 operational legal clinic at the Jérémie Law School: a model that could serve as an example **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4.4D:** # of files followed by legal clinics **Targets:  Value:** 5 **Notes:** Once the baseline results are available (next year), the targets will be adjusted. **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** The PBF-Justice’s baseline study project will be launched in the early of August 2020. The results will be available between October 2020 to January 2021 and data will be adjusted. **Source:**  MJSP Reports, HNP, BAL and CNAL   **Indicator 1.4.4E:** # of files processed by civil servants in the justice system **Targets:  Value:** 90 **Notes:** 90 people, 1 study and 1 module **Target Year:** 2021 **Value:** 90 **Notes:** 90 people, 1 study and 1 module **Target Year:** 2022 **Baseline:  Value:** 20 **Year:** 2019 **Notes:** The PBF-Justice’s baseline study project will be launched in the early of August 2020. The results will be available between October 2020 to January 2021 and baseline data will be adjusted **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4.4F:** # staff of new BALs, paralegals, legal assistants and trainee lawyers trained and having benefited from capacity building activities **Targets:  Value:** 90 **Notes:** 90 people, 1 study and 1 module **Target Year:** 2021 **Value:** 90 **Notes:** 90 people, 1 study and 1 module **Target Year:** 2022 **Baseline:  Value:** 25 **Year:** 2019 **Notes:** The PBF-Justice’s baseline study project will be launched in the early of August 2020. The results will be available between October 2020 to January 2021 and baseline data will be adjusted. **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4.4G:** # of reports produced by trained beneficiaries **Targets:  Value:** 2 **Notes:** 1 study and 1 module **Target Year:** 2021 **Value:** 2 **Notes:** 1 study and 1 module **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** The PBF-Justice’s baseline study project will be launched in the early of August 2020. The results will be available between October 2020 to January 2021 and baseline data will be adjusted **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4.4H:** Existence of a harmonized database **Targets:  Value:** Yes **Notes:** 1 database **Target Year:** 2021 **Value:** Yes **Notes:** 1 database **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2019 **Notes:** The PBF-Justice’s baseline study project will be launched in the early of August 2020. The results will be available between October 2020 to January 2021 and baseline data will be adjusted. **Source:**  MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4.4I:** # of analysis reports available at the BAL level **Targets:  Value:** 1 **Notes:** 1 report per year **Target Year:** 2021 **Value:** 1 **Notes:** 1 report per year **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** The PBF-Justice’s baseline study project will be launched in the early of August 2020. The results will be available between October 2020 to January 2021 and baseline data will be adjusted **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4.4J:** # of debate between civil society, BAL and legal clinics **Targets:  Value:** 1 **Notes:** 1 debate / forum **Target Year:** 2021 **Value:** 1 **Notes:** 1 debate / forum **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** The PBF-Justice’s baseline study project will be launched in the early of August 2020. The results will be available between October 2020 to Janauary 2021 and baseline data will be adjusted. **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4.4K:** # of analysis reports of the data collected through the database set up **Targets:  Value:** 1 **Notes:** 1 report per year **Target Year:** 2021 **Value:** 1 **Notes:** 1 report per year **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** The PBF-Justice’s baseline study project will be launched in the early of August 2020. The results will be available between October 2020 to Janauary 2021 and baseline data will be adjusted. **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.4.4L:** # of perception surveys among the population, in particular the most vulnerable populations, in particular children, young people at risk under 25 and women **Targets:  Value:** 1 **Notes:** 1 report per year **Target Year:** 2021 **Value:** 1 **Notes:** 1 report per year **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** The PBF-Justice’s baseline study project will be launched in the early of August 2020. The results will be available between October 2020 to January 2021 and baseline data will be adjusted **Source:** MJSP Reports, HNP, BAL and CNAL | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  32,240.00 (non-core) | 0.00 (core)  32,240.00 (non-core) |
| **Outcome 1.5 The prison and judicial sector has operational capacities facilitating better coordination of the COVID-19 response  Related SP Outcome/Output:**   **Indicator 1.5A:** # of prevention measures implemented in response to COVID-19 **Targets:  Value:** 5 **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Liste de matériels distribués dûment signé par le receveur  Bon de commande des matériels  Rapport d | **Output 1.5.2 The Directorate of Prison Administration (DAP) has increased technical and operational capacities facilitating better implementation of the social reintegration program for released prisoners** | **Indicator 1.5.2A:** # of coordination meetings held within the framework of partnership with civil society organizations **Targets:  Value:** 5 **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.5.2B:** Participation of CSO members in the psychosocial and medical follow-up sessions for released women **Targets:  Value:** Yes **Target Year:** 2021 **Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Source:** MJSP Reports, HNP, BAL and CNAL  **Indicator 1.5.2C:** # of departure kits purchased, distributed and used by released women **Targets:  Value:** 5 **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** MJSP Reports, HNP, BAL and CNAL | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  125,000.00 (non-core) | 0.00 (core)  84,000.00 (non-core) | 0.00 (core)  94,866.00 (non-core) | 0.00 (core)  303,866.00 (non-core) |
| **Output 1.5.3 Prisons benefit from effective decongestion thanks to an efficient offer of legal assistance** | **Indicator 1.5.3A:** # of files processed **Targets:  Value:** 50 **Target Year:** 2021 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** MJSP Reports, HNP, BAL and CNAL   **Indicator 1.5.3B:** # of legal assistants and trainee lawyers trained having benefited from capacity building activities in the preparation and analysis of legal files **Targets:  Value:** 10 **Target Year:** 2021 **Value:** 10 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** MJSP Reports, HNP, BAL and CNAL | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  237,050.00 (non-core) | 0.00 (core)  109,601.00 (non-core) | 0.00 (core)  60,191.00 (non-core) | 0.00 (core)  406,842.00 (non-core) |
| **Output 1.5.8 People living with, at risk of and affected by HIV obtain equitable access and reap equitable benefits from HIV prevention, treatment, care and support services** | **Indicator 1.5.8A:** Existence and ownership of a strategic orientation guide for the promotion of young men's commitment to Gender Equality, with a focus on the fight against gender-based and sexual violence and HIV **Targets:  Value:** Yes **Target Year:** 2022 **Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2021 **Source:** Annual and Donor Report  **Indicator 1.5.8B:** Number of new and old clubs with SGBV and HIV activities **Targets:  Value:** 6 **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2021 **Source:** Annual and Donor Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  28,750.00 (non-core) | 0.00 (core)  28,750.00 (non-core) |
| **Outcome 1.6 Women's rights groups, social movements and CSOs, including those representing young people and groups facing multiple and intersecting forms of discrimination, have a more effective influence, and contribute to progress towards gender equality, women's empowerment, and the elimination of all forms of violence against women and girls, including sexual and gender-based violence (SGBV) and harmful practices  Related SP Outcome/Output:**   **Indicator 1.6A:** Proportion of women's rights organizations, autonomous social movements and CSOs, including those representing youth and groups facing multiple and intersecting forms of discrimination/marginalization, report having greater influence and agency to work on ending VAWG, including family violence **Targets:  Value:** 10% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2020 **Source:** Project Document Report  **Indicator 1.6B:** Development of a risk management and contingency plan for Organizations **Targets:  Value:** Yes **Notes:** Risk management and contingency plan developed and well used by organizations **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Note:** No risk management and contingency plan developed **Source:** Project Document Report | **Output 1.6.1 Women's rights groups and relevant CSOs representing groups facing multiple and intersecting forms of discrimination/marginalisation have strengthened capacities and support to design, implement and monitor their own programmes on VAWG, including family violence** | **Indicator 1.6.1A:** Number of women's rights groups and relevant CSOs representing groups facing multiple and intersecting forms of discrimination/marginalization that have strengthened capacities and support to design, implement, monitor, and evaluate their own programmes on VAWG, including family violence **Targets:  Value:** 7 **Notes:** 7 women's rights groups and relevant CSOs representing groups facing multiple and intersecting forms of discrimination/marginalization **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Annual and Donor Report  **Indicator 1.6.1B:** Number of women’s rights groups and relevant CSOs using knowledge products developed by the participating UN agencies in the design of their own programmes on ending VAWG, including family violence **Targets:  Value:** 7 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Annual and Donor Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  849,998.00 (non-core) | 0.00 (core)  849,998.00 (non-core) |
| **Output 1.6.2 Women's rights groups and relevant CSOs, have increased opportunities and support to share knowledge, network, partner and jointly advocate for GEWE and ending VAWG, including family violence, with relevant stakeholders at sub-national, national, regional and global levels - WPHF Grant to CSOs under the Spotlight Initiative (MOFEDGA-AFM-HAGN-FEFBA-ALTERTOP-JPHRO-ZL-RAPHA-MIEFH-YWCA-RSDDH-A4C-CASDA-SOFNE)** | **Indicator 1.6.2A:** Number of CSOs representing youth and other groups facing multiple and intersecting forms of discrimination that are integrated with coalitions and networks of women’s rights groups and civil society working on ending VAWG including family violence **Targets:  Value:** 15 **Target Year:** 2022 **Baseline:  Value:** 5 **Year:** 2021 **Source:** Annual and Donor Report  **Indicator 1.6.2B:** Number of women's rights groups, networks and relevant CSOs with strengthened capacities to network, partner and jointly advocate for progress on ending VAWG including family violence at local, national, regional, and global levels **Targets:  Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Annual and Donor Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  458,000.00 (non-core) | 0.00 (core)  458,000.00 (non-core) |
| **Outcome 1.7 Women candidates and voters feel safer and actively participate in the electoral process and in decisions related to peacebuilding and conflict prevention  Related SP Outcome/Output:**   **Indicator 1.7A:** Increased level of sense of security of women candidates and voters when participating in the electoral process. **Targets:  Value:** 30% **Notes:** A 30% increase in the sense of security of politicians, women candidates, and voters, in the target areas, when participating in the electoral process. **Target Year:** 2022 **Baseline:  Value:** 2% **Year:** 2016 **Note:** In 2016, women candidates felt less secure when participating in the electoral process. **Source:** Sense of security of women candidates and voters' surveys, Project Final Evaluation  **Indicator 1.7B:** Increase in the proportion of women participating in the electoral process as candidates, due to the increased sense of security. **Targets:  Value:** 10% **Notes:** In 2022, a 10% increase in the participation of women as a candidate in the legislative elections. **Target Year:** 2022 **Baseline:  Value:** 8% **Year:** 2016 **Note:** In 2016, only 8% of women took part as candidates in the legislative elections in the project's intervention areas. **Source:** Electoral Council Report, Project Report | **Output 1.7.1 The Haitian National Police (HNP) has specific capacities to prevent and combat electoral violence against women** | **Indicator 1.7.1A:** Number of HNP interventions to respond to recorded incidents of VEEF violence against women **Targets:  Value:** In 2021, 75 VEEF incidents recorded and treated by the HNP (TBD in 2022) **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 25 (TBD in 2016) **Year:** 2016 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 1.7.1B:** Number of registrations of women harassed or assaulted during the election cycle **Targets:  Value:** In 2021, 100 complaints registered by the HNP according to the operational system set up to collect data on electoral and political violence against women (TBD in 2022). **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 0 (TBD in 2016) **Year:** 2016 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 1.7.1C:** Number of police officers trained and involved in the complaint registration process and monitoring **Targets:  Value:** In 2022, about 30 police officers will be trained and involved in the complaint registration process and monitoring **Target Year:** 2022 **Baseline:  Value:** 10 (TBD in 2021) **Year:** 2021 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  146,636.00 (non-core) | 0.00 (core)  146,636.00 (non-core) |
| **Output 1.7.2 Community-based and women-led electoral violence prevention and early warning mechanisms are strengthened and linked to the Haitian National Police (HNP)** | **Indicator 1.7.2A:** Number of electoral Violence against women (EVAW) alert reports produced by the community mechanism and used by women's organizations and the Haitian National Police (HNP) **Targets:  Value:** 12 **Notes:** From 2022 to 2023, at least 12 consolidated alert reports produced by the community mechanism and used by women's organizations and the HNP. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2016 **Notes:** Lack of alert reports on EVAW produced in 2016 **Source:** Annual and Donor Report  **Indicator 1.7.2B:** Existence of a community mechanism for the prevention and early warning of violence against women **Targets:  Value:** Yes **Notes:** In 2021, a community mechanism for the prevention and early warning of violence against women will have been set up and will be functional **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2016 **Notes:** No community mechanism for the prevention and early warning of electoral violence against women (EVAW) **Source:** Annual and Donor Report  **Indicator 1.7.2C:** Percentage of community members (disaggregated by sex) monitoring EVAW cases trained in the use of the community mechanism **Targets:  Value:** 65% **Notes:** By 2021, 65% of community members (70% of whom are women and 15% young people) monitoring EVAW cases will have been trained in the management of the community mechanism **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2016 **Source:** Annual and Donor Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  398,364.00 (non-core) | 0.00 (core)  398,364.00 (non-core) |
| **Total Resources for outcome 1.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  94,760.00 (non-core) | 0.00 (core)  94,760.00 (non-core) |
| **Total Resources for outcome 1.4 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  177,690.00 (non-core) | 0.00 (core)  177,690.00 (non-core) |
| **Total Resources for outcome 1.5 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  362,050.00 (non-core) | 0.00 (core)  193,601.00 (non-core) | 0.00 (core)  183,807.00 (non-core) | 0.00 (core)  739,458.00 (non-core) |
| **Total Resources for outcome 1.6 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,307,998.00 (non-core) | 0.00 (core)  1,307,998.00 (non-core) |
| **Total Resources for outcome 1.7 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  545,000.00 (non-core) | 0.00 (core)  545,000.00 (non-core) |
| **Total Resources for impact area 1** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  362,050.00 (non-core) | 0.00 (core)  193,601.00 (non-core) | 0.00 (core)  2,309,255.00 (non-core) | 0.00 (core)  2,864,906.00 (non-core) |
| **Impact2 One of the main means to implement this will be to boost women's access to finance and increase women's participation and leadership in the energy and water sectors and in targeted chains (climate-resilient agriculture and value green chains).** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Outcome 1: The population, especially the most vulnerable, has equitable access to livelihoods, decent and green jobs, and productive resources to reduce poverty in all its forms in a supportive and inclusive socio-economic and cultural environment Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 2.1 Women led businesses have increased participation and leadership in the development of climate-resilient agriculture, water, renewable energy and service markets and benefit from equal access to resources and services  Related SP Outcome/Output:**   **Indicator 2.1A:** Number of women with strengthened capacities and skills to participate in the economy, including as entrepreneurs, with UN-Women’s support **Targets:  Value:** 10,000 **Target Year:** 2021 **Value:** 5,000 **Target Year:** 2019 **Value:** 5,000 **Target Year:** 2020 **Value:** 100 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Final Report of Enterprise Platform for Women project  (C)   **Indicator 2.1B:** Number of women entrepreneurs supported to access finance and gender-responsive financial products and services, with UN-Women’s support **Targets:  Value:** 100 **Target Year:** 2021 **Value:** 70 **Target Year:** 2020 **Value:** 30 **Target Year:** 2019 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** UN-Women’s Project Report (C)  **Indicator 2.1C:** Number of legal, regulatory and policy frameworks that remove barriers to women´s economic empowerment **Targets:  Value:** 3 **Target Year:** 2021 **Value:** 2 **Target Year:** 2020 **Value:** 1 **Target Year:** 2019 **Value:** 3 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** UN-Women’s Project Report (C)  **Indicator 2.1D:** Number of rural women supported to gain access, use and/or control of productive resources by UN-Women **Targets:  Value:** 1,500 **Notes:** Age Disability status HIV/AIDS status **Target Year:** 2021 **Value:** 500 **Notes:** Age Disability status HIV/AIDS status **Target Year:** 2020 **Value:** 500 **Notes:** Age Disability status HIV/AIDS status **Target Year:** 2019 **Value:** 150 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** UN-Women’s Project Reports (C)  **Indicator 2.1E:** % of women that are connected and use the “Buy for Women” platform to develop their businesses **Targets:  Value:** 100% **Target Year:** 2021 **Value:** 25% **Target Year:** 2020 **Value:** 50% **Target Year:** 2019 **Value:** 25% **Target Year:** 2018 **Value:** 100% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2017 **Source:** Monitoring and Final Reports of the Platform Buy For Women Projects (C)  **Indicator 2.1F:** % of women-led businesses connected to the “Buy for Women” platform that have increased productivity **Targets:  Value:** 80% **Target Year:** 2021 **Value:** 70% **Target Year:** 2020 **Value:** 60% **Target Year:** 2019 **Value:** 50% **Target Year:** 2018 **Value:** 80% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2017 **Source:** Monitoring and Final Reports of the Platform Buy For Women Projects  **Indicator 2.1G:** % of women-led businesses connected to the “Buy for Women” platform that have access to credit **Targets:  Value:** 80% **Target Year:** 2021 **Value:** 70% **Target Year:** 2020 **Value:** 50% **Target Year:** 2019 **Value:** 40% **Target Year:** 2018 **Value:** 80% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2017 **Source:** Monitoring and Final Reports of the Platform Buy For Women Projects | **Output 2.1.2 Women have increased capacities to develop sustainable and financially profitable businesses (alignment to FPI output 4.1)** | **Indicator 2.1.2A:** Number of women with strengthened capacities to develop sustainable and financially profitable businesses (through the UN Women “Enterprise Platform for Women” and Virtual Skills School) **Targets:  Value:** 5,000 **Target Year:** 2018 **Value:** 2,000 **Target Year:** 2019 **Value:** 3,000 **Target Year:** 2020 **Value:** 10,000 **Target Year:** 2021 **Value:** 100 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Final Report of Enterprise Platform for Women project  (C)   **Indicator 2.1.2B:** % of women’s entrepreneurs supported by UNW that are connected to information, markets and/or finance using the “Buy from Women” Platform **Targets:  Value:** 10% **Target Year:** 2018 **Value:** 20% **Target Year:** 2019 **Value:** 30% **Target Year:** 2020 **Value:** 40% **Target Year:** 2021 **Value:** 50% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2017 **Source:** Monitoring and Final Reports of the Platform Buy For Women Projects  (C) | 20,000.00 (core)  0.00 (non-core) | 20,000.00 (core)  0.00 (non-core) | 20,000.00 (core)  450,000.00 (non-core) | 20,000.00 (core)  0.00 (non-core) | 0.00 (core)  672,735.00 (non-core) | 80,000.00 (core)  1,122,735.00 (non-core) |
| **Outcome 2.2 Innovative solutions are consolidated and scaled up to strengthen rural women’s economic empowerment  Related SP Outcome/Output:**   **Indicator 2.2A:** Buy from Women Platform is operational **Targets:  Value:** Yes **Notes:** The BfW platform is fully operational **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2021 **Note:** The BfW platorm is unfunctional **Source:** Project Document, Annual report  **Indicator 2.2B:** Number of rural women with strengthened capacities to better develop their farm **Targets:  Value:** 2000 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Annual and Donor Report | **Output 2.2.1 Rural women affected by natural disasters such as hurricanes, floods and earthquakes actively participate in the development of economic activities, benefit from equal access to productive means and have increased their resilience to natural disasters** | **Indicator 2.2.1A:** Number of organizations and individuals involved in agricultural production supported in their recovery **Targets:  Value:** 6 **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2021 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 2.2.1B:** % of increase in the land yield for the key selected crops **Targets:  Value:** 3% **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2021 **Source:** Annual and Donor Report  **Indicator 2.2.1C:** Number of organizations and individuals involved in food processing supported in their recovery **Targets:  Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 20 **Year:** 2021 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 2.2.1D:** Quantity of food processing line installed **Targets:  Value:** High **Notes:** This is an estimate because it will be adjusted after the baseline results  **Target Year:** 2022 **Baseline:  Value:** Low **Year:** 2021 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 2.2.1E:** Number of organizations and individuals involved in storage and marketing supported to have better revenue from their activity **Targets:  Value:** 50 **Notes:** This is an estimate because it will be adjusted after the baseline results  **Target Year:** 2022 **Baseline:  Value:** 20 **Year:** 2022 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 2.2.1F:** Number of new storage equipment donated and installed **Targets:  Value:** 3 **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  303,752.00 (non-core) | 0.00 (core)  303,752.00 (non-core) |
| **Output 2.2.2 The regulatory and institutional framework is strengthened for better integration of gender equality into crisis/humanitarian response and recovery plans** | **Indicator 2.2.2A:** Number of strategic partnerships with government programs targeting women and related to food security and economic recovery **Targets:  Value:** 2 **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 2.2.2B:** Number of knowledge-management activities related to natural disasters, food insecurity, policies and humanitarian response & recovery held **Targets:  Value:** 2 **Target Year:** 2022 **Value:** 3 **Notes:** This is an estimate because it will be adjusted after the baseline results  **Target Year:** 2022 **Value:** 3 **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 2.2.2C:** Regulatory & institutional framework modified related to crisis/ humanitarian response & recovery taken into account the gender dimension **Targets:  Value:** Yes **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2021 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** : Annual and Donor Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  260,490.00 (non-core) | 0.00 (core)  260,490.00 (non-core) |
| **Output 2.2.3 Women's social capital facilitating women's access to information and resources as a peace agent is strengthened** | **Indicator 2.2.3A:** Number of women’s organizations trained **Targets:  Value:** 25 **Target Year:** 2022 **Value:** 25 **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 10 **Year:** 2022 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 2.2.3B:** Number of people in the communities sensitized and mobilized on climate change **Targets:  Value:** 300 **Notes:** This is an estimate because it will be adjusted after the baseline results  **Target Year:** 2022 **Baseline:  Value:** 100 **Year:** 2022 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 2.2.3C:** Number of people in the communities using techniques / knowledge related to climate change smart agriculture **Targets:  Value:** 500 **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 100 **Year:** 2022 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report  **Indicator 2.2.3D:** Number of network and collaboration opportunities established **Targets:  Value:** 2 **Notes:** This is an estimate because it will be adjusted after the baseline results **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Notes:** This is an estimate because it will be adjusted after the baseline results **Source:** Annual and Donor Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  536,168.00 (non-core) | 0.00 (core)  536,168.00 (non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | | | 20,000.00 (core)  0.00 (non-core) | 20,000.00 (core)  0.00 (non-core) | 20,000.00 (core)  450,000.00 (non-core) | 20,000.00 (core)  0.00 (non-core) | 0.00 (core)  672,735.00 (non-core) | 80,000.00 (core)  1,122,735.00 (non-core) |
| **Total Resources for outcome 2.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,100,410.00 (non-core) | 0.00 (core)  1,100,410.00 (non-core) |
| **Total Resources for impact area 2** | | | 20,000.00 (core)  0.00 (non-core) | 20,000.00 (core)  0.00 (non-core) | 20,000.00 (core)  450,000.00 (non-core) | 20,000.00 (core)  0.00 (non-core) | 0.00 (core)  1,773,145.00 (non-core) | 80,000.00 (core)  2,223,145.00 (non-core) |
| **Impact3 The UN Women’s Spotlight strategy aims to protect women and girls against domestic violence such as rape, incest, sexual and moral harassment, deprivation and restriction of liberty, beatings, injuries etc. by ensuring holistic care services for women and girls survivors of violence with particular emphasis on the specific needs of groups exposed to multiple forms of discrimination.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Outcome 5 Public institutions and civil society improve the rule of law and decentralization for good governance at all levels of decision-making Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 3.1 The socio-cultural settings, as well as legislative, political, institutional and organizational frameworks are strengthened and structured to respond to domestic violence against women and girls  Related SP Outcome/Output:**   **Indicator 3.1A:** Percentage of people who think it is justified for a man (the subject) to beat his wife/intimate partner (with violence), by gender and age in at least one of the following cases If she is unfaithful to him? If she disobeys her husband / partner? If she argues with him? If she refuses to have sex with him? If she does not do housework properly? **Targets:  Value:** 3.7% **Target Year:** 2022 **Baseline:  Value:** 8.7% **Year:** 2020 **Note:** % persons 15-49 years old : 8.7% GDG survey 4 departments (sample: 2036) **Source:** Final Evaluation, Programme's report  **Indicator 3.1B:** Percentage of people who think it is right to subject a woman or girl to child marriage **Targets:  Value:** 3.7% **Target Year:** 2022 **Baseline:  Value:** 9.2% **Year:** 2022 **Note:** % persons 15-49 years old : 9.2% GDG survey in 4 dptns 2021 **Source:** Final Evaluation, Programme's report  **Indicator 3.1C:** Percentage of women's rights organizations, autonomous social movements, and relevant CSOs that increase their efforts to jointly advocate for the elimination of VAWG **Targets:  Value:** 10% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2020 **Note:** Denominator: 60 **Source:** Programme's report, Endline  **Indicator 3.1D:** Extent to which there is increased use of social accountability mechanisms by civil society to monitor and engage in efforts to eliminate VAW, including domestic violence (e.g., citizen report cards, community scorecards, UPR reports, citizen audits, citizen participation in policy making/decision making) **Targets:  Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Source:** Progress Programme Report  **Indicator 3.1E:** Proportion of women's rights organizations, autonomous social movements, and CSOs including those representing youth and groups exposed to multiple forms of cross-discrimination that report having greater influence in taking action against VAW, including domestic violence **Targets:  Value:** 15 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Progress Programme Report | **Output 3.1.1 Spotlight Outcome 1: Legislative and policy frameworks, based on evidence and in line with international human rights standards, on all forms of violence against women and girls and harmful practices are in place and translated into plans** | **Indicator 3.1.1A:** Number of new and/or strengthened draft laws and/or policies aimed at ending VAWG and/or gender equality and non-discrimination that address the rights of women and girls facing multiple and intersecting forms of discrimination and are consistent with international human rights standards developed in the past year **Targets:  Value:** 1 **Notes:** Project Overall Target: 2 (split into 1 UN Women and 1 UNDP)  **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2020 **Source:** Programme Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  266,948.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  148,555.00 (non-core) | 0.00 (core)  415,503.00 (non-core) |
| **Output 3.1.2 Spotlight Outcome 2: National and sub-national systems and institutions plan, fund and deliver evidence-based programmes that prevent and respond to violence against women and girls, including domestic violence and in other sectors.** | **Indicator 3.1.2A:** Programs and/or development plans at the national or sub-national level in other sectors to address VAWG that have been developed with significant input from women's rights advocates. **Targets:  Value:** Yes **Notes:** Justice: Yes Culture: N/A Autres: SNGRD: Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Notes:** Justice: N/S Culture: N/A Autres: SNGRD: Non **Source:** Programme's Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  245,359.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  111,008.00 (non-core) | 0.00 (core)  356,367.00 (non-core) |
| **Output 3.1.4 Spotlight Programme Management Costs** | **Indicator 3.1.4A:** Implementation rate of the spotlight's regular resources **Targets:  Value:** 85% **Target Year:** 2021 **Value:** 85% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2020 **Source:** Spotlight Programme Financial Report  **Indicator 3.1.4B:** Implementation rate for other resources **Targets:  Value:** 80% **Target Year:** 2021 **Value:** 80% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2020 **Source:** Spotlight Programme Financial Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  361,447.00 (non-core) | 0.00 (core)  361,447.00 (non-core) |
| **Output 3.1.5 Spotlight Outcome 3: Social norms, behaviors and gender attitudes at community and individual levels are changing to prevent violence against women and girls, including domestic violence** | **Indicator 3.1.5A:** Number of girls and boys who participate in school and out-of-school programs aimed at promoting gender equitable norms, attitudes and behaviors and the exercise of rights, including reproductive rights, in the past year **Targets:  Value:** 400 **Notes:** # girls and boys under 19 (out-of-school): 400 **Target Year:** 2022 **Value:** 300 **Notes:** # girls (out-of-school): 300 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** # girls and boys (under 19): 0 # girls and boys (out-of-school): 0 # girls: 0 # girls (out-of-school): 0 **Source:** Programme Monitoring Report, Programme Reports  **Indicator 3.1.5B:** Number of women, men, girls and boys who regularly participate (AT LEAST ONE ACTIVITY EVERY 2 MONTHS DURING ONE YEAR) in community-based programs aimed at promoting equitable gender norms, attitudes and behaviors, including those related to women's and girls' sexuality and reproduction, in the past year. **Targets:  Value:** 1176 **Notes:** # Total UNW: 1176 **Target Year:** 2022 **Value:** 576 **Notes:** # Women UNW: 576 **Target Year:** 2022 **Value:** 200 **Notes:** # Girls UNW: 200 **Target Year:** 2022 **Value:** 200 **Notes:** # Men UNW: 200 **Target Year:** 2022 **Value:** 200 **Notes:** # Boys UNW: 200 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** # Total UNW: 0 **Source:**  Programme Monitoring Report, Programme Reports   **Indicator 3.1.5C:** Number of people reached by campaigns against harmful social norms and gender stereotypes, in the past year **Targets:  Value:** 1000 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** # Total UNW: 0 **Source:**  Programme Monitoring Report, Programme Reports   **Indicator 3.1.5D:** Number of men and boys who regularly participate in gender transformative programs that address violent masculinities and men's violence against women and girls in community centers, schools and other meaningful spaces , during the last year **Targets:  Value:** 60 **Notes:** # Total men and boys UNW: 60 **Target Year:** 2022 **Value:** 30 **Notes:** # Boys under 19 UNW : 30 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2022 **Notes:** # Total men and boys UNW **Source:**  Programme Monitoring Report, Programme Reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  272,320.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  265,517.00 (non-core) | 0.00 (core)  537,837.00 (non-core) |
| **Output 3.1.6 Spotlight Outcome 4: Women and girls, survivors of all forms of violence and harmful practices, use quality essential services that are available, accessible and acceptable for their immediate and long-term recovery** | **Indicator 3.1.6A:** Existence of national guidelines or protocols that are consistent with guidelines and tools for essential services for women and girls victims of violence. **Targets:  Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Source:** Programme's Report; Monitoring Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  43,200.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  188,000.00 (non-core) | 0.00 (core)  231,200.00 (non-core) |
| **Output 3.1.7 Spotlight Outcome 6: Women's rights groups, autonomous social movements and relevant CSOs, including those representing youth and groups facing multiple and intersecting forms of discrimination/marginalization, more effectively influence and advance progress on GEWE and ending VAWG** | **Indicator 3.1.7A:** Number of joint recommendations to end VAW, produced over the past year as a result of multi-stakeholder dialogues including representatives of groups facing multiple and intersecting forms of discrimination (PRESENTED TO STATE BODY) **Targets:  Value:** 10 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Programme Report; Monitoring Report  **Indicator 3.1.7B:** Number of women's rights groups and CSOs supported that use the appropriate accountability mechanisms to advocate against VAW in the past year (e.g. CEDAW, UPR shadow reports and social responsibility such as social audits, evaluation bulletins, etc.) **Targets:  Value:** 20 **Notes:**   **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** # women's organizations and CSOs that use this type of mechanism  LB: 0  Denominator: 60 **Source:** Programme's Report; Monitoring Report  **Indicator 3.1.7C:** Number of women's rights groups and CSOs representing groups facing multiple and intersecting forms of discrimination / marginalization who have strengthened capacities and support to design, implement, monitor and evaluate their own anti-gender programs. GBV and family violence . **Targets:  Value:** 20 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** LB: 0 Denominator: 60 **Source:** Programme's Report and Monitoring Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  260,643.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  190,960.00 (non-core) | 0.00 (core)  451,603.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,088,470.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,265,487.00 (non-core) | 0.00 (core)  2,353,957.00 (non-core) |
| **Total Resources for impact area 3** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,088,470.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,265,487.00 (non-core) | 0.00 (core)  2,353,957.00 (non-core) |