

UN Women Strategic Note 2018-2022

**UN WOMEN India COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |
| --- | --- |
| **Impact1Women, especially from the most marginalized communities participate, lead and are represented in governance processes on equal terms at all levels** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: By 2022, women, children, and young people have improved access to equal opportunities and an enabling environment, to advance their social, economic and political rights Related national development priorities:Related national development priorities:** |
|  |  |  | **Year2018** | **Year2019** | **Year2020** | **Year2021** | **Year2022** | **Total** |
| **Outcome 1.1Conducive policy environment and enhanced institutional capacities of governance institutions to mainstream genderRelated SP Outcome/Output:****Indicator 1.1A:** Number of central ministries/departments that institutionalize mechanisms for gender mainstreaming (such as dedicated human resource as Gender Focal Points/Gender Budget Cells)**Targets: Value:** 61**Notes:** Additional 4 ministries to set up GBCs**Target Year:** 2022**Value:** 4**Notes:** Additional 4 ministries**Target Year:** 2021**Baseline: Value:** 4 **Year:** 2020**Source:** MWCD Annual Report 2016**Indicator 1.1B:** Number of state governments that have gender policies/women’s policies**Targets: Value:** 6**Notes:** Additional 2 states to develop their gender policies during SN period**Target Year:** 2022**Value:** 2**Target Year:** 2021**Baseline: Value:** 4 **Year:** 2020**Note:** (Maharashtra, MP, Odisha, Rajasthan) have developed Gender Policy**Source:** State Government Websites**Indicator 1.1D:** Number of ministries/departments at national/state levels that monitor specific resources to promote gender equality (such as outcome budgets)**Targets: Value:** 1 at the national level; and 2 at the state level**Target Year:** 2022**Value:** 1**Notes:** 1 at state level**Target Year:** 2021**Baseline: Value:** 2 **Year:** 2020**Source:** Ministry Websites**Indicator 1.1E:** Number of states which issue directives to mainstream gender in Local Development Plans such as GPDP**Targets: Value:** 3**Target Year:** 2022**Value:** 1**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2017**Source:** Baseline developed under UN Women- Governance project**Indicator 1.1F:** Formal mechanisms created for women’s organisations to provide regular inputs in policy design, implementation and monitoring at the national and state level (Y/N)**Targets: Value:** Y**Target Year:** 2022**Value:** Yes**Target Year:** 2021**Baseline: Value:** N **Year:** 2017**Source:** UN Women Report | **Output 1.1.5GRB mechanisms are refined and strengthened** | **Indicator 1.1.5A:** No. of central ministries and state departments with embedded technical support.**Targets: Value:** 5**Notes:** This target was achieved in 2020 and embedded resources to continue uptil 2022**Target Year:** 2022**Value:** 5**Notes:** This target was achieved in 2020 and embedded resources to continue uptil 2022**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Source:** Reports **Indicator 1.1.5B:** Number of national and state training institutions for which gender mainstreaming strategy developed**Targets: Value:** 8**Notes:** Additional 2 will be achieved in 2022 making it a total of 8**Target Year:** 2022**Value:** 6**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Source:** Minutes of meeting**Indicator 1.1.5C:** No. of states that conduct scoping study and adopt GRB action plans developed under the project.**Targets: Value:** 4**Notes:** This target is to be achieved in 2021**Target Year:** 2022**Value:** 4**Notes:** This target is to be achieved in 2021**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Source:** Study and Project reports**Indicator 1.1.5D:** Methodology and Manual for developing a gender budget statement prepared**Targets: Value:** Yes**Target Year:** 2022**Value:** Yes**Target Year:** 2021**Baseline: Value:** No **Year:** 2019**Source:** GRB Manual | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)508,447.00(non-core) | 0.00(core)269,637.00(non-core) | 0.00(core)778,084.00(non-core) |
| **Output 1.1.6Knowledge products, including customized training modules, developed on GRB** | **Indicator 1.1.6A:** No. of GRB sectoral analysis undertaken and published as policy briefs.**Targets: Value:** 8**Notes:** Additional 4 to be developed in 2022, making it a total target of 8**Target Year:** 2022**Value:** 4**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Source:** Knowledge and research products developed **Indicator 1.1.6B:** No. of national and state level workshops organised for dissemination of knowledge Products developed under the project.**Targets: Value:** 8**Notes:** Two workshops will be organized in 2022 making it a total target of 8**Target Year:** 2022**Value:** 6**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Source:** Consultation/training workshop reports**Indicator 1.1.6C:** No. of state-specific customized training modules and IEC material developed.**Targets: Value:** 4**Notes:** Additional one target to be achieved in 2022, making it a total target of 4**Target Year:** 2022**Value:** 3**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2021**Source:** Training modules and toolkit, Project Reports, Government reports and websites | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)212,078.00(non-core) | 0.00(core)246,202.00(non-core) | 0.00(core)458,280.00(non-core) |
| **Output 1.1.7Gender budgeting capacities of government stakeholders strengthened** | **Indicator 1.1.7A:** Level of knowledge and skills and training needs in gender budgeting of relevant stakeholders in 4 states identified**Targets: Value:** yes**Notes:** This target will be achieved in 2021.**Target Year:** 2022**Value:** Yes**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Source:** through Training Needs Assessment**Indicator 1.1.7B:** Percentage of workshop/training participants reported enhanced capacity to undertake gender Budgeting**Targets: Value:** 50%**Target Year:** 2022**Value:** 50%**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Source:** Training reports**Indicator 1.1.7C:** No. of states that have adopted capacity development strategy with outputs**Targets: Value:** 4**Target Year:** 2022**Value:** 2**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Source:** Capacity development strategy **Indicator 1.1.7D:** No. of gender budgeting capacity development programs for officials of relevant departments organized in 4 states**Targets: Value:** 8**Notes:** : 2 capacity development programmes will be conducted in 2022 making it a total of 8**Target Year:** 2022**Value:** 5**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Source:** Training reports of capacity development programs | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)78,896.00(non-core) | 0.00(core)257,474.00(non-core) | 0.00(core)336,370.00(non-core) |
| **Output 1.1.8E-governance tool on GRB developed** | **Indicator 1.1.8A:** Requisite material for e-governance tool developed**Targets: Value:** Yes**Target Year:** 2022**Value:** Yes**Target Year:** 2021**Baseline: Value:** No **Year:** 2019**Source:** E-Governance Tool | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)40,266.00(non-core) | 0.00(core)145,514.00(non-core) | 0.00(core)185,780.00(non-core) |
| **Output 1.1.9Enhanced knowledge and capacity of multi-stakeholders for increasing financing for gender equality** |  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 63,875.00(core)0.00(non-core) | 63,875.00(core)0.00(non-core) |
| **Outcome 1.2Conducive policy environment and enhanced institutional capacities of governance institutions to prevent and respond toall forms of violence against womenRelated SP Outcome/Output:****Indicator 1.2A:** Number of state/private institutions have policies to prevent and respond to all forms of violence**Targets: Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and Annual Report **Indicator 1.2B:** Number of service providers with enhanced capacities to prevent and respond to all forms of violence against women0**Targets: Value:** 5**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and annual report  | **Output 1.2.1Capacities and engagement of service providers to implement legislations, policies and programmes/plans relating to VAWG (Sexual Harassment Act, Information Technology Act and National Cyber Security Policy) are strengthened** | **Indicator 1.2.1A:** Number of VAWG action plans (both the center and states) relating to domestic, workplace and public spaces drafted**Targets: Value:** 12**Notes:** Additional 2 each year**Target Year:** 2022**Value:** 10**Target Year:** 2021**Baseline: Value:** 8 **Year:** 2020**Source:**  Government websites, reports, monitoring reports from partners and progress reports of consuktants**Indicator 1.2.1B:** Number of laws/ policies/programmes reviewed**Targets: Value:** 2**Target Year:** 2021**Value:** 3**Target Year:** 2022**Baseline: Value:** 2 **Year:** 2019**Source:** Programme reports, Meeting reports etc**Indicator 1.2.1C:** Number of relevant stakeholders that use training modules and monitoring tools relating to VAWG (SHA, BBBP, IT Act and SCM)**Targets: Value:** 8**Notes:** +2**Target Year:** 2021**Value:** 10**Notes:** +2**Target Year:** 2022**Baseline: Value:** 6 **Year:** 2020**Source:**  Programme Reports, Government reports **Indicator 1.2.1D:** Number of ministries and govt. institutions that have dedicated technical resources to EVAWG**Targets: Value:** 5**Target Year:** 2021**Value:** 6**Target Year:** 2022**Baseline: Value:** 4 **Year:** 2020**Source:** Programme Report, Progress Reports from embedded technical support | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 123,211.00(core)150,000.00(non-core) | 43,000.00(core)0.00(non-core) | 166,211.00(core)150,000.00(non-core) |
| **Output 1.2.2Women’s groups and community-based organizations have the capacity to foster accountability towards ending of all forms of violence against women and girls** | **Indicator 1.2.2A:** Dedicated women’s oversight groups, with representation from most marginalised and vulnerable groups (such as women from the dalit community, tribal communities, religious minorities, single women, trafficking survivors and women with disabilities), supported by UN Women to monitor implementation of EVAW laws, policies and programmes (Y/N)**Targets: Value:** yes**Target Year:** 2021**Value:** yes**Target Year:** 2022**Baseline: Value:** yes **Year:** 2020**Source:** Programme report, Meeting reports**Indicator 1.2.2B:** Proportion of women reached that start accessing essential services, including from the dalit community, tribal communities, religious minorities, single women, trafficking survivors and women with disabilities**Targets: Value:** 3%**Target Year:** 2021**Value:** 5%**Target Year:** 2022**Baseline: Value:** 1% **Year:** 2017**Source:** Training Reports, Programme Report  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 5,000.00(core)0.00(non-core) | 0.00(core)70,459.00(non-core) | 5,000.00(core)70,459.00(non-core) |
| **Output 1.2.3Ensure availability of, and accessibility to gender responsive and age sensitive protection and SGBV related multi-sectoral essential services for women and girls at risk of and/or survivors of SGBV (MPTF)** | **Indicator 1.2.3A:** Number of women and girls at risk and/or survivors of SGBV have access to SGBV case management and MHPSS services (Disaggregated by age, disability, ethnicity)**Targets: Value:** 150000**Target Year:** 2021**Value:** 250000**Target Year:** 2021**Baseline: Value:** TBD **Year:** 2020**Source:** Source: Programme reports**Indicator 1.2.3B:** Number of frontline healthcare professionals, staff of OSC have enhanced capacity on providing SGBV related services**Targets: Value:** 1200**Target Year:** 2021**Value:** 2000**Target Year:** 2022**Baseline: Value:** 500 **Year:** 2020**Source:** Programme reports**Indicator 1.2.3C:** Number of women and girls at risks/survivors of SGBV have access to Artificial Intelligence (AI) based solutions (Disaggregated by age, disability, ethnicity)**Targets: Value:** 100000**Target Year:** 2021**Value:** 150000**Target Year:** 2022**Baseline: Value:** TBD **Year:** 2020**Source:** Programme report, AI Dashboard | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)68,000.00(non-core) | 0.00(core)70,460.00(non-core) | 0.00(core)138,460.00(non-core) |
| **Output 1.2.4Enhanced capacity of the gender-sensitive justice systems for improved access of women and girls at risk of or survivors of GBV (MPTF)** | **Indicator 1.2.4A:** Number of states with referral mechanisms and training schemes in place by the National Police Academy to prevent and respond to SGBV/VAWG**Targets: Value:** tbd**Target Year:** 2021**Value:** 4**Target Year:** 2022**Baseline: Value:** 1 **Year:** 2020**Source:** Programme reports**Indicator 1.2.4B:** Number of officials from the law enforcement, security forces and select frontline functionaries trained on cyber safety and security**Targets: Value:** 3000**Target Year:** 2021**Value:** 5000**Target Year:** 2022**Baseline: Value:** 200 **Year:** 2020**Source:** Source: Training report | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)116,000.00(non-core) | 0.00(core)31,577.00(non-core) | 0.00(core)147,577.00(non-core) |
| **Output 1.2.5Women and girls are aware of the risks of SGBV and harmful practices, and increasingly engaged in decision making processes related to COVID-19 response and recovery (MPTF)** | **Indicator 1.2.5A:** Number of local authorities, women's and community groups and women elected representatives benefit from participation-based comprehensive interventions to prevent and respond to SGBV**Targets: Value:** 50000**Target Year:** 2021**Value:** 100000**Target Year:** 2022**Baseline: Value:** 20000 **Year:** 2020**Source:** Programme reports**Indicator 1.2.5B:** Number of women, girls, boys, men reached with messages on SGBV prevention and response through community based outreach, media campaigns, including social media platforms**Targets: Value:** 250000**Target Year:** 2021**Value:** 500000**Target Year:** 2022**Baseline: Value:** 100000 **Year:** 2020**Source:** Programme reports, Media Reports | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)74,310.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)74,310.00(non-core) |
| **Output 1.2.6Vulnerable families of women and girls at risk of and/or survivors of SGBV/VAC have reduced their economic vulnerability and increased access to livelihood and income generation programs (MPTF)** | **Indicator 1.2.6A:** Number of women and girls at risk and/or survivors of SGBV benefit from social protection and livelihood programmes (Disaggregated by age, disability, ethnicity)**Targets: Value:** 5000**Target Year:** 2021**Value:** 10000**Target Year:** 2022**Baseline: Value:** TBD **Year:** 2020**Source:** Programme reports**Indicator 1.2.6B:** Number of India's Flagship programmes on livelihoods that are gender sensitive**Targets: Value:** 1**Target Year:** 2021**Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** Programme reports, Media Reports**Indicator 1.2.6C:** Number of states with Gender Action Plan, including responding to SGBV, developed and implemented**Targets: Value:** 2**Target Year:** 2021**Value:** 3**Target Year:** 2022**Baseline: Value:** 1 **Year:** 2020**Source:** Programme report | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)285,453.00(non-core) | 0.00(core)96,225.00(non-core) | 0.00(core)381,678.00(non-core) |
| **Output 1.2.7Knowledge Management for Gender-Responsive COVID-19 Recovery including Women’s Health, Wellness and Safety in Rural Spaces in the Tea Sector in Assam** | **Indicator 1.2.7A:** Number of Communication Material Developed**Targets: Value:** 6**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and annual reports. UN Women India CO social media handles**Indicator 1.2.7B:** Number of monitoring visits conducted**Targets: Value:** 4**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Annual report, monitoring mission reports | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)5,070.00(non-core) | 0.00(core)269,336.00(non-core) | 0.00(core)274,406.00(non-core) |
| **Output 1.2.8One-Stop Centres (OSCs) have strengthened ability to deliver and ensure for the accessibility and availability of essential GBV services** | **Indicator 1.2.8A:** Number of frontline professionals and staff of OSCCs have enhanced capacity on providing GBV related services**Targets: Value:** 750**Target Year:** 2022**Baseline: Value:** 150 **Year:** 2021**Source:** Annual and Quarterly report **Indicator 1.2.8B:** Number of Women that OSCC served**Targets: Value:** 1000**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Reports from OSCC, annual report **Indicator 1.2.8C:** Number of guidelines developed and/or adapted**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 1 **Year:** 2021**Notes:** National Level**Source:** annual report **Indicator 1.2.8D:** Number of CSOs/GBV service providers that received grants**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Annual Report  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)4,955.00(non-core) | 0.00(core)106,995.00(non-core) | 0.00(core)111,950.00(non-core) |
| **Output 1.2.9Capacity of partners enhanced on women's health and wellbeing on measures to respond to escalating risks realted to VAWG during COVID-19(community meetings, IEC development, translation, publication and printing, training sessions with managers in tea sector, field vists etc.)** | **Indicator 1.2.9A:** Number of women workers, local women's orgnaizations informed and engaged on COVID-19 prevention and responses messages and strategies (Disaggregated by age, disability, ethnicity)**Targets: Value:** 10000**Target Year:** 2022**Baseline: Value:** 500 **Year:** 2021**Source:** Programme reports/ Meeting Minutes**Indicator 1.2.9B:** Number of women's organizations/women in tea sector trained/sensitized on women's wellness and safety messages**Targets: Value:** TBD**Target Year:** 2022**Baseline: Value:** TBD **Year:** 2021**Source:** Programme reports, Media Reports/training reports**Indicator 1.2.9C:** Number of managers/officials of tea estate and related servcies trained on gender approach in preparedness plans to respond to humanitarian crisis, including POST Act, Domestic Violence, VAWG**Targets: Value:** TBD**Target Year:** 2022**Baseline: Value:** TBD **Year:** 2021**Source:** Programme report**Indicator 1.2.9D:** Number of meetings conducted on Women's Safety and Empowerment Tea Platform in Assam to facilitate dialogue for gender responsive preparedness and management during humanitarian crisis**Targets: Value:** TBD**Target Year:** 2022**Baseline: Value:** TBD **Year:** 2021**Source:** Programme Report **Indicator 1.2.9E:** Number of mapping studies undertaken on the impact of COVID-19 on women and girls in the tea sector to inform national and local response and recovery plans in government and in industry**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Programme Report **Indicator 1.2.9F:** Number of reports/case studies impact of new labour laws and legal frameworks (including the Industrial Relations Code Bill 2020, the Occupational Safety and Health Working Conditions, 2020, specifically on women in tea sector**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Programme reports/scoping /case study study report | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)121,378.00(non-core) | 0.00(core)121,378.00(non-core) |
| **Output 1.2.10Multi-stakeholder partnership platforms strenghtened to identify and implement women’s health, wellness and safety solutions\* (women's rights/consultants for support to legal aid centre and delivery of critical services)** | **Indicator 1.2.10A:** Number of women workers access critical services in the tea sector**Targets: Value:** 300**Notes:** number of women**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Notes:** number of women**Source:** Annual Report **Indicator 1.2.10B:** Number of meetings of the Women's Saftey and Empowerment tea platform in Assam conducted to facilitate dialouge for gender responsive preparedness**Targets: Value:** 500**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** annual report  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)9,724.00(non-core) | 0.00(core)9,724.00(non-core) |
| **Output 1.2.11Local data available on the impact of COVID-19 on women and girls in the tea sector in selected intervention areas in Assam (multi site mapping, evidence on impact of new labour laws etc.)** | **Indicator 1.2.11A:** Conduct multi-site mapping on the impact of Covid-19 on women and girls in the tea sector to inform national and local response**Targets: Value:** 200**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Annual Report **Indicator 1.2.11B:** Generate evidence on the gendered impact of new labour laws and legal frameworks**Targets: Value:** 150**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Annual report  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)39,438.00(non-core) | 0.00(core)39,438.00(non-core) |
| **Output 1.2.12Women have increased access to and benefit from economic and livelihood opportunities to enhance COVID-19 recovery** | **Indicator 1.2.12A:** Number of women beneficiaries in the three project states who reported benefit from economic and livelihood opportunities**Targets: Value:** 900**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** annual report  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)130,150.00(non-core) | 0.00(core)130,150.00(non-core) |
| **Output 1.2.13National and regional platforms are strengthened to inform inclusive and gender-responsive measures to prevent the spread and the negative socio-economic impact of COVID-19 in line with the UN Secretary-General Socio-Economic Framework for COVID-19 Response** | **Indicator 1.2.13A:** Reach(number of downloads, distributions, etc) of regional knowledge products developed (UN Women ROAP Indicator 6.1.4A)**Targets: Value:** 300**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** annual report **Indicator 1.2.13B:** Number of actions taken by regional platforms to produce research and tools to inform gender-responsive response to COVID-19 (UN Women ROAP Indicator 6.1.4B)**Targets: Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Annual Report **Indicator 1.2.13C:** Reach (# of shares/likes, listeners) of advocacy and media campaigns, including most vulnerable groups about preventing COVID-19 and accessing essential services (UN Women ROAP Indicator 6.1.4C)**Targets: Value:** 10000**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Annual Report  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)122,879.00(non-core) | 0.00(core)122,879.00(non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)839,687.00(non-core) | 63,875.00(core)918,827.00(non-core) | 63,875.00(core)1,758,514.00(non-core) |
| **Total Resources for outcome 1.2 (core and non-core)** | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 128,211.00(core)703,788.00(non-core) | 43,000.00(core)1,068,621.00(non-core) | 171,211.00(core)1,772,409.00(non-core) |
| **Total Resources for impact area 1** | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 128,211.00(core)1,543,475.00(non-core) | 106,875.00(core)1,987,448.00(non-core) | 235,086.00(core)3,530,923.00(non-core) |
| **Impact2Women, especially the most marginalized, fully realize their right to sustainable livelihoods, income security and economic autonomy.** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: By 2022, environmental and natural resource management (NRM) is strengthened and communities have increased access to clean energy and are more resilient to climate change and disaster risks;By 2022, People vulnerable to social, economic and environmental exclusion have increased opportunities for productive employment through decent jobs and entrepreneurship;By 2022, women, children, and young people have greater opportunities and enjoy an environment that advances their social, economic, and political rightsRelated national development priorities:** |
|  |  |  | **Year2018** | **Year2019** | **Year2020** | **Year2021** | **Year2022** | **Total** |
| **Outcome 2.2More women lead, participate and have access to business opportunities to advance sustainable and inclusive growthRelated SP Outcome/Output:****Indicator 2.2A:** No. Of mentorship platforms created for women entrepreneurs**Targets: Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and Annual Report **Indicator 2.2B:** No of private sector companies/institutions engaged to increase women's labour force participation.**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and annual reporting | **Output 2.2.1Knowledge: Women’s networks, public institutions and the private sector in the EU and Asia share expertise and knowledge to advance an enabling business environment for women’s economic empowerment** | **Indicator 2.2.1A:** Percentage of participants targeted by outreach and advocacy events who acknowledge having engaged further on the topic on their own initiative as a result of their exposure to an event**Targets: Value:** 70**Target Year:** 2022**Value:** 70**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2019**Notes:** Online Survey**Source:** online survey | 0.00(core)0.00(non-core) | 0.00(core)151,636.00(non-core) | 0.00(core)0.00(non-core) | 38,276.00(core)110,271.00(non-core) | 29,875.00(core)100,723.00(non-core) | 68,151.00(core)362,630.00(non-core) |
| **Output 2.2.2Capacity development and technical assistance: Women-owned business and entrepreneurs have increased capacity to engage with governments and private sector companies in policies and dialogues for advancement of women’s economic empowerment** | **Indicator 2.2.2A:** Number of processes related to state level and sub- state level (bilateral, regional, multi-lateral) and non state partnership strategies and policy dialogues which have been influenced**Targets: Value:** 3**Target Year:** 2022**Value:** 1**Target Year:** 2019**Value:** 2**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2018**Notes:** Target to be refined during the inception phase**Source:** Annual progress reports/final evaluation of the project | 0.00(core)0.00(non-core) | 0.00(core)67,398.00(non-core) | 0.00(core)0.00(non-core) | 48,000.00(core)212,471.00(non-core) | 70,000.00(core)1,031,689.00(non-core) | 118,000.00(core)1,311,558.00(non-core) |
| **Output 2.2.3Advocacy and representation: More private sector companies implement the WEPs, including the gender-sensitive business culture and practices in EU and the country** | **Indicator 2.2.3A:** Number of WEPs signatories reporting to have an action plan for WEPs implementation and/or case studies about WEPs implementation**Targets: Value:** 158**Notes:** +100 from the baseline figure**Target Year:** 2022**Value:** 50**Notes:** +50**Target Year:** 2021**Baseline: Value:** 58 **Year:** 2018**Notes:** 58 WEPS Signatory from India. We do not have data on how many have action plan for WEPs.**Source:** https://www.empowerwomen.org/en/weps/companies | 0.00(core)0.00(non-core) | 0.00(core)67,398.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)138,912.00(non-core) | 0.00(core)41,683.00(non-core) | 0.00(core)247,993.00(non-core) |
| **Total Resources for outcome 2.2 (core and non-core)** | 0.00(core)0.00(non-core) | 0.00(core)286,432.00(non-core) | 0.00(core)0.00(non-core) | 86,276.00(core)461,654.00(non-core) | 99,875.00(core)1,174,095.00(non-core) | 186,151.00(core)1,922,181.00(non-core) |
| **Total Resources for impact area 2** | 0.00(core)0.00(non-core) | 0.00(core)286,432.00(non-core) | 0.00(core)0.00(non-core) | 86,276.00(core)461,654.00(non-core) | 99,875.00(core)1,174,095.00(non-core) | 186,151.00(core)1,922,181.00(non-core) |
| **Impact6Global norms, policies and standards on gender equality and women’s empowerment are translated into national laws and policies and implemented** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: By 2022, women, children, and young people have improved access to equal opportunities and an enabling environment, to advance their social, economic and political rights;2022, India’s voice and participation in multilateral fora is increased on matters of peace, security, human rights, development and humanitarian assistance Related national development priorities:** |
|  |  |  | **Year2018** | **Year2019** | **Year2020** | **Year2021** | **Year2022** | **Total** |
| **Outcome 6.1Governments and stakeholders (including civil society, UN and other relevant partners) have transparent systems and mechanisms in place to regularly review the implementation of global normative and policy frameworks on gender equality and women’s empowermentRelated SP Outcome/Output:****Indicator 6.1A:** Whether regular review of implementation of the normative commitments by government (CEDAW and SDGs) takes place at the central level and is made available publicly (Y/N)**Targets: Value:** Y**Target Year:** 2022**Value:** yes**Target Year:** 2021**Baseline: Value:** Y **Year:** 2017**Source:** OHCHR website - http://www.ohchr.org/EN/Countries/AsiaRegion/Pages/INIndex.aspx**Indicator 6.1B:** Whether formal mechanisms created for women’s organisations to provide regular inputs on the state of implementation of normative commitments are established (CEDAW, SDG) (Y/N)**Targets: Value:** Y**Target Year:** 2022**Value:** Yes**Target Year:** 2021**Baseline: Value:** N **Year:** 2017**Source:** UN Women website**Indicator 6.1C:** Whether national policies on Gender Mainstreaming in paramilitary institutions are adopted (Y/N)**Targets: Value:** Y**Target Year:** 2022**Value:** yes**Target Year:** 2021**Baseline: Value:** N **Year:** 2017**Source:** Annual report Ministry of Home Affairs | **Output 6.1.1Government and Civil Society have the capacity to report against CEDAW, SDGs, and CSW, and participate meaningfully on relevant inter-governmental platforms** | **Indicator 6.1.1A:** Number of Ministries and government institutions that have dedicated human and financial resources to monitor normative commitments on GEWE**Targets: Value:** 4**Target Year:** 2022**Value:** 1**Target Year:** 2021**Baseline: Value:** 2 **Year:** 2017**Source:** Respective ministry budget document**Indicator 6.1.1B:** Whether an institutional platform where women’s groups can share their recommendations with the government exists (Y/N)**Targets: Value:** Y**Target Year:** 2022**Value:** Yes**Target Year:** 2021**Baseline: Value:** N **Year:** 2017**Source:** UN Women documents  | 64,660.00(core)130,846.00(non-core) | 106,704.00(core)0.00(non-core) | 43,282.00(core)0.00(non-core) | 84,227.00(core)22,776.00(non-core) | 58,693.00(core)0.00(non-core) | 357,566.00(core)153,622.00(non-core) |
| **Output 6.1.2National and sub-national institutions and their staff have increased capacity to implement WPS normative commitments** | **Indicator 6.1.2A:** Number of knowledge products created and disseminated to UN Peacekeepers in the military and police which are incorporated in their training material and curriculum**Targets: Value:** 7**Notes:** Additional 1 per year**Target Year:** 2022**Value:** 1**Notes:** +1**Target Year:** 2021**Baseline: Value:** 2 **Year:** 2017**Source:** UN Women record**Indicator 6.1.2D:** Number of para-military institutions for which gender action plans are developed**Targets: Value:** 2**Target Year:** 2022**Value:** 1**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2017**Source:** UN Women annual report | 43,282.00(core)36,047.00(non-core) | 55,996.00(core)0.00(non-core) | 30,000.00(core)0.00(non-core) | 28,000.00(core)0.00(non-core) | 2,000.00(core)0.00(non-core) | 159,278.00(core)36,047.00(non-core) |
| **Output 6.1.3Women have capacity to respond to crisis through Leadership, Empowerment, Access & Protection** | **Indicator 6.1.3A:** Gender Analysis assessment conducted to inform crisis response and humanitarian planning**Targets: Value:** Yes**Target Year:** 2022**Baseline: Value:** no **Year:** 2018**Source:** UN Women Report, Assessment report | 0.00(core)0.00(non-core) | 10,000.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 12,000.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 22,000.00(core)0.00(non-core) |
| **Outcome 6.2Renewed commitments for gender equality and women's empowerment (GEWE) translate into a new feminist agenda settingRelated SP Outcome/Output:****Indicator 6.2A:** No. of CSOs, including youth and women’s movements, meaningfully participate in normative processes to advocate for GEWE commitments**Targets: Value:** 15**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and annual report  | **Output 6.2.1Multi-stakeholder advocacy dialogues present analysis of progress and gaps in implementation of Beijing Platform for Action** | **Indicator 6.2.1A:** Number of national consultations with stakeholders led by Member States with the support of UN Women**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 1 **Year:** 2020**Source:** UN Women documents **Indicator 6.2.1B:** Number of national reports on gaps, progress and challenges which include inputs from multi-stakeholder dialogues, supported by UN Women**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 1 **Year:** 2020**Source:** Government documents**Indicator 6.2.1C:** Number of thematic briefings and dialogues convened by UN-Women at the national and sub-national levels in preparation for intergovernmental processes**Targets: Value:** 3**Target Year:** 2022**Baseline: Value:** 1 **Year:** 2020**Source:** UN Women documents  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)63,000.00(non-core) | 0.00(core)105,000.00(non-core) | 0.00(core)168,000.00(non-core) |
| **Output 6.2.2CSOs, including youth and women’s movements, meaningfully contribute to Beijing+25 processes and lobby governments to renew their GEWE commitments** | **Indicator 6.2.2A:** Number of CSO partners supported to undertake advocacy initiatives**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women programme documents **Indicator 6.2.2B:** Youth groups supported in Beijing+25/GEF processes**Targets: Value:** yes**Target Year:** 2022**Baseline: Value:** no **Year:** 2020**Source:**  UN Women documents**Indicator 6.2.2C:** No. Of CSO advocacy toolkits prepared and dissemintaed**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women documents  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 6,840.00(core)232,394.00(non-core) | 0.00(core)169,653.00(non-core) | 6,840.00(core)402,047.00(non-core) |
| **Output 6.2.3Key stakeholders engaged in various global and regional fora on Beijing+25 review** | **Indicator 6.2.3B:** Number of stakeholders engaged in global, regional and national fora**Targets: Value:** TBD**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN women documents  | 0.00(core)14,000.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)44,000.00(non-core) | 0.00(core)39,833.00(non-core) | 0.00(core)97,833.00(non-core) |
| **Outcome 6.3Stakeholders (CSOs, private sector, academia, media, UN, etc.) mobilize and present key actions that will fuel progress on GEWE by 2025Related SP Outcome/Output:****Indicator 6.3A:** No. Of key stakeholders that participate in the normative processes**Targets: Value:** 5**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and annual report  | **Output 6.3.1Launch of concrete, ambitious andtransformative actions through multi-stakeholder partnerships in the form of Action Coalitions** | **Indicator 6.3.1A:** Number of Action Coalitions contributed to through support by UN Women**Targets: Value:** 3**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women Documents | 0.00(core)59,606.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)44,000.00(non-core) | 0.00(core)6,000.00(non-core) | 0.00(core)109,606.00(non-core) |
| **Outcome 6.4Advocacy and communications campaign builds momentum and galvanizes key groups and the general public towards support and actionRelated SP Outcome/Output:****Indicator 6.4A:** No. Of advocacy and communications campaigns to promote and raises awareness about Beijing+25, GE Forum, and renewed feminist agenda**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and annual report  | **Output 6.4.1Communications campaign promotes and raises awareness about Beijing+25, GE Forum, and renewed feminist agenda** | **Indicator 6.4.1A:** % increase of social media followers on Twitter, FB, Instagram**Targets: Value:** 10%**Target Year:** 2022**Baseline: Value:** TBD **Year:** 2020**Source:** Communications assessment reports **Indicator 6.4.1B:** Number of content produced for GEF**Targets: Value:** 10**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:**  UN Women documents  | 0.00(core)48,178.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)68,000.00(non-core) | 0.00(core)24,989.00(non-core) | 0.00(core)141,167.00(non-core) |
| **Total Resources for outcome 6.1 (core and non-core)** | 107,942.00(core)166,893.00(non-core) | 172,700.00(core)0.00(non-core) | 73,282.00(core)0.00(non-core) | 124,227.00(core)22,776.00(non-core) | 60,693.00(core)0.00(non-core) | 538,844.00(core)189,669.00(non-core) |
| **Total Resources for outcome 6.2 (core and non-core)** | 0.00(core)14,000.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 6,840.00(core)339,394.00(non-core) | 0.00(core)314,486.00(non-core) | 6,840.00(core)667,880.00(non-core) |
| **Total Resources for outcome 6.3 (core and non-core)** | 0.00(core)59,606.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)44,000.00(non-core) | 0.00(core)6,000.00(non-core) | 0.00(core)109,606.00(non-core) |
| **Total Resources for outcome 6.4 (core and non-core)** | 0.00(core)48,178.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)68,000.00(non-core) | 0.00(core)24,989.00(non-core) | 0.00(core)141,167.00(non-core) |
| **Total Resources for impact area 6** | 107,942.00(core)288,677.00(non-core) | 172,700.00(core)0.00(non-core) | 73,282.00(core)0.00(non-core) | 131,067.00(core)474,170.00(non-core) | 60,693.00(core)345,475.00(non-core) | 545,684.00(core)1,108,322.00(non-core) |
| **Impact5Marginalized women and young women have access to, participate in and achieve quality learning, entrepreneurship and employment outcomes through second chance education.** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: By 2022, People vulnerable to social, economic and environmental exclusion, have increased opportunities for productive employment through decent jobs and entrepreneurshipRelated national development priorities:** |
|  |  |  | **Year2018** | **Year2019** | **Year2020** | **Year2021** | **Year2022** | **Total** |
| **Outcome 5.1Marginalized women and young women have access to, participate in and achieve quality learning, entrepreneurship and employment outcomes through second chance education.Related SP Outcome/Output:****Indicator 5.1A:** Number of learners accessing high quality SCE content.**Targets: Value:** 10000**Notes:** Programme Target for India according to the ProDoc:**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2018**Source:** Programme Report**Indicator 5.1B:** Number of employed women and young women age 15-24 amongst programme graduates**Targets: Value:** 20%**Notes:** 20% annual increase among direct beneficiaries**Target Year:** 2019**Value:** 20%**Notes:** 20% annual increase among direct beneficiaries**Target Year:** 2020**Value:** 20%**Notes:** 20% annual increase among direct beneficiaries**Target Year:** 2021**Baseline: Value:** TBD **Year:** 2018**Note:** Baseline to be decided through needs assessment study**Source:** Programme reports**Indicator 5.1C:** Number of National Education Plans and Strategies that have a component that addresses social norms, attitudes, and behavior transformation.**Targets: Value:** 1**Notes:** 1 national education strategy**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2018**Source:** Programme reports**Indicator 5.1D:** Number of community spaces addressing attitude and behavioral change.**Targets: Value:** 1**Target Year:** 2021**Baseline: Value:** TBD **Year:** 2018**Note:** dependent on how many community spaces are operational during country needs assessments**Source:** Programme Documents**Indicator 5.1E:** Number of empowerment hubs in refugee settings addressing attitude and behavioral change**Targets: Value:** 8**Notes:** 8 empowerment Hubs per country**Target Year:** 2021**Baseline: Value:** TBD **Year:** 2018**Note:** dependent on how many community spaces are operational during country needs assessments**Source:** Programme Docuemnts**Indicator 5.1F:** New, revised or in active review/discussions of legislative frameworks or policies that promote second chance education and vocational training opportunities for women developed and/or being implemented in Programme countries.**Targets: Value:** Yes**Notes:** country models developed in each CO in the first 3 years**Target Year:** 2021**Baseline: Value:** No **Year:** 2018**Source:** Programme documents  | **Output 5.1.1Relevant content is developed and curated in each context.** | **Indicator 5.1.1A:** SCE e-learning platform is online and functional**Targets: Value:** Yes**Target Year:** 2019**Value:** Yes**Target Year:** 2021**Value:** yes **Target Year:** 2022**Baseline: Value:** No **Year:** 2018**Source:** SCE project report**Indicator 5.1.1B:** Number of training modules/curricula developed informed by SCE country needs assessments**Targets: Value:** 6**Target Year:** 2019**Value:** 3**Target Year:** 2021**Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project document | 0.00(core)82,000.00(non-core) | 0.00(core)30,294.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)102,136.00(non-core) | 0.00(core)53,976.00(non-core) | 0.00(core)268,406.00(non-core) |
| **Output 5.1.10Evidence-based advocacy for women’s and young women’s second chance education conducted with national and local policy makers.** | **Indicator 5.1.10A:** Gender-sensitive and multi-stakeholder second chance education needs assessments identifies education barriers,solutions, gaps and opportunities for young women.**Targets: Value:** YES**Notes:** country level assessments and policy recommendations.**Target Year:** 2022**Baseline: Value:** No **Year:** 2018**Source:** SCE project reports | 0.00(core)32,000.00(non-core) | 0.00(core)111,000.00(non-core) | 0.00(core)40,642.00(non-core) | 0.00(core)156,630.00(non-core) | 0.00(core)91,224.00(non-core) | 0.00(core)431,496.00(non-core) |
| **Output 5.1.11Cross sectoral legislative and policy reform supported to promote marginalized women’s and young women’s access to second chance education.** | **Indicator 5.1.11A:** Policy dialogues on the importance of women and young women’s right to education and vocational learningundertaking, with UN Women’s support**Targets: Value:** YES**Notes:** 1 policy dialogue per country**Target Year:** 2022**Baseline: Value:** No **Year:** 2018**Source:** SCE project reports | 0.00(core)0.00(non-core) | 0.00(core)59,294.00(non-core) | 0.00(core)64,000.00(non-core) | 0.00(core)124,731.00(non-core) | 19,472.00(core)72,731.00(non-core) | 19,472.00(core)320,756.00(non-core) |
| **Output 5.1.12Financing frameworks are supported to translate policies and strategies into practice.** | **Indicator 5.1.12A:** Revised budgetary allocations or frameworks in favor of marginalized young women’s access to second chanceeducation and vocational training.**Targets: Value:** YES**Target Year:** 2022**Baseline: Value:** No **Year:** 2018**Source:** SCE Project reports | 0.00(core)0.00(non-core) | 0.00(core)50,000.00(non-core) | 0.00(core)40,000.00(non-core) | 0.00(core)70,033.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)160,033.00(non-core) |
| **Output 5.1.13Comprehensive Programme Management including Knowledge development, sharing & communication and programme Monitoring & Evaluation** | **Indicator 5.1.13A:** # of knowledge products developed and shared**Targets: Value:** 4**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project reports | 0.00(core)39,830.00(non-core) | 0.00(core)200,000.00(non-core) | 0.00(core)200,000.00(non-core) | 0.00(core)367,957.00(non-core) | 45,022.00(core)279,812.00(non-core) | 45,022.00(core)1,087,599.00(non-core) |
| **Output 5.1.14Enable young women to pursue and complete higher education for degree or diploma and gain employable skill** | **Indicator 5.1.14A:** Number of participants sensitized on gender**Targets: Value:** 500**Target Year:** 2021**Value:** 2500**Target Year:** 2022**Value:** 5000**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly report, MIS**Indicator 5.1.14B:** Number of young women granted scholarship under the project**Targets: Value:** 750**Target Year:** 2021**Value:** 750**Target Year:** 2022**Value:** 750**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and Annual Reports, donor Reports and MIS**Indicator 5.1.14C:** Number of modules created under the project**Targets: Value:** 1**Target Year:** 2021**Value:** 5**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and Annual Report, Donor Report and MIS**Indicator 5.1.14D:** Number of companies’ gender sensitized under the project**Targets: Value:** 25**Target Year:** 2022**Value:** 50**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2021**Source:** Quarterly and Annual Reporting, donor reporting and MIS | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)80,408.00(non-core) | 0.00(core)169,913.00(non-core) | 0.00(core)250,321.00(non-core) |
| **Output 5.1.2Learning and career pathways are followed by women and young women accessing appropriate e-learning platforms** | **Indicator 5.1.2A:** Number and % of users signing up (enrollment) for online learning Programmes accessed through the UN Womenwelearn.unwomen.org web platform.**Targets: Value:** 10000**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project document**Indicator 5.1.2B:** Number and % of users completing online learning programmes accessed through the UN Women VSS**Targets: Value:** 10000**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project Document | 0.00(core)35,000.00(non-core) | 0.00(core)185,900.00(non-core) | 0.00(core)17,294.00(non-core) | 0.00(core)209,221.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)447,415.00(non-core) |
| **Output 5.1.3Context-specific delivery mechanisms are established, including safe community-based centers or Women’s Empowerment Hubs** | **Indicator 5.1.3A:** Number of physical spaces or Women’s Empowerment Hubs providing access to VSS e-learning platform and otherSCE learning opportunities established, with UN-Women’s support**Targets: Value:** 1**Notes:** 1 community space and 1 Women’s Empowerment Hub**Target Year:** 2019**Value:** 12**Target Year:** 2021**Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project document**Indicator 5.1.3B:** Number of partnerships established identifying the community spaces with local governments, communities andprivate sector partners to create safe learning spaces.**Targets: Value:** 74**Notes:** ( 30 Pvt. Sec +5 government+ 15 Training Partners + 24 District partnerships)**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project reports | 0.00(core)10,000.00(non-core) | 0.00(core)420,000.00(non-core) | 0.00(core)200,000.00(non-core) | 0.00(core)210,760.00(non-core) | 0.00(core)121,408.00(non-core) | 0.00(core)962,168.00(non-core) |
| **Output 5.1.4Potential employers in the private, public and NGO sector become more gender-aware and gender responsive and more women and young women are hired and retained.** | **Indicator 5.1.4A:** Number of government entities, companies, and/or international organizations that have strengthened capacity tointegrate gender-responsive actions into employment strategies and programmes, with UN Women’s support, andare hiring more women than previously.**Targets: Value:** 4**Target Year:** 2021**Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE Project reports | 0.00(core)10,000.00(non-core) | 0.00(core)60,000.00(non-core) | 0.00(core)40,000.00(non-core) | 0.00(core)99,180.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)209,180.00(non-core) |
| **Output 5.1.5Private and public sector offer bridging programmes which are taken up by women and young women graduates emerging from the Programme** | **Indicator 5.1.5A:** Number of government entities, companies, and/or international organizations that develop and/or implementgender-responsive employment policies or Programmes with UN Women’s support.**Targets: Value:** 1**Target Year:** 2021**Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project reports | 0.00(core)0.00(non-core) | 0.00(core)92,044.00(non-core) | 0.00(core)30,000.00(non-core) | 0.00(core)121,705.00(non-core) | 0.00(core)16,623.00(non-core) | 0.00(core)260,372.00(non-core) |
| **Output 5.1.6Graduate mentoring and coaching programme established. Women and young women become mentors to new learners to share experiences, advice, and support for second chance education.** | **Indicator 5.1.6A:** % of graduate women and young women who are mentoring new learners six months after completing Programmeor gaining qualifications and/or beyond the Programme period.**Targets: Value:** 20%**Target Year:** 2021**Value:** 20**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project reports | 0.00(core)0.00(non-core) | 0.00(core)82,764.00(non-core) | 0.00(core)50,000.00(non-core) | 0.00(core)1,300,545.00(non-core) | 0.00(core)203,103.00(non-core) | 0.00(core)1,636,412.00(non-core) |
| **Output 5.1.7Awareness and advocacy of the importance of women’s and young women’s right to education and entrepreneurship and vocational learning, and how this benefits their families and societies is increased.** | **Indicator 5.1.7A:** Number of national awareness and advocacy campaigns on the importance of young women’s right to educationand vocational learning undertaken, with UN Women’s support.**Targets: Value:** 1**Notes:** 1 Campaign per country awareness raising sessions in 2 Empowerment Hubs per country, 1 communityspace per country.**Target Year:** 2021**Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project reports | 0.00(core)16,000.00(non-core) | 0.00(core)65,500.00(non-core) | 0.00(core)40,000.00(non-core) | 0.00(core)141,089.00(non-core) | 0.00(core)40,000.00(non-core) | 0.00(core)302,589.00(non-core) |
| **Output 5.1.8Engagement with community stakeholders, households and individuals to support women’s and young women’s education and entrepreneurship and vocational learning is promoted.** | **Indicator 5.1.8A:** Conducting community activities with women and men, boys and girls on gender equality and the right to educationof women and girls**Targets: Value:** 1**Target Year:** 2021**Value:** 10**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2018**Source:** SCE project documnt | 0.00(core)6,000.00(non-core) | 0.00(core)60,000.00(non-core) | 0.00(core)37,000.00(non-core) | 0.00(core)118,644.00(non-core) | 0.00(core)4,363.00(non-core) | 0.00(core)226,007.00(non-core) |
| **Output 5.1.9Women’s and young women’s education, entrepreneurship and vocational learning opportunities are supported and reinforced through social systems and networks** | **Indicator 5.1.9A:** Number of peer networks for women and young women established, with UN Women’s support per country.**Targets: Value:** SCE specific peer network through Empowerment Hubs (or community spaces)**Target Year:** 2021**Value:** 10**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2019**Source:** SCE project reports | 0.00(core)0.00(non-core) | 0.00(core)50,000.00(non-core) | 0.00(core)38,000.00(non-core) | 0.00(core)82,832.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)170,832.00(non-core) |
| **Total Resources for outcome 5.1 (core and non-core)** | 0.00(core)230,830.00(non-core) | 0.00(core)1,466,796.00(non-core) | 0.00(core)796,936.00(non-core) | 0.00(core)3,185,871.00(non-core) | 64,494.00(core)1,053,153.00(non-core) | 64,494.00(core)6,733,586.00(non-core) |
| **Total Resources for impact area 5** | 0.00(core)230,830.00(non-core) | 0.00(core)1,466,796.00(non-core) | 0.00(core)796,936.00(non-core) | 0.00(core)3,185,871.00(non-core) | 64,494.00(core)1,053,153.00(non-core) | 64,494.00(core)6,733,586.00(non-core) |