

UN Women Strategic Note 2019-2022

**UN WOMEN Kenya COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact1 Women in Kenya are empowered in driving Kenya’s gender responsive governance led by a more coherent, influential, accountable and coordinated women’s movement** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Outcome 1:1 By 2022, people in Kenya enjoy improved governance, access to justice, respect for the rule of law, human rights and gender equality Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 1.1 Participation by women in politics and decision making increased  Related SP Outcome/Output:**   **Indicator 1.1B:** Proportion of women in political leadership positions at national and county level institutions **Targets:  Value:** 30 **Notes:** Parliament 30% Senate 33%, National assembly 27%, County Assemblies 34.5% **Target Year:** 2022 **Baseline:  Value:** 23 **Year:** 2020 **Note:** Parliament 23% Senate 31.3%, national assembly 23.3%, County Assemblies 34.5% **Source:** National data, UN Women and partner reports | **Output 1.1.1 Capacities of targeted institutions to develop and implement legal frameworks that promote women political participation and decision making strengthened** | **Indicator 1.1.1A:** Number of recommendations made on law reforms to promote women’s participation in electoral processes with UN Women support **Targets:  Value:** 1 **Notes:** Milestone 2022: 1 IEBC Act **Target Year:** 2022 **Value:** 1 **Notes:** Milestone 2020: 1 Political Parties Act. **Target Year:** 2020 **Value:** 1 **Notes:** Milestone 2021: 1 - Elections Act **Target Year:** 2021 **Baseline:  Value:** 3 **Year:** 2020 **Notes:** 3 Elections act, PP Act, IEBC Act **Source:** Reports of UN Women, ORPP and target institutions; NGEC& KNCHR State of Human Rights Reports.  **Indicator 1.1.1B:** Number of policy engagements by NSA on law reforms to promote women's participation in electoral processes with UN Women support. **Targets:  Value:** 4 **Notes:** 4 2/3rd and 50/50 engagement on COWA, IEBC and PP Act compliance to 2/3rd **Target Year:** 2022 **Value:** 2 **Notes:** Milestone 2020: 2 2/3rd gender rule and COWA-50/50 representation in executive **Target Year:** 2020 **Value:** 2 **Notes:** Milestone 2021:2 Political parties Act and IEBC Act on 2/3rd compliance **Target Year:** 2021 **Baseline:  Value:** 2 **Year:** 2020 **Notes:** 2 2/3rds and COWA **Source:** NGEC, SDfG, UN Women, CMD, ORPP, FIDA, KEWOPA reports | 0.00 (core)  105,300.00 (non-core) | 0.00 (core)  80,000.00 (non-core) | 0.00 (core)  110,500.00 (non-core) | 0.00 (core)  520,000.00 (non-core) | 0.00 (core)  815,800.00 (non-core) |
| **Output 1.1.2 Capacities to advance GEWE by women in decision making positions enhanced** | **Indicator 1.1.2A:** Number of GEWE recommendations in national assembly proposed with UN Women support **Targets:  Value:** 4 **Notes:** 4 2/3rd, COWA, IEBC Act and Political Parties Act **Target Year:** 2022 **Value:** 3 **Notes:** 3 2/3rd COWA and compliance of PP Act on 2/3rd **Target Year:** 2020 **Value:** 3 **Notes:** 3 2/3rd, COWA, compliance on IEBC Act on 2/3rd **Target Year:** 2021 **Value:** 2 **Target Year:** 2020 **Baseline:  Value:** 2 **Year:** 2020 **Notes:** 2 (2/3rd on article 100 and Common Women Agenda-COWA) **Source:** (KEWOPA, NGEC, FIDA, UN Women reports))  **Indicator 1.1.2B:** Number of GEWE recommendations in county assemblies proposed with UN Women support **Targets:  Value:** 10 **Notes:** 10 gender responsive motions/ bills at county level **Target Year:** 2022 **Value:** 2 **Notes:** 2 gender mainstreaming and capacity development policies for women leaders in 2 counties **Target Year:** 2020 **Value:** 2 **Notes:** 2 gender mainstreaming and capacity development policies for women leaders in 2 counties **Target Year:** 2021 **Baseline:  Value:** 10 **Year:** 2020 **Notes:** 10 gender responsive motions that were moved in 2019 in 9 counties (Source of Data - SOCATT UN Women Data) **Source:** (CAF, SOCATT, UN Women reports)   **Indicator 1.1.2C:** Number of GEWE recommendations proposed by CSOs with UN Women support **Targets:  Value:** 2 **Notes:** 2 2/3rds and 50/50 representation policies **Target Year:** 2022 **Value:** 15 **Notes:** 1 draft recommendations on 2/3rds through article 100 and Covid-19: GROOTS: (2020): 14 **Target Year:** 2020 **Value:** 1 **Notes:** 1 draft recommendations on 50/50 representation at executive level **Target Year:** 2021 **Baseline:  Value:** 2 **Year:** 2020 **Notes:** 2 (2/3rds in decison making and common women Agenda (COWA) by CSOs and parliament/ KEWOPA) **Source:** UN women and partner reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  344,000.00 (non-core) | 0.00 (core)  344,000.00 (non-core) |
| **Output 1.1.3 Increased community and civic understanding of women's right to political participation** | **Indicator 1.1.3A:** Number of gender champions promoting women's leadership and participation in decision making with UN Women support **Targets:  Value:** 25 **Notes:** 25 in select counties **Target Year:** 2022 **Value:** 54 **Notes:** 10 in 2 select counties + Covid-19: AWCFS: (2020): 14 + 20. GROOTS: (2020): 10 (Covid-response committees). **Target Year:** 2020 **Value:** 10 **Notes:** 10 in 2 select counties **Target Year:** 2021 **Baseline:  Value:** 5 **Year:** 2020 **Source:** UN Women reports  **Indicator 1.1.3B:** Number of gender sensitive coverage by media promoting visibility of women in leadership with UN Women support **Targets:  Value:** 20 **Target Year:** 2022 **Value:** 38 **Notes:** Added Covid-19: AWCFS: (2020): 10 + 10. GROOTS: (2020): 8. **Target Year:** 2020 **Value:** 10 **Target Year:** 2021 **Baseline:  Value:** 11 **Year:** 2018 **Notes:** 11 in 2018 by AWCFS, MCK **Source:** UN Women reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  602,144.00 (non-core) | 0.00 (core)  602,144.00 (non-core) |
| **Outcome 1.2 Increased budgetary allocation for GEWE at national and county level  Related SP Outcome/Output:**   **Indicator 1.2B:** % of budget allocated to GEWE **Targets:  Value:** 3.5 **Notes:** 3.5% national level, 10% by 2022 at county level (CIDP analysis report and KIPRA policy briefs) **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2020 **Note:** 1% national level. 5% 2020 at county level (CIDPs analysis reports) **Source:** CIDPs analysis reports and KIPRA policy briefs | **Output 1.2.1 Capacities and systems of targeted institutions for inclusive planning and budgeting enhanced** | **Indicator 1.2.1K:** Number of policies that advance inclusive planning and budgeting at national and county level with UN Women support **Targets:  Value:** 3 **Notes:** Milestone 2020 Value: 3 policies/guidelines Note: Support to national institutions in formulation of gender responsive policies or guidelines on: (a) public participation; (b) access to information; (c) governance of transboundary resources; (d) performance management at county level (e) marginalization policy master plan; (f) mainstreaming guidelines for county assemblies **Target Year:** 2020 **Value:** 3 policies/guidelines/recommendations **Notes:** a) Domestication of GEWE policies/guidelines and budget brief recommendations for inclusive plans and budgets in at least 4 counties,  b) public participation and access to information policies/recommendations disseminated in at least 4 counties;  c) Model gender policy domesticated in at least 4 counties **Target Year:** 2021 **Value:** 3 policies/guidelines/recommendations **Notes:** a) Domestication of GEWE policies/guidelines and budget brief recommendations for inclusive plans and budgets in at least 4 counties, b) public participation and access to information policies/recommendations disseminated in at least 4 counties; c) Model gender policy domesticated in at least 4 counties **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2019 **Source:** Policy/guidelines documents, UN Women reports, IP Reports   **Indicator 1.2.1L:** Number of institutions with systems to implement and monitor inclusive planning and budgeting with UN Women support **Targets:  Value:** 2 institutions **Notes:** County Policy Briefs on inclusive planning and budgeting recommendations, GM guidelines developed through CAF/SOCATT/COG partnerships **Target Year:** 2020 **Value:** 3 **Notes:** 2 national PMF institutions supported through capacity and systems strengthening to integrate gender dimensions within their mandate; 1 county institution supported to mainstream gender in planning and budgeting processes **Target Year:** 2021 **Value:** 4 **Notes:** 1 national PMF institutions supported through capacity and systems strengthening to integrate gender dimensions within their mandate;  3 county institutions supported to advance GRB **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women reports, CAF/SOCATT quarterly reports, JP progress reports   **Indicator 1.2.1M:** Number of assessments, policy measures, recovery plans, guidelines and advisory notes developed on gender-responsive prevention and response to Covid-19 with UN Women support **Targets:  Value:** 8 **Notes:** 2 AWCFS, 2 GROOTS, 2 GVRC, Statistics: GRA 1 and KNBS household survey 1 **Target Year:** 2020 **Value:** 8 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Value:** 3 **Target Year:** 2021 **Value:** 3 **Target Year:** 2021 **Value:** 3 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** Indicator for 2020 but can monitor implementation of COVID 19 guidelines developed in 2020 **Source:** Partner reports, finalized assessmet GRA and KNBS household | 0.00 (core)  0.00 (non-core) | 0.00 (core)  326,700.00 (non-core) | 0.00 (core)  326,700.00 (non-core) | 0.00 (core)  651,000.00 (non-core) | 0.00 (core)  1,304,400.00 (non-core) |
| **Output 1.2.2 Capacities of gender equality advocates to advocate for gender responsive plans and budgets enhanced** | **Indicator 1.2.2A:** Number of budget recommendations submitted by gender equality advocates with UN Women support **Targets:  Value:** 7 **Notes:** 7 recommendations made by gender equality advocates to advance inclusive planning and budgeting (1 in 7 counties) **Target Year:** 2021 **Value:** 14 **Notes:** 14 recommendations made by gender equality advocates to advance inclusive planning and budgeting (1 in 17 Joint Programme Counties) **Target Year:** 2022 **Value:** 2 **Notes:** 2 recommendations made by gender equality advocates to advance inclusive planning and budgeting **Target Year:** 2020 **Baseline:  Value:** 2 **Year:** 2020 **Notes:** 2 recommendations made gender equality advocates to advance inclusive planning and budgeting **Source:** Reports from IPs - NSAs, SOCATT, CAF, CoG, OCOB, CRA, UN Women reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) |
| **Output 1.2.3 Capacities of state-and non-state actors to monitor and report on progress in implementation of global normative and policy frameworks on GEWE enhanced** | **Indicator 1.2.3A:** Number of reports submitted to Treaty Bodies in time with UN Women support **Targets:  Value:** 2 **Notes:** 2 CSW 66, CEDAW 9 supplementary report **Target Year:** 2022 **Value:** 3 **Notes:** CSW 64/BPFA political declaration action plan for Kenya, CEDAW8 Action Plan, 9th CEDAW, VNR **Target Year:** 2020 **Value:** 2 **Notes:** CSW 65, AU solemn declaration on gender **Target Year:** 2021 **Baseline:  Value:** 4 **Year:** 2019 **Notes:** Baseline: 4 8th CEDAW, CSW 62, Gender score card & BPFA+20, Kenya SDGs VNR **Source:** SDGA reports, State department of planning reports, COG reports and Attorney general reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  54,000.00 (non-core) | 0.00 (core)  54,000.00 (non-core) | 0.00 (core)  54,000.00 (non-core) | 0.00 (core)  162,000.00 (non-core) |
| **Outcome 1.3 Gender statistics, sex-disaggregated data and knowledge are produced, analyzed and used to inform policy-making, advocacy and accountability for delivering gender equality and women's empowerment results.  Related SP Outcome/Output:** | **Output 1.3.1 Gaps in the planning, coordination, production and use of gender statistics at National and County level are identified and sustainably addressed** | **Indicator 1.3.1A:** Indicator 1.1.a: Number of inter-agency coordination mechanisms governing the production of multi-level disaggregated gender statistics and sex-disaggregated data strengthened (SP) **Targets:  Value:** 3 **Notes:** Minutes of meeting and workshops (MTP IV Gender Sector Plan, Indicator Handbook, new UN Sustainable Development Cooperation Framework) **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2021 **Source:** Source: Minutes of meeting and workshops  **Indicator 1.3.1B:** Indicator 1.1.b: Number of plans, policies and normative frameworks with minimum sets of gender indicators mainstreamed with support from UN Women. **Targets:  Value:** Yes **Notes:** MTP IV Gender Sector Plan **Target Year:** 2022 **Value:** 1 **Notes:** MTP IV Gender Sector Plan **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2018 **Notes:** MTP III Gender Sector Plan **Source:**  MTP IV Gender Sector Plan | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  252,390.00 (non-core) | 0.00 (core)  252,390.00 (non-core) |
| **Output 1.3.2 Technical capacity of governments, civil society and other key actors is strengthened to improve the production and use of gender statistics.** | **Indicator 1.3.2A:** Number of data producers and users with strengthened capacities in the collection, analysis, dissemination and use of gender statistics (SP) **Targets:  Value:** 2 **Target Year:** 2022 **Value:** 300 **Notes:** Time Use Survey data collection will be completed in December 2021 and care work capacity building will begin in 2022.  SCOA implementation also scheduled for 2022. **Target Year:** 2022 **Baseline:  Value:** 388 **Year:** 2021 **Notes:** Time Use Survey data collection will be completed in December 2021 and care work capacity building will begin in 2022.   SCOA implementation also scheduled for 2022. **Source:** Training/Workshop Reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  188,913.00 (non-core) | 0.00 (core)  188,913.00 (non-core) |
| **Output 1.3.3 Increased data production and analysis to monitor the SDGs and other national and international priorities.** | **Indicator 1.3.3A:** Number of gender statistics and sex-disaggregated data collection initiatives, including in emerging areas, conducted or analyzed **Targets:  Value:** 3 **Notes:** Time Use Survey, Kenya Demographic Health Survey-2022 and SIGI **Target Year:** 2022 **Value:** 2 **Notes:** Data collection initiatives; 1. Kenya Demographic Health Survey-2022  2. Social Institutions and Gender Index (SIGI) survey **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** Data collection initiatives: 1. Kenya Population and Housing Census -2019 2. Time Use Survey 2021 **Source:** Kenya Demographic Health Survey-2022 and SIGI  **Indicator 1.3.3B:** SDG gender-related indicators that are produced by reprocessing existing data. **Targets:  Value:** 2 **Notes:** Inequality Study, Unpaid Care and Domestic Work qualitative analysis report **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2021 **Notes:** Women Empowerment Index, Comprehensive Poverty Report, Gender Dimensions Monograph **Source:** Inequality Study, Unpaid Care and Domestic Work qualitative analysis report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  458,672.00 (non-core) | 0.00 (core)  458,672.00 (non-core) |
| **Output 1.3.4 Statistical business processes are increasingly modernized to improve the production of gender statistics.** | **Indicator 1.3.4A:** Number of non-conventional data collection initiatives with focus on gender issues conducted and/or analysed with UN Women’s support. **Targets:  Value:** Yes **Target Year:** 2022 **Value:** 1 **Notes:** Citizen Generated Guidelines for Kenya **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** Citizen Generated Guidelines for Kenya **Source:** Citizen Generated Guidelines for Kenya | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  20,000.00 (non-core) | 0.00 (core)  20,000.00 (non-core) |
| **Output 1.3.5 Increased use of gender statistics for policy-making, budgeting and reporting is promoted** | **Indicator 1.3.5A:** Number of institutionalized user-producer dialogues to increase accessibility, quality and demand for multi-level disaggregated gender statistics, sex-disaggregated data and knowledge **Targets:  Value:** 5 **Notes:** Time Use Survey launch report, students' symposium report, journalists' symposium report, GROOTS meetings reports **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2021 **Source:** Time Use Survey launch report, students' symposium report, journalists' symposium report, GROOTS mee | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  174,800.00 (non-core) | 0.00 (core)  174,800.00 (non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | | | 0.00 (core)  105,300.00 (non-core) | 0.00 (core)  80,000.00 (non-core) | 0.00 (core)  110,500.00 (non-core) | 0.00 (core)  1,466,144.00 (non-core) | 0.00 (core)  1,761,944.00 (non-core) |
| **Total Resources for outcome 1.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  380,700.00 (non-core) | 0.00 (core)  380,700.00 (non-core) | 0.00 (core)  705,000.00 (non-core) | 0.00 (core)  1,466,400.00 (non-core) |
| **Total Resources for outcome 1.3 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,094,775.00 (non-core) | 0.00 (core)  1,094,775.00 (non-core) |
| **Total Resources for impact area 1** | | | 0.00 (core)  105,300.00 (non-core) | 0.00 (core)  460,700.00 (non-core) | 0.00 (core)  491,200.00 (non-core) | 0.00 (core)  3,265,919.00 (non-core) | 0.00 (core)  4,323,119.00 (non-core) |
| **Impact3 Kenyans are increasingly socialized to uphold and respect women's’ rights, gender equality and oppose all forms of discrimination and violence against women and girls** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Outcome 2.5: By 2022 Marginalized and vulnerable people especially women and children to have increased access to and utilize social protection, and services for prevention and response to gender based violence and violence against children Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 3.1 Favorable social normal, attitudes and behaviors are promoted at communty and individual levels to prevent VAWG  Related SP Outcome/Output:**   **Indicator 3.1A:** Percentage of people who believe that man is justified to beat his partner under given circumstances **Targets:  Value:** 10% **Target Year:** 2022 **Baseline:  Value:** 6% (national) 41.8% (Kitui, Turkana, Marsabit and Kwale) **Year:** 2021 **Note:** 6% (National) 41.8% (average: Kitui, Turkana, Marsabit and Kwale) **Source:** Baseline study in 2021 and end line survey to be conducted. | **Output 3.1.1 Women, girls, men and boys at community and individual level are mobilized in favor of gender equality and respectful relationships** | **Indicator 3.1.1A:** Number of people reached with advocacy messages on VAWG prevention/ women's leadership/ resilience/ WPS/ women's economic empowerment/ Covid-19 with UN Women support **Targets:  Value:** 14,000 **Notes:** Total 3,311,550 from the years **Target Year:** 2022 **Value:** 3,268,450 **Notes:** 2020: 15,000 + GVRC: 2020: 27,000+ 57,000. FEMNET 4000 (men and boys in H6 counties). HAK: 235,000. AWCFS: 2020: 1 million. GROOTS: 2020: 1 million. HAWENKA: 2020: 1000+1000. WWFP: 2020: 90,850. RWPL: 2020: 600 (flyers)+ 750,000 (radio). UWEZA (2020): 57,000. KABWO: 30,000 **Target Year:** 2020 **Value:** 29,100 **Notes:** 17,000 +CREAW: 2021: 4800 +800. FEMNET 2021: 2500 (men and boys)+ 4000 new men and boys. **Target Year:** 2021 **Value:** 14000 **Target Year:** 2022 **Baseline:  Value:** 13,500 **Year:** 2020 **Source:** UN Women and partner reports | 0.00 (core)  195,000.00 (non-core) | 0.00 (core)  90,000.00 (non-core) | 0.00 (core)  90,000.00 (non-core) | 0.00 (core)  320,000.00 (non-core) | 0.00 (core)  695,000.00 (non-core) |
| **Output 3.1.2 Capacities of targeted institutions to facilitate safe spaces that prevent sexual harrassment of women and girls strengthened** | **Indicator 3.1.2A:** Number of safe spaces created with UN Women support **Targets:  Value:** 3 **Target Year:** 2020 **Value:** 4 **Target Year:** 2021 **Value:** 3 **Notes:** In total, the target is to have 20 safe spaces with UN Women support **Target Year:** 2022 **Baseline:  Value:** 10 **Year:** 2020 **Notes:** 10 safe space provided 1 by Unilever (Kericho and Bomet counties) and 9 by Universities **Source:** UN Women and partner reports | 0.00 (core)  248,000.00 (non-core) | 0.00 (core)  140,000.00 (non-core) | 0.00 (core)  140,000.00 (non-core) | 0.00 (core)  140,000.00 (non-core) | 0.00 (core)  668,000.00 (non-core) |
| **Outcome 3.2 Uptake of essential justice services by survivors VAWG increased  Related SP Outcome/Output:**   **Indicator 3.2A:** Average time taken to complete police investigation in reported cases of VAWG **Targets:  Value:** 6 months **Target Year:** 2022 **Baseline:  Value:** 1 to 2 years **Year:** 2021 **Note:** 1 to 2 years **Source:** Baseline survey and data collection tools | **Output 3.2.1 Effective development/implementation of EVAWG laws and policies enhanced** | **Indicator 3.2.1A:** Number of laws and policies developed on VAWG prevention and response with UN Women support **Targets:  Value:** 2 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Value:** 3 **Notes:** 8 County GBV policies in 8 counties (Finland and Italy funded counties) **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2020 **Notes:** 1 national SDGA 1 county Migori GBV policy **Source:** Un Women reports  **Indicator 3.2.1B:** Number of advocacy initiatives by gender equality advocates demanding accountability for quality services for VAWG survivors with UN Women support **Targets:  Value:** 14 **Notes:** Covid-19: GVRC: 5+5 (2020). **Target Year:** 2020 **Value:** 20 **Notes:** 5 plus Covid-19: CREAW: 2021: 7 (4+3). FEMNET 2021: 5+ 3 (minimum). **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 5 **Year:** 2019 **Notes:** 1 GBV conference, 4 Gender Sector Working Group Meetings in 2019 **Source:** UN Women and partner reports  **Indicator 3.2.1C:** Number of recorded cases of physical, sexual or psychological violence against women and girls during the COVID-19 pandemic **Targets:  Value:** 2250 **Notes:** GVRC 50, HAK 2,200 **Target Year:** 2020 **Value:** 2500 **Notes:** HAK, GVRC,CREAW **Target Year:** 2021 **Value:** 670 **Notes:** This was a Covid response indicator added in 2020. While we no longer have covid related activities, we will still be tracking the number of recorded GBV cases. **Target Year:** 2022 **Baseline:  Value:** 1410 **Year:** 2020 **Notes:** HAK 1410 **Source:** Partner reports  **Indicator 3.2.1D:** Number of women and girls and healthcare workers that accessed specialized gender-based violence response services and/or interventions with UN women support during the COVID-19 crisis **Targets:  Value:** 6136 **Notes:** HAK 3400, CREAW 1500 (dignity kits) + 400 (accessing shelters and resque centres), GVRC 750 (dignity kits), RWPL 86 **Target Year:** 2020 **Value:** 1500 **Notes:** Kenya Medical Women Association, HAK, GVRC **Target Year:** 2021 **Value:** 1550 **Notes:** Access to comprehensive GBV services is still a relevant indicator in 2022. **Target Year:** 2022 **Baseline:  Value:** 1410 **Year:** 2020 **Notes:** HAK 1410 **Source:** Partner reports  **Indicator 3.2.1E:** Level of knowledge and understanding by health and justice actors (police, prosecution and judiciary) trained **Targets:  Value:** 600 **Notes:** 120 in the 4 Finland counties, 400 under Italy, 80-Canada and Ireland **Target Year:** 2022 **Baseline:  Value:** 120 **Year:** 2020 **Notes:** 120 duty bearers in total in 4 counties-Finland funded **Source:** Training evaluation reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) |
| **Output 3.2.2 Capacities to collect, analyse, present and utilize data on VAWG enhanced** | **Indicator 3.2.2A:** Existence of an interoperable repository of VAWG data with UN Women support **Targets:  Value:** Yes **Target Year:** 2022 **Value:** In progress; not yet **Target Year:** 2020 **Value:** In progress not yet **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Source:** UN Women and partner reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 0.00 (core)  443,000.00 (non-core) | 0.00 (core)  230,000.00 (non-core) | 0.00 (core)  230,000.00 (non-core) | 0.00 (core)  460,000.00 (non-core) | 0.00 (core)  1,363,000.00 (non-core) |
| **Total Resources for outcome 3.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) |
| **Total Resources for impact area 3** | | | 0.00 (core)  443,000.00 (non-core) | 0.00 (core)  230,000.00 (non-core) | 0.00 (core)  230,000.00 (non-core) | 0.00 (core)  460,000.00 (non-core) | 0.00 (core)  1,363,000.00 (non-core) |
| **Impact4 Kenya implements more commitments on women, peace and security, and more gender equality advocates influence peace and security, disaster risk reduction and recovery processes** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Outcome 1.3: People in Kenya live in a secure, peaceful, inclusive and cohesive society Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 4.1 Women's and girls' participation in conflict prevention and peace and security processes increased  Related SP Outcome/Output:**   **Indicator 4.1C:** Number of women influencing peace and security processes at national and county level **Targets:  Value:** WPS: 1400 and DRR 610 women **Target Year:** 2022 **Value:** 635 **Notes:** Covid-19: HAWENKA: 2020: 35. WWFP: 2020: 500. RWPL: 100 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Baseline:  Value:** WPS: 1400 and DRR 610 women **Year:** 2020 **Source:** UN Women and partner reports | **Output 4.1.1 Capacities to develop and implement the gender responsive policies and frameworks on peace and security, P/CVE and DRR strengthened** | **Indicator 4.1.1A:** Number of gender responsive policies, strategies and frameworks on WPS, P/CVE and disaster risk reduction with UN Women support **Targets:  Value:** 7 **Notes:** 2 National on WPS, 2 Counties on WPS, 3 Counnties on DRR    In total18 (5 national on WPS, 5 Counties on WPS + 8 Counties on DRR) - KNAP II - Integrate KNAP II in 5 Counties  - Police - Youth Peace and Security Action Plan on UNSCR 2250 - Election Contingency Strategy  - Uwiano Platform for Peace Strategy  - 8 County DRR policies, strategies and frameworks **Target Year:** 2022 **Value:** 7 **Notes:** 2 National on WPS, 2 Counties on WPS, 3 Counties on DRR **Target Year:** 2021 **Value:** 5 (1 national 2+2 counties) **Notes:** 1 National on WPS (KNAP II), 2 Counties on WPS (Kwale, Marsabit), 2 Counties (Samburu, Narok) on DRR **Target Year:** 2020 **Baseline:  Value:** 11 **Year:** 2020 **Notes:** 11 policies, strategies and frameworks  -Kenya National Action Plan on UNSCR 1325  - Ministry of Defence Gender Policy  -IPSTC Gender Policy  -National Strategy on PVE  - Kenya National Peacebuilding Policy - National DRM Policy  - Gender Mainstreaming Guidelines on Sendai Framework  - NDMA Gender Mainstreaming Guidelines  - Kenya National Action Plan on DRR -DRR Turkana County Policy  - DRR Baringo County Policy **Source:** UN Women and partner reports  **Indicator 4.1.1B:** Number of advocacy intiatives by peace builders to advance WPS agenda with UN Women support **Targets:  Value:** 1 **Notes:** In total 3 over the years **Target Year:** 2022 **Value:** 1 **Target Year:** 2021 **Value:** 23 **Notes:** AWCFS: 2020: 3. HAWENKA: 2020: 4. HAWENKA: 2020: 5 +6. RWPL: 2020: 5. WWFP: **Target Year:** 2020 **Baseline:  Value:** 4 **Year:** 2019 **Source:** UN Women reports | 0.00 (core)  762,000.00 (non-core) | 0.00 (core)  713,177.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  783,828.00 (non-core) | 0.00 (core)  2,259,005.00 (non-core) |
| **Output 4.1.2 Access to DRR and humanitarian services by women and girls increased** | **Indicator 4.1.2A:** Proportion of women and girls accessing timely DRR and humanitarian services with UN Women support **Targets:  Value:** 50% **Notes:** 50% of 500, which is 250 individuals **Target Year:** 2020 **Value:** 50% **Notes:** 50% of 500 which is 250 individuals **Target Year:** 2021 **Value:** 50% **Notes:** 50% of 500 which is 250 individuals.  In total 50% of 1500 which is 750 individuals **Target Year:** 2022 **Baseline:  Value:** 610 **Year:** 2019 **Source:** UN Women and partner reports | 0.00 (core)  430,000.00 (non-core) | 0.00 (core)  563,177.00 (non-core) | 0.00 (core)  509,469.00 (non-core) | 0.00 (core)  1,894,262.00 (non-core) | 0.00 (core)  3,396,908.00 (non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | | | 0.00 (core)  1,192,000.00 (non-core) | 0.00 (core)  1,276,354.00 (non-core) | 0.00 (core)  509,469.00 (non-core) | 0.00 (core)  2,678,090.00 (non-core) | 0.00 (core)  5,655,913.00 (non-core) |
| **Total Resources for impact area 4** | | | 0.00 (core)  1,192,000.00 (non-core) | 0.00 (core)  1,276,354.00 (non-core) | 0.00 (core)  509,469.00 (non-core) | 0.00 (core)  2,678,090.00 (non-core) | 0.00 (core)  5,655,913.00 (non-core) |
| **Impact2 More women in Kenya have increased access to and control of productive resources and market opportunities** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Outcome 3.1: By 2022, productivity in services sectors, agriculture, manufacturing, extractives, blue economy and their value chains increased.  Outcome 3.2: By 2022, marginalized vulnerable groups and regions in Kenya have increased access to decent jobs, income and entrepreneurship opportunities Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 2.1 Productivity of women in the agricultural value-chain increased  Related SP Outcome/Output:**   **Indicator 2.1B:** Volume (USD) in sales  KOICA: (Agricultural production of beneficiaries (1 bags/acre - > 9 bags/acre), This has been changed from tonnes/Ha to bags/acre and expressed in Kgs, where a bag weighs 90 Kgs (Main three cereals crops captured here for others check on report body) **Targets:  Value:** 500 **Notes:** Milestone 2019: 100 Women  Milestone 2020: 200 Women  Milestone 2021: 200 Women **Target Year:** 2022 **Value:** 9 bags/ acre or 2 tons/Ha **Notes:** 9 bags/ acre or 2 tons/Ha **Target Year:** 2023 **Baseline:  Value:** Maize (5.3 bags/acre); Beans (1.5 bags/acre); Sorghum (1.7 bags/acres) **Year:** 2021 **Note:** KOICA: Maize (5.3 bags/acre); Beans (1.5 bags/acre); Sorghum (1.7 bags/acres) **Source:** UN Women Monitoring Data | **Output 2.1.1 Capacities of national and county institutions to develop and implement gender responsive CSA policies strengthened** | **Indicator 2.1.1A:** Number of counties that have integrated gender responsive CSA into their agricultural strategies **Targets:  Value:** 1 **Notes:** In total 4 from over the years **Target Year:** 2022 **Value:** 1 **Target Year:** 2020 **Value:** 2 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women reports | 0.00 (core)  110,000.00 (non-core) | 0.00 (core)  80,000.00 (non-core) | 0.00 (core)  80,000.00 (non-core) | 0.00 (core)  1,009,750.00 (non-core) | 0.00 (core)  1,279,750.00 (non-core) |
| **Output 2.1.2 Access to information, technology, finance and markets by women in the agricultural value chain increased** | **Indicator 2.1.2A:** Number of women farmers adopting CSA practices with UN Women support **Targets:  Value:** 200 **Target Year:** 2020 **Value:** 200 **Target Year:** 2021 **Value:** 200 **Notes:** Cumulative target 600 over the years **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women and partner reports | 0.00 (core)  140,000.00 (non-core) | 0.00 (core)  170,000.00 (non-core) | 0.00 (core)  120,000.00 (non-core) | 0.00 (core)  1,109,750.00 (non-core) | 0.00 (core)  1,539,750.00 (non-core) |
| **Outcome 2.2 Access by women entrepreneurs to existing and emerging markets/procurement opportunities increased  Related SP Outcome/Output:**   **Indicator 2.2A:** Value (USD) of procurement contracts awarded to women and young women **Targets:  Value:** TBC: baseline **Notes:** TBC: baseline survey **Target Year:** 2022 **Value:** Women is $ 161,100; Youth is $ 114,728; PWDs is $ 18,934 **Notes:** Women is $ 161,100; Youth is $ 114,728; PWDs is $ 18,934 **Target Year:** 2022 **Baseline:  Value:** Women is $ 151,981; Youth is $ 108,234; PWDs is $ 17,862 **Year:** 2021 **Note:** Women is $ 151,981; Youth is $ 108,234; PWDs is $ 17,862 **Source:** UN Women and partner reports | **Output 2.2.1 Capacities of women enterpreneurs as suppliers strengthened** | **Indicator 2.2.1A:** Number of women enterpreneurs qualified on preferred vendor lists **Targets:  Value:** 75 **Notes:** Cumulative **Target Year:** 2022 **Value:** 30 **Notes:** Cumulative **Target Year:** 2020 **Value:** 50 **Notes:** Cumulative **Target Year:** 2021 **Baseline:  Value:** 24 **Year:** 2019 **Source:** UN Women and partner reports  **Indicator 2.2.1B:** Number of women with enhanced economic resilience during and after Covid-19 supported by UN Women **Targets:  Value:** 560 **Notes:** 141 CREAW, GROOTS 20 + 200, KAWBO 189, UWEZA 10. **Target Year:** 2020 **Value:** 1257 **Notes:** ENA 1000, KABWO 189, UWEZA 68 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Partner reports  **Indicator 2.2.1C:** Number of women and girls who benefit from COVID 19 prevention initiatives implemented with support from UN Women **Targets:  Value:** 29,400 **Notes:** GROOTS 20,000 (masks), 2000 women at minimum (1000 hand washing stations), KABWO 3,400 (masks), UWEZA 4000 (masks) **Target Year:** 2021 **Value:** 29,400 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Partner reports  **Indicator 2.2.1D:** Number of advocacy initiatives on women's enhanced economic resilience associated with response to COVID 19 effects on women businesses with support from UN Women **Targets:  Value:** 30 **Notes:** KABWO 30 **Target Year:** 2021 **Value:** 30 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Source:** KABWO reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  120,000.00 (non-core) | 0.00 (core)  120,000.00 (non-core) |
| **Output 2.2.2 Capacities of selected institutions to implement, monitor and report on women's access to procurement opportunities strengthened** | **Indicator 2.2.2A:** Number of institutions complying with AGPO, WEPs and affirmative procument policies **Targets:  Value:** 10 **Notes:** 50 over the years **Target Year:** 2022 **Value:** 20 **Target Year:** 2020 **Value:** 20 **Target Year:** 2021 **Baseline:  Value:** 5 **Year:** 2019 **Source:** UN Women and partner reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  145,000.00 (non-core) | 0.00 (core)  145,000.00 (non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | | | 0.00 (core)  250,000.00 (non-core) | 0.00 (core)  250,000.00 (non-core) | 0.00 (core)  200,000.00 (non-core) | 0.00 (core)  2,119,500.00 (non-core) | 0.00 (core)  2,819,500.00 (non-core) |
| **Total Resources for outcome 2.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  265,000.00 (non-core) | 0.00 (core)  265,000.00 (non-core) |
| **Total Resources for impact area 2** | | | 0.00 (core)  250,000.00 (non-core) | 0.00 (core)  250,000.00 (non-core) | 0.00 (core)  200,000.00 (non-core) | 0.00 (core)  2,384,500.00 (non-core) | 0.00 (core)  3,084,500.00 (non-core) |