

UN Women Strategic Note 2018-2022

**UN WOMEN Kyrgyzstan COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact3 All women and girls live a life free from all forms of violence** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Outcome 2: By 2022, institutions at all levels are more accountable and inclusive ensuring justice, human rights, gender equality and sustainable peace for all Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 3.1 Women and men, especially youth, value social norms supporting gender equality and women’s empowerment at individual and community levels  Related SP Outcome/Output:**   **Indicator 3.1A:** Proportion of women and men, who believe that in certain cases marriage of minors may be excused **Targets:  Value:** 33 **Target Year:** 2022 **Value:** 50 **Target Year:** 2018 **Value:** 45 **Target Year:** 2019 **Value:** 40 **Target Year:** 2020 **Value:** 35 **Target Year:** 2021 **Value:** 35 **Target Year:** 2021 **Value:** 10 **Target Year:** 2022 **Value:** 33 **Target Year:** 2022 **Baseline:  Value:** 53 **Year:** 2016 **Note:** Women 54% Men 52% **Source:** Omnibus survey  **Indicator 3.1B:** Proportion of women and men who believe that men make better leaders than women **Targets:  Value:** 60 **Notes:** Omnibus survey **Target Year:** 2022 **Value:** 65 **Target Year:** 2021 **Value:** 70 **Target Year:** 2020 **Value:** 75 **Target Year:** 2019 **Value:** 77 **Target Year:** 2018 **Value:** 60 **Target Year:** 2022 **Value:** 60 **Target Year:** 2022 **Baseline:  Value:** 78,5 **Year:** 2016 **Note:** Women 74% Men 83% **Source:** NSC | **Output 3.1.1 Youth, women and men are able to transform gender power relations within families and communities** | **Indicator 3.1.1A:** Number of new “community champions” each year who command tools of the Gender Action Learning System and are able to train community members on using the tools as per the methodology **Targets:  Value:** 10 **Notes:** Additional champions are to be trained within expected GPI project **Target Year:** 2022 **Value:** 15 **Notes:** 15 champions **Target Year:** 2022 **Baseline:  Value:** 43 **Year:** 2017 **Source:** RP's narrative quarterly reports | 0.00 (core)  389,615.00 (non-core) | 10,000.00 (core)  266,297.00 (non-core) | 0.00 (core)  77,581.00 (non-core) | 0.00 (core)  256,940.00 (non-core) | 0.00 (core)  313,376.00 (non-core) | 10,000.00 (core)  1,303,809.00 (non-core) |
| **Output 3.1.2 Young women and men have increased understanding on gender equality and inclusion and how to promote respectful relationships and non-violent communication** | **Indicator 3.1.2A:** Number of training participants who have increased understanding on gender equality and inclusion and how to promote it **Targets:  Value:** 1000 **Notes:** 700 girls and 300 boys (number of people is not cumulative). **Target Year:** 2018 **Value:** 2000 **Notes:** 1400 girls and 600 boys (number of people is not cumulative). **Target Year:** 2019 **Value:** 2000 **Notes:** 1400 women and 600 men (number of people is not cumulative). **Target Year:** 2020 **Value:** 2000 **Notes:** 1400 women and 600 men (number of people is not cumulative). **Target Year:** 2021 **Value:** 1000 **Notes:** 700 girls and 300 boys (number of people is not cumulative). **Target Year:** 2022 **Value:** 30 **Target Year:** 2022 **Baseline:  Value:** 16000 **Year:** 2017 **Notes:** trained for SN period 2015-2017 **Source:** Training report  **Indicator 3.1.2B:** Percentage of trained participants on gender equality, social inclusion, peacebuilding who promote and advocate for these values at the individual and community levels **Targets:  Value:** 80% **Notes:** 70% girls and 30% boys **Target Year:** 2018 **Value:** 80% **Notes:** 70% girls and 30% boys **Target Year:** 2019 **Value:** 70% **Notes:** 70% women and girls and 30% men and boys **Target Year:** 2020 **Value:** 70% **Notes:** 70% women and girls and 30% men and boys **Target Year:** 2021 **Value:** 70% **Notes:** 70% women and girls and 30% men and boys **Target Year:** 2022 **Value:** 80 **Target Year:** 2022 **Baseline:  Value:** 80% **Year:** 2010 **Source:** Training and monitoring reports | 0.00 (core)  170,594.00 (non-core) | 0.00 (core)  249,080.00 (non-core) | 0.00 (core)  318,471.00 (non-core) | 0.00 (core)  183,539.00 (non-core) | 0.00 (core)  502,000.00 (non-core) | 0.00 (core)  1,423,684.00 (non-core) |
| **Output 3.1.4 Women Economic Empowerment: Rural women have enhanced leadership and participation in their communities and in rural institutions, and in shaping laws, policies and programmes** | **Indicator 3.1.4A:** Number of rural women participating in policy lobbying activities at local and central levels **Targets:  Value:** 80 **Target Year:** 2019 **Value:** 80 **Notes:** In the context of the JP-ARWEE programme phase that started in January 2020 **Target Year:** 2020 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 80 **Year:** 2019 **Notes:** In the context of the JP-ARWEE programme phase that started in January 2019 **Source:** Project monitoring  **Indicator 3.1.4C:** Number of women implemented of economic initiatives with support of the program **Targets:  Value:** 10 **Notes:** In the context of the JP-ARWEE programme phase that started in January 2020 **Target Year:** 2021 **Value:** 0 **Target Year:** 2022 **Value:** 30 **Target Year:** 2022 **Baseline:  Value:** 15 **Year:** 2019 **Notes:** 15 SGHs were supported with equipment for their economic initiatives. **Source:** Partner and Program reports | 0.00 (core)  23,787.00 (non-core) | 0.00 (core)  126,447.00 (non-core) | 0.00 (core)  224,346.00 (non-core) | 0.00 (core)  160,058.00 (non-core) | 0.00 (core)  136,000.00 (non-core) | 0.00 (core)  670,638.00 (non-core) |
| **Output 3.1.5 Women affected by COVID-19 crisis in target localities have improved access to livelihood opportunities, skills development and leadership** | **Indicator 3.1.5A:** Number of rural women from Kyrgyzstan who participate in training to increase knowledge and skills and engage to conduct small-scale initiatives **Targets:  Value:** 500 **Notes:** 500 women trained and 100 women out of them engaged in small-scale initiatives **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Partners' and project reports  **Indicator 3.1.5B:** Number of households who participate in community advocacy initiatives for redistribution of domestic work in Kyrgyzstan **Targets:  Value:** 120 households **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Partners' and project reports   **Indicator 3.1.5C:** Number of rural women activists who participated in dialogue with local governments for crisis preparedness planning **Targets:  Value:** 60 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Partners' and project reports   **Indicator 3.1.5D:** Number of gender responsive plans or policies on COVID-19 informed and supported through gender data, analysis and policy dialogues **Targets:  Value:** 1 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Project reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  199,000.00 (non-core) | 0.00 (core)  201,480.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  400,480.00 (non-core) |
| **Outcome 3.2 Service providers are better able to prevent VAWG and deliver essential services to victims and survivors of violence  Related SP Outcome/Output:**   **Indicator 3.2A:** The number of registered cases reported by victims of violence increased by 10% **Targets:  Value:** 10% **Target Year:** 2020 **Value:** 11 **Target Year:** 2021 **Value:** 10 **Target Year:** 2022 **Value:** 10 **Target Year:** 2022 **Value:** 10 **Target Year:** 2022 **Value:** 10 **Target Year:** 2022 **Value:** 10 **Target Year:** 2022 **Baseline:  Value:** 10 **Year:** 2020 **Source:**  NSC | **Output 3.2.2 Normative and policy frameworks are promoted and adapted in line with international standards, and institutions have the commitment, knowledge and capacities to legislate, plan, implement and monitor policies to address VAWG and femicide.** | **Indicator 3.2.2A:** Number of draft new and/or strengthened laws and/or policies on ending VAWG, including DV/IPV, and/or gender equality and non-discrimination developed that respond to the rights of women and girls, particularly those facing intersecting and multiple forms of discrimination, and are in line with international HR standards **Targets:  Value:** 1 **Target Year:** 2021 **Value:** 1 **Notes:** DV Law\_Amendment to the existing one within legal inventory process **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2021 **Notes:** NGES until 2030 and its NAP 2021-2023 **Source:** Ministry website (MLSD) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  5,500.00 (non-core) | 27,823.00 (core)  139,342.00 (non-core) | 27,823.00 (core)  144,842.00 (non-core) |
| **Output 3.2.3 Key officials at national and/or sub-national levels in all relevant institutions are better able to develop and deliver evidence-based programmes that prevent and respond to VAWG, including DV/IPV, especially for those groups of women and girls facing intersecting and multiple forms of discrimination, including in other sectors** | **Indicator 3.2.3A:** Number of key government officials trained on human rights and gender-equitable norms, attitudes and behaviours towards women and girls, including for those groups facing intersecting and multiple forms of discrimination **Targets:  Value:** 2 **Target Year:** 2021 **Value:** 5 **Target Year:** 2021 **Value:** 8 **Target Year:** 2022 **Baseline:  Value:** 5 **Year:** 2021 **Source:** Ministry/agencies reports  **Indicator 3.2.3B:** Number of institutions that develop strategies, plans and/or programmes to prevent and respond to VAWG, including DV/IPV, including for women and girls facing intersecting and multiple forms of discrimination **Targets:  Value:** 10 **Target Year:** 2021 **Value:** 2 **Target Year:** 2021 **Value:** 2 **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2021 **Source:** Ministries/agencies report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  64,484.00 (non-core) | 0.00 (core)  65,000.00 (non-core) | 0.00 (core)  129,484.00 (non-core) |
| **Output 3.2.4 Decision makers in relevant institutions and key informal decision makers are better able to advocate for implementation of legislation and policies on ending SGBV and for gender-equitable norms, attitudes and behaviours on women and girls’ rights** | **Indicator 3.2.4A:** Number of news outlets that develop standards on ethical and gender-sensitive reporting **Targets:  Value:** 10 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2021 **Source:** media sources   **Indicator 3.2.4B:** Number of people reached by campaigns challenging harmful social norms and gender stereotyping **Targets:  Value:** 0.01% **Target Year:** 2022 **Value:** 60 **Target Year:** 2021 **Value:** 60 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2021 **Source:** media, communication reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  60,000.00 (non-core) | 0.00 (core)  160,000.00 (non-core) |
| **Output 3.2.5 Relevant government authorities and women’s rights organisations at national and sub-national levels have better knowledge and capacity to deliver quality and coordinated essential services, including SRH services and access to justice, to women and girls’ survivors of violence, especially those facing multiple and intersecting forms of discrimination** | **Indicator 3.2.5A:** National guidelines or protocols that have been developed and/or strengthened in line with the guidance and tools for essential services **Targets:  Value:** 5 **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:**  Expert and project reports  **Indicator 3.2.5B:** Number of government service providers who have increased knowledge and capacities to deliver quality and coordinated essential services to women and girls’ survivors of violence **Targets:  Value:** 10 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Training reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  172,850.00 (non-core) | 0.00 (core)  90,000.00 (non-core) | 0.00 (core)  262,850.00 (non-core) |
| **Output 3.2.6 Women's rights groups and relevant CSOs, have increased opportunities and support to share knowledge, network, partner and jointly advocate for GEWE and ending SGBV, more specifically, with relevant stakeholders at sub-national, national, regional and global levels** | **Indicator 3.2.6A:** Number of women's rights groups, networks and relevant CSOs with strengthened capacities to network, partner and jointly advocate for progress on ending SGBV at local, national, regional and global levels **Targets:  Value:** 10 **Target Year:** 2021 **Value:** 10 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Experts reports   **Indicator 3.2.6B:** Number of supported women's right groups and relevant CSOs using the appropriate accountability mechanisms for advocacy **Targets:  Value:** 10 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2021 **Source:** CSO/Experts reports   **Indicator 3.2.6C:** Number of women’s organizations with increased capacities to respond to and mitigate the pandemic, fight against COVID-19 related gender-based violence, racism, xenophobia, stigma, and other forms of discrimination, prevent and remedy human rights abuses, and ensure longer-term recovery **Targets:  Value:** 5 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Project reports; lists of training participants, reports of grantees | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  204,900.00 (non-core) | 11,206.00 (core)  186,206.00 (non-core) | 11,206.00 (core)  391,106.00 (non-core) |
| **Output 3.2.7 Technical and financial support provided for implementation of Spotlight Initiative** | **Indicator 3.2.7A:** Timely and high quality technical and financial support to programme implementation provided **Targets:  Value:** yes **Target Year:** 2021 **Value:** yes **Target Year:** 2022 **Value:** yes **Target Year:** 2022 **Baseline:  Value:** yes **Year:** 2021 **Source:** financial reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 48,549.00 (core)  279,729.00 (non-core) | 0.00 (core)  38,365.00 (non-core) | 48,549.00 (core)  318,094.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 0.00 (core)  583,996.00 (non-core) | 10,000.00 (core)  641,824.00 (non-core) | 0.00 (core)  819,398.00 (non-core) | 0.00 (core)  802,017.00 (non-core) | 0.00 (core)  951,376.00 (non-core) | 10,000.00 (core)  3,798,611.00 (non-core) |
| **Total Resources for outcome 3.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 48,549.00 (core)  827,463.00 (non-core) | 39,029.00 (core)  578,913.00 (non-core) | 87,578.00 (core)  1,406,376.00 (non-core) |
| **Total Resources for impact area 3** | | | 0.00 (core)  583,996.00 (non-core) | 10,000.00 (core)  641,824.00 (non-core) | 0.00 (core)  819,398.00 (non-core) | 48,549.00 (core)  1,629,480.00 (non-core) | 39,029.00 (core)  1,530,289.00 (non-core) | 97,578.00 (core)  5,204,987.00 (non-core) |
| **Impact1 By 2022, institutions at all levels are more accountable and inclusive ensuring justice, human rights, gender equality and sustainable peace for all** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Outcome 2: By 2022, institutions at all levels are more accountable and inclusive ensuring justice, human rights, gender equality and sustainable peace for all Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 1.1 Key national institutions are implementing international obligations and national commitments on gender equality and women’s empowerment in policy and budgeting processes, and are accountable for results, including through the coordination mandate of the country office.  Related SP Outcome/Output:**   **Indicator 1.1A:** Number of public platforms organized where Government reports on progress made by the Government on GEWE commitments with UN Women’s support **Targets:  Value:** 1 **Target Year:** 2018 **Value:** 2 **Target Year:** 2019 **Value:** 1 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Value:** 2 **Target Year:** 2021 **Value:** 2 **Target Year:** 2021 **Value:** 10 **Notes:** Meetings on Gender Equality Strategy, WPS, and Statistics **Target Year:** 2022 **Value:** 10 **Notes:** Meetings Gender Equality Strategy, WPS, Statistics **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2020 **Note:** The Government hour in Parliament on GEWE **Source:** Monitoring reports  **Indicator 1.1B:** Percentage of activities in the National Action Plan on Gender Equality reported as 'in progress' **Targets:  Value:** 80 **Target Year:** 2020 **Value:** 80 **Target Year:** 2022 **Value:** 65 **Target Year:** 2018 **Value:** 80 **Target Year:** 2021 **Value:** 70 **Target Year:** 2019 **Value:** 65 **Target Year:** 2021 **Value:** 10 **Notes:** NAP on GES is in the process of approval by the end of 2021, therefore the rate **Target Year:** 2022 **Baseline:  Value:** 60 **Year:** 2017 **Source:** Ministry Of Labour and Social Develoment  **Indicator 1.1C:** Number of local governments and ministries who have introduced programme budget with allocations for gender budgets with UN Women's support **Targets:  Value:** 2 **Notes:** 1 Ministry and 1 LSG **Target Year:** 2018 **Value:** 3 **Notes:** 1 Ministry and 2 LSGs **Target Year:** 2019 **Value:** 4 **Notes:** 1 Ministry and 3 LSGs **Target Year:** 2020 **Value:** 4 **Notes:** 2 Ministries and 2 LSGs **Target Year:** 2021 **Value:** 5 **Notes:** 2 Ministries and 3 LSGs **Target Year:** 2022 **Value:** 3 **Target Year:** 2021 **Baseline:  Value:** 1 **Year:** 2017 **Note:** Ministry of Labour and Social Development **Source:** approved budgets of ministries and LSGs | **Output 1.1.1 Line ministries and local governments have the requisite knowledge and tools to integrate gender equality and women’s empowerment into sectorial policies and budgeting processes at national and local levels** | **Indicator 1.1.1A:** Number of senior management and decision-makers of state institutions reporting improved abilities on inclusive decision making and gender-responsive policies and practices **Targets:  Value:** 10 **Notes:** Number of people is not cumulative. **Target Year:** 2018 **Value:** 30 **Notes:** Number of people is not cumulative. **Target Year:** 2019 **Value:** 12 **Notes:** Number of people is not cumulative. **Target Year:** 2020 **Value:** 6 **Notes:** Number of people is not cumulative. **Target Year:** 2021 **Value:** 6 **Notes:** Number of people is not cumulative. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Training reports  **Indicator 1.1.1B:** Number of gender-responsive action plans developed through inclusive decision-making and consultations and endorsed by local self-governments with UN Women support **Targets:  Value:** 0 **Notes:** Number of action plans is not cumulative. **Target Year:** 2018 **Value:** 15 **Notes:** Number of action plans is not cumulative. **Target Year:** 2019 **Value:** 15 **Notes:** Number of action plans is not cumulative. **Target Year:** 2020 **Value:** 10 **Notes:** Number of action plans is not cumulative. **Target Year:** 2021 **Value:** 4 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Action plans and local self-government records | 0.00 (core)  108,000.00 (non-core) | 62,000.00 (core)  273,305.00 (non-core) | 100,000.00 (core)  265,000.00 (non-core) | 0.00 (core)  273,554.00 (non-core) | 0.00 (core)  364,250.00 (non-core) | 162,000.00 (core)  1,284,109.00 (non-core) |
| **Output 1.1.2 Civil society organizations, gender equality activists and media institutions, including those representing groups facing intersecting forms of discrimination, have necessary capacity for evidence-based advocacy and gender analysis, to inform planning and budgeting and to hold the state accountable** | **Indicator 1.1.2A:** Number of representatives of civil society organizations, including other groups facing intersecting forms of discrimination, gender equality activists and representatives of media institutions equipped with increased knowledge to effectively contribute to engendered national reform, planning processes and de-stigmatization efforts **Targets:  Value:** 39 **Notes:** Number of people is not cumulative. **Target Year:** 2018 **Value:** 46 **Notes:** Number of people is not cumulative. **Target Year:** 2019 **Value:** 36 **Notes:** Number of people is not cumulative. **Target Year:** 2020 **Value:** 36 **Notes:** Number of people is not cumulative. **Target Year:** 2021 **Value:** 36 **Notes:** Number of people is not cumulative. **Target Year:** 2022 **Value:** 15 **Notes:** 10 women and 5 men with HIV **Target Year:** 2020 **Baseline:  Value:** 72 **Year:** 2017 **Notes:** Over years 2015-2017 **Source:** Partners and project reports | 47,000.00 (core)  288,411.00 (non-core) | 21,500.00 (core)  354,641.00 (non-core) | 50,000.00 (core)  250,000.00 (non-core) | 0.00 (core)  153,612.00 (non-core) | 0.00 (core)  246,485.00 (non-core) | 118,500.00 (core)  1,293,149.00 (non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | | | 47,000.00 (core)  396,411.00 (non-core) | 83,500.00 (core)  627,946.00 (non-core) | 150,000.00 (core)  515,000.00 (non-core) | 0.00 (core)  427,166.00 (non-core) | 0.00 (core)  610,735.00 (non-core) | 280,500.00 (core)  2,577,258.00 (non-core) |
| **Total Resources for impact area 1** | | | 47,000.00 (core)  396,411.00 (non-core) | 83,500.00 (core)  627,946.00 (non-core) | 150,000.00 (core)  515,000.00 (non-core) | 0.00 (core)  427,166.00 (non-core) | 0.00 (core)  610,735.00 (non-core) | 280,500.00 (core)  2,577,258.00 (non-core) |