

UN Women Strategic Note 2019-2022

**UN WOMEN Lebanon COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |
| --- | --- |
| **Impact2Women have income security, decent work and economic authority** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: UNSF 2017-2020 Core priority (3): Lebanon reduces poverty and promotes sustainable development while addressing immediate needs in a human rights/gender-sensitive manner.Outcome 3.1: Productive sectors strengthened to promote inclusive growth and local development especially most disadvantaged areasOutcome 3.2: Improved equitable access to and delivery of quality social services, social protection and direct assistanceRelated national development priorities:** |
|  |  |  | **Year2019** | **Year2020** | **Year2021** | **Year2022** | **Total** |
| **Outcome 2.3National authorities, private sector and CSOs are engaged in and actively support gender equality and women’s economic empowerment and protectionRelated SP Outcome/Output:****Indicator 2.3A:** Percentage of women who completed the skill development training with UN Women improve their self-confidence**Targets: Value:** 85%**Target Year:** 2021**Baseline: Value:** N/A **Year:** 2021**Source:** UN Women**Indicator 2.3B:** Percentage of women who completed the skill development training with UN Women increase their skills and knowledge**Targets: Value:** 80%**Target Year:** 2021**Baseline: Value:** N/A **Year:** 2021**Source:** UN Women**Indicator 2.3E:** Percentage of women who completed the job placement programme with UN Women continue earning income after the end of the programme**Targets: Value:** 15%**Target Year:** 2022**Baseline: Value:** N/A **Year:** 2021**Source:** UN Women  | **Output 2.3.1Promote employment opportunities for women through direct service delivery and engagement with the private sector** | **Indicator 2.3.1A:** Number of women benefiting from skills training**Targets: Value:** 660**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women**Indicator 2.3.1G:** Number of women accessing the labor market**Targets: Value:** 360**Notes:** Cash-for-work**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women**Indicator 2.3.1H:** Number of female-led micro-enterprises supported through business development support**Targets: Value:** 20**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women**Indicator 2.3.1I:** Number of companies who sign the WEPs**Targets: Value:** 28**Target Year:** 2022**Baseline: Value:** 18 **Year:** 2021**Source:** UN Women**Indicator 2.3.1J:** Reduction in deployment of livelihood-based coping strategies**Targets: Value:** 20**Notes:** WEE monitoring tool**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women and partner**Indicator 2.3.1K:** % of women reporting increased confidence and skills to participate in paid work**Targets: Value:** 75 %**Target Year:** 2022**Baseline: Value:** N/A **Year:** 2021**Source:** WEE monitoring tool | 0.00(core)0.00(non-core) | 0.00(core)690,000.00(non-core) | 0.00(core)1,823,555.00(non-core) | 0.00(core)1,687,448.00(non-core) | 0.00(core)4,201,003.00(non-core) |
| **Output 2.3.4Lebanon's institutional framework and macro socio-economic environment promotes women's engagement in the economy** | **Indicator 2.3.4A:** Number of knowledge products produced**Targets: Value:** 4**Notes:** 4 additional in year 2022**Target Year:** 2022**Baseline: Value:** 3 **Year:** 2021**Source:** UN Women**Indicator 2.3.4B:** Number of MOA project Budgets reviewed and analyzed**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UNW**Indicator 2.3.4C:** Number of Consultations held with IMF, GoL, and other stakeholders to feed into the recovery plan**Targets: Value:** 5**Notes:** 4 additional in 2022**Target Year:** 2022**Baseline: Value:** 1 **Year:** 2021**Source:** UN Women**Indicator 2.3.4D:** Number of economic policies, legislations reviewed to remove barriers against women's economic participation**Targets: Value:** 3**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women | 0.00(core)0.00(non-core) | 0.00(core)625,000.00(non-core) | 0.00(core)504,437.00(non-core) | 0.00(core)262,785.00(non-core) | 0.00(core)1,392,222.00(non-core) |
| **Output 2.3.5Women and girls are supported with essential protection services, including to respond to increased needs as a result of the Covid-19 epidemic** | **Indicator 2.3.5A:** Number of women and girls survivors/at risk of violence provided with protection services and awareness (medical/legal/psychosocial)**Targets: Value:** 1000**Target Year:** 2022**Baseline: Value:** N/A **Year:** 2021**Source:** UN Women**Indicator 2.3.5D:** Number of women benefitting of in-kind support in the form of kits and PPEs**Targets: Value:** 360**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women**Indicator 2.3.5E:** Percentage of beneficiaries report feeling more protected**Targets: Value:** 75% **Target Year:** 2022**Baseline: Value:** N/A **Year:** 2020**Source:** UN Women's responsible Parties**Indicator 2.3.5F:** Percentage of beneficiaries who received GBV assistance report an improved sense of safety and well-being**Targets: Value:** 75**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women | 0.00(core)0.00(non-core) | 0.00(core)200,000.00(non-core) | 0.00(core)808,880.00(non-core) | 0.00(core)405,850.00(non-core) | 0.00(core)1,414,730.00(non-core) |
| **Total Resources for outcome 2.3 (core and non-core)** | 0.00(core)0.00(non-core) | 0.00(core)1,515,000.00(non-core) | 0.00(core)3,136,872.00(non-core) | 0.00(core)2,356,083.00(non-core) | 0.00(core)7,007,955.00(non-core) |
| **Total Resources for impact area 2** | 0.00(core)0.00(non-core) | 0.00(core)1,515,000.00(non-core) | 0.00(core)3,136,872.00(non-core) | 0.00(core)2,356,083.00(non-core) | 0.00(core)7,007,955.00(non-core) |
| **Impact4Women and girls contribute to and have greater influence in building sustainable peace and resilience and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action.** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: UNSF 2017-2020-Core priority (1): All People in Lebanon have Peace and Security; Outcome 1.2: Lebanese authorities are better equipped to maintain internal security accordance with human rights principles; Outcome 1.3: Lebanon has institutionalized mechanisms to promote peace and prevent, mitigate and manage conflict at municipal and local level.Core priority (2): Lebanon enjoys domestic stability and practices effective governance; Outcome 2.1: Government’s ability to improve the performance of institutions; Outcome 2.3: Institutional mechanisms and policies strengthened for improving the legal status of women and girls, eliminating gender-based violence and promoting gender equality. Core priority (3): Lebanon reduces poverty and promotes sustainable development while addressing immediate needs in a human rights/gender sensitive manner; Outcome 3.2: Improved equitable access to and delivery of quality social services social protection and basic assistance.Related national development priorities:** |
|  |  |  | **Year2019** | **Year2020** | **Year2021** | **Year2022** | **Total** |
| **Outcome 4.1The Women, Peace and Security Agenda is implemented through an enabling environment that supports women's participation in conflict preventionRelated SP Outcome/Output:****Indicator 4.1A:** Number of NAP indicators met to show progress**Targets: Value:** 75**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** NCLW**Indicator 4.1I:** Number of national mediation platforms formed**Targets: Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** CSOs | **Output 4.1.1National institutions - governmental and non governmental - are supported to ensure the implementation of the NAP on UNSCR 1325** | **Indicator 4.1.1A:** Percentage of NAP interventions implemented by national institutions through support from civil society and the UN**Targets: Value:** 45 %**Target Year:** 2022**Baseline: Value:** 10 % **Year:** 2020**Source:** National Gender Machinery**Indicator 4.1.1B:** Number of NAP indicators met to show progress**Targets: Value:** 25**Target Year:** 2021**Value:** 73**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** NCLW | 0.00(core)0.00(non-core) | 0.00(core)186.00(non-core) | 0.00(core)369,323.00(non-core) | 0.00(core)318,996.00(non-core) | 0.00(core)688,505.00(non-core) |
| **Output 4.1.2Women are capacitated to prevent and manage conflict through mediation skills.** | **Indicator 4.1.2A:** Number of local mediation networks formed and capacitated to resolve local disputes**Targets: Value:** 9**Target Year:** 2021**Value:** 11**Target Year:** 2022**Baseline: Value:** 3 **Year:** 2020**Source:** UN Women**Indicator 4.1.2B:** Number of local disputes resolved through engagement of women mediation networks**Targets: Value:** 12**Target Year:** 2021**Value:** 20**Target Year:** 2022**Baseline: Value:** 5 **Year:** 2021**Source:** UN Women**Indicator 4.1.2C:** Number of national mediation platforms formed**Targets: Value:** 1**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women**Indicator 4.1.2D:** Number of parties represented in parliament that agree to participate in dialogues**Targets: Value:** 11**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women | 0.00(core)0.00(non-core) | 0.00(core)221,370.00(non-core) | 0.00(core)827,908.00(non-core) | 0.00(core)770,023.00(non-core) | 0.00(core)1,819,301.00(non-core) |
| **Output 4.1.3Work to promote national reconciliation is supported through knowledge generation, dialogue and service delivery** | **Indicator 4.1.3A:** % of women engaged in inter-generational cross-community dialogue who report de-escalating at least one conflict incident in their community, as a result to their engagement in the project.**Targets: Value:** 50 %**Notes:** out of 80**Target Year:** 2022**Baseline: Value:** N/A **Year:** 2020**Source:** Project monitoring **Indicator 4.1.3B:** % of women facilitators who show increased capacity in dialogue and peacebuilding skills.**Targets: Value:** 85%**Notes:** 8 facilitators**Target Year:** 2022**Baseline: Value:** N/A **Year:** 2020**Source:** project monitoring**Indicator 4.1.3C:** % of women (80) engaged in inter-generational cross-community dialogue with increased knowledge on peace building and reconciliation.**Targets: Value:** 80 %**Target Year:** 2022**Baseline: Value:** N/A **Year:** 2020**Source:** project monitoring | 0.00(core)0.00(non-core) | 0.00(core)674,300.00(non-core) | 0.00(core)648,856.00(non-core) | 0.00(core)441,211.00(non-core) | 0.00(core)1,764,367.00(non-core) |
| **Output 4.1.4Women participate and shape Lebanon's crisis recovery** | **Indicator 4.1.4A:** Number of women rights organizations are supported to increase women's participation in the response**Targets: Value:** 10**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** UN Women**Indicator 4.1.4B:** Number of people directly benefiting from the response**Targets: Value:** 600**Target Year:** 2022**Baseline: Value:** N/A **Year:** 2021**Source:** porject monitoring/ partner reports**Indicator 4.1.4C:** Number of people indirectly benefiting from the response**Targets: Value:** 1500000**Target Year:** 2022**Baseline: Value:** N/A **Year:** 2021**Source:** project monitoring, partner reports | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 115,010.00(core)586,854.00(non-core) | 0.00(core)1,510,396.00(non-core) | 115,010.00(core)2,097,250.00(non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | 0.00(core)0.00(non-core) | 0.00(core)895,856.00(non-core) | 115,010.00(core)2,432,941.00(non-core) | 0.00(core)3,040,626.00(non-core) | 115,010.00(core)6,369,423.00(non-core) |
| **Total Resources for impact area 4** | 0.00(core)0.00(non-core) | 0.00(core)895,856.00(non-core) | 115,010.00(core)2,432,941.00(non-core) | 0.00(core)3,040,626.00(non-core) | 115,010.00(core)6,369,423.00(non-core) |
| **Impact6A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented**  | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: UNSF 2017-2020 Core priority (3): Lebanon reduces poverty and promotes sustainable development while addressing immediate needs in a human rights/gender-sensitive manner.Outcome 3.1: Productive sectors strengthened to promote inclusive growth and local development especially most disadvantaged areasOutcome 3.2: Improved equitable access to and delivery of quality social services, social protection and direct assistanceRelated national development priorities:** |
|  |  |  | **Year2019** | **Year2020** | **Year2021** | **Year2022** | **Total** |
| **Outcome 6.1Governments and civil society support progress on implementation of normative and policy frameworks, and work together to drive forward legislative change and reformRelated SP Outcome/Output:****Indicator 6.1A:** Number of laws, amendments, strategies, and policies on GEWE adopted and implemented**Targets: Value:** 3**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2018**Source:** NCLW, MoSWA and UN Women reports **Indicator 6.1B:** Number of laws, amendments, strategies and policies on national priorities that integrate a gender perspective**Targets: Value:** 3**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2018**Source:** NCLW, MoSWA and UN Women Reports**Indicator 6.1H:** Number of data sources and analyses produced for SDG indicators**Targets: Value:** 12**Notes:** 4 per year**Target Year:** 2021**Baseline: Value:** 2 **Year:** 2018**Source:** UN Women | **Output 6.1.1Feminist coalition and political parties are mobilized to call for the acceleration of women's rights** | **Indicator 6.1.1A:** Number of joined advocacy and programmatic initiatives conducted**Targets: Value:** 2**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women **Indicator 6.1.1B:** The feminist roadmap is endorsed by civil society.**Targets: Value:** yes**Target Year:** 2022**Baseline: Value:** no **Year:** 2021**Source:** UN Women**Indicator 6.1.1C:** Number of political parties receiving technical assistance and advancing their agendas to become more inclusive**Targets: Value:** 4**Target Year:** 2021**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women**Indicator 6.1.1D:** Number of women leaders, candidates and aspirants with strengthened capacities to engage in political life as leaders or run for political office**Targets: Value:** 100**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2021**Source:** UN Women**Indicator 6.1.1E:** Number of state and non-state actors engaged in dialogue**Targets: Value:** 30**Target Year:** 2022**Baseline: Value:** 0 **Year:** 2020**Source:** project monitoring**Indicator 6.1.1F:** Number of female student leaders engaged and supported to become potential future political leaders**Targets: Value:** 20**Target Year:** 2022**Baseline: Value:** 10 **Year:** 2021**Source:** Un Women project monitoring **Indicator 6.1.1G:** Number of reports produced on incidence of VAWP & VAWE in the months leading up to and after parliamentary elections**Targets: Value:** 6**Target Year:** 2022**Baseline: Value:** 1 **Year:** 2021**Source:** Project monitoring  | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 67,500.00(core)190,000.00(non-core) | 0.00(core)910,294.00(non-core) | 67,500.00(core)1,100,294.00(non-core) |
| **Output 6.1.2State entities and the feminist movement are supported and have capacity strengthened to progress on the implementation of legislative and policy reforms for GEWE and to challenge social norms** | **Indicator 6.1.2A:** Number of initiatives conducted by UN Women and CSOs to challenge gender social norms.**Targets: Value:** 4**Target Year:** 2022**Baseline: Value:** N/A **Year:** 2021**Source:** UN Women project monitoring | 0.00(core)0.00(non-core) | 118,000.00(core)50,000.00(non-core) | 0.00(core)623,818.00(non-core) | 0.00(core)91,082.00(non-core) | 118,000.00(core)764,900.00(non-core) |
| **Total Resources for outcome 6.1 (core and non-core)** | 0.00(core)0.00(non-core) | 118,000.00(core)50,000.00(non-core) | 67,500.00(core)813,818.00(non-core) | 0.00(core)1,001,376.00(non-core) | 185,500.00(core)1,865,194.00(non-core) |
| **Total Resources for impact area 6** | 0.00(core)0.00(non-core) | 118,000.00(core)50,000.00(non-core) | 67,500.00(core)813,818.00(non-core) | 0.00(core)1,001,376.00(non-core) | 185,500.00(core)1,865,194.00(non-core) |