

UN Women Strategic Note 2019-2022

**UN WOMEN Lebanon COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact2 Women have income security, decent work and economic authority** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNSF 2017-2020 Core priority (3): Lebanon reduces poverty and promotes sustainable development while addressing immediate needs in a human rights/gender-sensitive manner.  Outcome 3.1: Productive sectors strengthened to promote inclusive growth and local development especially most disadvantaged areas Outcome 3.2: Improved equitable access to and delivery of quality social services, social protection and direct assistance Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 2.3 National authorities, private sector and CSOs are engaged in and actively support gender equality and women’s economic empowerment and protection  Related SP Outcome/Output:**   **Indicator 2.3A:** Percentage of women who completed the skill development training with UN Women improve their self-confidence **Targets:  Value:** 85% **Target Year:** 2021 **Baseline:  Value:** N/A **Year:** 2021 **Source:** UN Women  **Indicator 2.3B:** Percentage of women who completed the skill development training with UN Women increase their skills and knowledge **Targets:  Value:** 80% **Target Year:** 2021 **Baseline:  Value:** N/A **Year:** 2021 **Source:** UN Women  **Indicator 2.3E:** Percentage of women who completed the job placement programme with UN Women continue earning income after the end of the programme **Targets:  Value:** 15% **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2021 **Source:** UN Women | **Output 2.3.1 Promote employment opportunities for women through direct service delivery and engagement with the private sector** | **Indicator 2.3.1A:** Number of women benefiting from skills training **Targets:  Value:** 660 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women  **Indicator 2.3.1G:** Number of women accessing the labor market **Targets:  Value:** 360 **Notes:** Cash-for-work **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women  **Indicator 2.3.1H:** Number of female-led micro-enterprises supported through business development support **Targets:  Value:** 20 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women  **Indicator 2.3.1I:** Number of companies who sign the WEPs **Targets:  Value:** 28 **Target Year:** 2022 **Baseline:  Value:** 18 **Year:** 2021 **Source:** UN Women  **Indicator 2.3.1J:** Reduction in deployment of livelihood-based coping strategies **Targets:  Value:** 20 **Notes:** WEE monitoring tool **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women and partner  **Indicator 2.3.1K:** % of women reporting increased confidence and skills to participate in paid work **Targets:  Value:** 75 % **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2021 **Source:** WEE monitoring tool | 0.00 (core)  0.00 (non-core) | 0.00 (core)  690,000.00 (non-core) | 0.00 (core)  1,823,555.00 (non-core) | 0.00 (core)  1,687,448.00 (non-core) | 0.00 (core)  4,201,003.00 (non-core) |
| **Output 2.3.4 Lebanon's institutional framework and macro socio-economic environment promotes women's engagement in the economy** | **Indicator 2.3.4A:** Number of knowledge products produced **Targets:  Value:** 4 **Notes:** 4 additional in year 2022 **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2021 **Source:** UN Women  **Indicator 2.3.4B:** Number of MOA project Budgets reviewed and analyzed **Targets:  Value:** 2 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UNW  **Indicator 2.3.4C:** Number of Consultations held with IMF, GoL, and other stakeholders to feed into the recovery plan **Targets:  Value:** 5 **Notes:** 4 additional in 2022 **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2021 **Source:** UN Women  **Indicator 2.3.4D:** Number of economic policies, legislations reviewed to remove barriers against women's economic participation **Targets:  Value:** 3 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women | 0.00 (core)  0.00 (non-core) | 0.00 (core)  625,000.00 (non-core) | 0.00 (core)  504,437.00 (non-core) | 0.00 (core)  262,785.00 (non-core) | 0.00 (core)  1,392,222.00 (non-core) |
| **Output 2.3.5 Women and girls are supported with essential protection services, including to respond to increased needs as a result of the Covid-19 epidemic** | **Indicator 2.3.5A:** Number of women and girls survivors/at risk of violence provided with protection services and awareness (medical/legal/psychosocial) **Targets:  Value:** 1000 **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2021 **Source:** UN Women  **Indicator 2.3.5D:** Number of women benefitting of in-kind support in the form of kits and PPEs **Targets:  Value:** 360 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women  **Indicator 2.3.5E:** Percentage of beneficiaries report feeling more protected **Targets:  Value:** 75%  **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2020 **Source:** UN Women's responsible Parties  **Indicator 2.3.5F:** Percentage of beneficiaries who received GBV assistance report an improved sense of safety and well-being **Targets:  Value:** 75 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women | 0.00 (core)  0.00 (non-core) | 0.00 (core)  200,000.00 (non-core) | 0.00 (core)  808,880.00 (non-core) | 0.00 (core)  405,850.00 (non-core) | 0.00 (core)  1,414,730.00 (non-core) |
| **Total Resources for outcome 2.3 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,515,000.00 (non-core) | 0.00 (core)  3,136,872.00 (non-core) | 0.00 (core)  2,356,083.00 (non-core) | 0.00 (core)  7,007,955.00 (non-core) |
| **Total Resources for impact area 2** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,515,000.00 (non-core) | 0.00 (core)  3,136,872.00 (non-core) | 0.00 (core)  2,356,083.00 (non-core) | 0.00 (core)  7,007,955.00 (non-core) |
| **Impact4 Women and girls contribute to and have greater influence in building sustainable peace and resilience and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNSF 2017-2020-Core priority (1): All People in Lebanon have Peace and Security; Outcome 1.2: Lebanese authorities are better equipped to maintain internal security accordance with human rights principles; Outcome 1.3: Lebanon has institutionalized mechanisms to promote peace and prevent, mitigate and manage conflict at municipal and local level. Core priority (2): Lebanon enjoys domestic stability and practices effective governance; Outcome 2.1: Government’s ability to improve the performance of institutions; Outcome 2.3: Institutional mechanisms and policies strengthened for improving the legal status of women and girls, eliminating gender-based violence and promoting gender equality. Core priority (3): Lebanon reduces poverty and promotes sustainable development while addressing immediate needs in a human rights/gender sensitive manner; Outcome 3.2: Improved equitable access to and delivery of quality social services social protection and basic assistance.   Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 4.1 The Women, Peace and Security Agenda is implemented through an enabling environment that supports women's participation in conflict prevention  Related SP Outcome/Output:**   **Indicator 4.1A:** Number of NAP indicators met to show progress **Targets:  Value:** 75 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** NCLW  **Indicator 4.1I:** Number of national mediation platforms formed **Targets:  Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** CSOs | **Output 4.1.1 National institutions - governmental and non governmental - are supported to ensure the implementation of the NAP on UNSCR 1325** | **Indicator 4.1.1A:** Percentage of NAP interventions implemented by national institutions through support from civil society and the UN **Targets:  Value:** 45 % **Target Year:** 2022 **Baseline:  Value:** 10 % **Year:** 2020 **Source:** National Gender Machinery  **Indicator 4.1.1B:** Number of NAP indicators met to show progress **Targets:  Value:** 25 **Target Year:** 2021 **Value:** 73 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** NCLW | 0.00 (core)  0.00 (non-core) | 0.00 (core)  186.00 (non-core) | 0.00 (core)  369,323.00 (non-core) | 0.00 (core)  318,996.00 (non-core) | 0.00 (core)  688,505.00 (non-core) |
| **Output 4.1.2 Women are capacitated to prevent and manage conflict through mediation skills.** | **Indicator 4.1.2A:** Number of local mediation networks formed and capacitated to resolve local disputes **Targets:  Value:** 9 **Target Year:** 2021 **Value:** 11 **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2020 **Source:** UN Women  **Indicator 4.1.2B:** Number of local disputes resolved through engagement of women mediation networks **Targets:  Value:** 12 **Target Year:** 2021 **Value:** 20 **Target Year:** 2022 **Baseline:  Value:** 5 **Year:** 2021 **Source:** UN Women  **Indicator 4.1.2C:** Number of national mediation platforms formed **Targets:  Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women  **Indicator 4.1.2D:** Number of parties represented in parliament that agree to participate in dialogues **Targets:  Value:** 11 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women | 0.00 (core)  0.00 (non-core) | 0.00 (core)  221,370.00 (non-core) | 0.00 (core)  827,908.00 (non-core) | 0.00 (core)  770,023.00 (non-core) | 0.00 (core)  1,819,301.00 (non-core) |
| **Output 4.1.3 Work to promote national reconciliation is supported through knowledge generation, dialogue and service delivery** | **Indicator 4.1.3A:** % of women engaged in inter-generational cross-community dialogue who report de-escalating at least one conflict incident in their community, as a result to their engagement in the project. **Targets:  Value:** 50 % **Notes:** out of 80 **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2020 **Source:** Project monitoring   **Indicator 4.1.3B:** % of women facilitators who show increased capacity in dialogue and peacebuilding skills. **Targets:  Value:** 85% **Notes:** 8 facilitators **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2020 **Source:** project monitoring  **Indicator 4.1.3C:** % of women (80) engaged in inter-generational cross-community dialogue with increased knowledge on peace building and reconciliation. **Targets:  Value:** 80 % **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2020 **Source:** project monitoring | 0.00 (core)  0.00 (non-core) | 0.00 (core)  674,300.00 (non-core) | 0.00 (core)  648,856.00 (non-core) | 0.00 (core)  441,211.00 (non-core) | 0.00 (core)  1,764,367.00 (non-core) |
| **Output 4.1.4 Women participate and shape Lebanon's crisis recovery** | **Indicator 4.1.4A:** Number of women rights organizations are supported to increase women's participation in the response **Targets:  Value:** 10 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women  **Indicator 4.1.4B:** Number of people directly benefiting from the response **Targets:  Value:** 600 **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2021 **Source:** porject monitoring/ partner reports  **Indicator 4.1.4C:** Number of people indirectly benefiting from the response **Targets:  Value:** 1500000 **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2021 **Source:** project monitoring, partner reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 115,010.00 (core)  586,854.00 (non-core) | 0.00 (core)  1,510,396.00 (non-core) | 115,010.00 (core)  2,097,250.00 (non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  895,856.00 (non-core) | 115,010.00 (core)  2,432,941.00 (non-core) | 0.00 (core)  3,040,626.00 (non-core) | 115,010.00 (core)  6,369,423.00 (non-core) |
| **Total Resources for impact area 4** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  895,856.00 (non-core) | 115,010.00 (core)  2,432,941.00 (non-core) | 0.00 (core)  3,040,626.00 (non-core) | 115,010.00 (core)  6,369,423.00 (non-core) |
| **Impact6 A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNSF 2017-2020 Core priority (3): Lebanon reduces poverty and promotes sustainable development while addressing immediate needs in a human rights/gender-sensitive manner. Outcome 3.1: Productive sectors strengthened to promote inclusive growth and local development especially most disadvantaged areas Outcome 3.2: Improved equitable access to and delivery of quality social services, social protection and direct assistance  Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 6.1 Governments and civil society support progress on implementation of normative and policy frameworks, and work together to drive forward legislative change and reform  Related SP Outcome/Output:**   **Indicator 6.1A:** Number of laws, amendments, strategies, and policies on GEWE adopted and implemented **Targets:  Value:** 3 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2018 **Source:** NCLW, MoSWA and UN Women reports   **Indicator 6.1B:** Number of laws, amendments, strategies and policies on national priorities that integrate a gender perspective **Targets:  Value:** 3 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2018 **Source:** NCLW, MoSWA and UN Women Reports  **Indicator 6.1H:** Number of data sources and analyses produced for SDG indicators **Targets:  Value:** 12 **Notes:** 4 per year **Target Year:** 2021 **Baseline:  Value:** 2 **Year:** 2018 **Source:** UN Women | **Output 6.1.1 Feminist coalition and political parties are mobilized to call for the acceleration of women's rights** | **Indicator 6.1.1A:** Number of joined advocacy and programmatic initiatives conducted **Targets:  Value:** 2 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women   **Indicator 6.1.1B:** The feminist roadmap is endorsed by civil society. **Targets:  Value:** yes **Target Year:** 2022 **Baseline:  Value:** no **Year:** 2021 **Source:** UN Women  **Indicator 6.1.1C:** Number of political parties receiving technical assistance and advancing their agendas to become more inclusive **Targets:  Value:** 4 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women  **Indicator 6.1.1D:** Number of women leaders, candidates and aspirants with strengthened capacities to engage in political life as leaders or run for political office **Targets:  Value:** 100 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women  **Indicator 6.1.1E:** Number of state and non-state actors engaged in dialogue **Targets:  Value:** 30 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** project monitoring  **Indicator 6.1.1F:** Number of female student leaders engaged and supported to become potential future political leaders **Targets:  Value:** 20 **Target Year:** 2022 **Baseline:  Value:** 10 **Year:** 2021 **Source:** Un Women project monitoring   **Indicator 6.1.1G:** Number of reports produced on incidence of VAWP & VAWE in the months leading up to and after parliamentary elections **Targets:  Value:** 6 **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2021 **Source:** Project monitoring | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 67,500.00 (core)  190,000.00 (non-core) | 0.00 (core)  910,294.00 (non-core) | 67,500.00 (core)  1,100,294.00 (non-core) |
| **Output 6.1.2 State entities and the feminist movement are supported and have capacity strengthened to progress on the implementation of legislative and policy reforms for GEWE and to challenge social norms** | **Indicator 6.1.2A:** Number of initiatives conducted by UN Women and CSOs to challenge gender social norms. **Targets:  Value:** 4 **Target Year:** 2022 **Baseline:  Value:** N/A **Year:** 2021 **Source:** UN Women project monitoring | 0.00 (core)  0.00 (non-core) | 118,000.00 (core)  50,000.00 (non-core) | 0.00 (core)  623,818.00 (non-core) | 0.00 (core)  91,082.00 (non-core) | 118,000.00 (core)  764,900.00 (non-core) |
| **Total Resources for outcome 6.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 118,000.00 (core)  50,000.00 (non-core) | 67,500.00 (core)  813,818.00 (non-core) | 0.00 (core)  1,001,376.00 (non-core) | 185,500.00 (core)  1,865,194.00 (non-core) |
| **Total Resources for impact area 6** | | | 0.00 (core)  0.00 (non-core) | 118,000.00 (core)  50,000.00 (non-core) | 67,500.00 (core)  813,818.00 (non-core) | 0.00 (core)  1,001,376.00 (non-core) | 185,500.00 (core)  1,865,194.00 (non-core) |