

UN Women Strategic Note 2020-2024

**UN WOMEN Liberia COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact6 The capacity of the GoL, gender equality advocates and other national stakeholders strengthened to assess progress and accelerate the implementation of continental and global normative and policy frameworks** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Crosscutting issues Related national development priorities:** | | | | | | |
|  |  |  | **Year 2020** | **Year 2021** | **Year 2022** | **Year 2023** | **Year 2024** | **Total** |
| **Outcome 6.1 The capacity of the GoL, gender equality advocates and other national stakeholders strengthened to assess progress and accelerate the implementation of continental and global normative and policy frameworks  Related SP Outcome/Output:**   **Indicator 6.1A:** Liberia submits high quality reports on international commitments (CEDAW,Beijing Declaration, & Platform for Action, SDGs) **Targets:  Value:** Yes **Notes:** CEDAW and Beijing report **Target Year:** 2019 **Value:** Yes **Target Year:** 2021 **Value:** Yes **Target Year:** 2022 **Value:** Yes **Target Year:** 2020 **Value:** Yes **Notes:** CEDAW and Beijing report **Target Year:** 2023 **Value:** Yes **Notes:** CEDAW and Beijing report **Target Year:** 2024 **Baseline:  Value:** Yes **Year:** 2014 **Note:** The last CEDAW report submitted in 2014 but due in 2013. The last Beijing report submitted in 2012 **Source:** Government reports, and UNWOMEN reports  **Indicator 6.1B:** Proportion of legal frameworks that addresses discrimination on the basis of sex, nationality, disability and compliance with international human rights standards. ((UNSDCF) **Targets:  Value:** 4 **Notes:** 2 laws amended (Refugee Act & Alien & Nationality Law) 2 bills passed (Domestic violence Act & Gender equity Bill); National Action Plan on Disability implemented **Target Year:** 2024 **Value:** 4 **Target Year:** 2021 **Value:** 4 **Target Year:** 2022 **Value:** 4 **Target Year:** 2023 **Baseline:  Value:** 4 **Year:** 2020 **Note:** Rape law, Alien & Nationality Law, Domestic Relations Law, Refugee Act, Human Trafficking Act, Inheritance Act; National Commission on Disability Act; Children’s Law; Penal Code 14.72,74; Domestic Violence Bill; Executive Order 92 on FGM; National Public Health Law. **Source:** CEDAW 2019 & 2024 Report, ICCPR, UPR Report 2020, One UN Annual Report, CRC 2019 | **Output 6.1.1 Targeted Ministries Agencies and Commissions have strengthened capacity to implement, monitor, report on CEDAW concluding observations, Commission on the Status of Women agreed conclusions and Beijing Platform for action** | **Indicator 6.1.1B:** Number of country reports prepared, presented and dissimenated by MoGCSP **Targets:  Value:** 1 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Value:** 3 **Notes:** Annual report **Target Year:** 2023 **Baseline:  Value:** 2 **Year:** 2019 **Notes:** (CEDAW report, Beijing Report) **Source:** UNW reports  **Indicator 6.1.1C:** Number of Ministries Agencies and Commissions that have strengthened technical capacities to monitor the implementation of CEDAW concluding observations, Commission on the Status of Women agreed conclusions **Targets:  Value:** 1 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Value:** 6 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** MOV: Training report to monitor the implementation of CEDAW concluding observations, Commission on the Status of Women agreed conclusions **Source:** CSW reports and presentation, minutes from working sessions | 0.00 (core)  38,750.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  238,750.00 (non-core) |
| **Output 6.1.2 CSOs, Networks and Youth Groups have strengthened capacity to advocate and monitor the implementation of CEDAW concluding observations, Universal Periodic review recommendations, Commission on the Status of Women agreed conclusions and Beijing Platform for action.** | **Indicator 6.1.2A:** Number of CSOs, Networks and Youth Groups with strengthened capacity to monitor the implementation of CEDAW, CSW agreed conclusions, UPR recommendations and Beijing Platform for Action concluding observations **Targets:  Value:** 1 **Target Year:** 2020 **Value:** 20 **Target Year:** 2021 **Value:** 20 **Notes:** annual reports **Target Year:** 2024 **Baseline:  Value:** 20 **Year:** 2021 **Notes:** annual reports **Source:** UNW reports  **Indicator 6.1.2B:** Number of shadow reports submitted to the CEDAW committee **Targets:  Value:** 1 **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Value:** 2 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** 6 **Year:** 2015 **Source:** UNW reports | 0.00 (core)  15,000.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  215,000.00 (non-core) |
| **Total Resources for outcome 6.1 (core and non-core)** | | | 0.00 (core)  53,750.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  453,750.00 (non-core) |
| **Total Resources for impact area 6** | | | 0.00 (core)  53,750.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  453,750.00 (non-core) |
| **Impact1 Women fully and equally participate in leadership and decision making and women and girls benefit from gender responsive governance.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Pillar IV Outcome 4.1 Related national development priorities:** | | | | | | |
|  |  |  | **Year 2020** | **Year 2021** | **Year 2022** | **Year 2023** | **Year 2024** | **Total** |
| **Outcome 1.2 By 2024, people in Liberia especially the vulnerable and disadvantaged, benefit from strengthened institutions that are more effective, accountable, transparent, inclusive and gender-responsive in the delivery of essential services at the national and sub-national levels.  Related SP Outcome/Output:**   **Indicator 1.2A:** Number of MACs with systems to track public allocations and expenditures for gender equality. **Targets:  Value:** 20 **Target Year:** 2024 **Value:** 5 **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Value:** 5 **Target Year:** 2023 **Value:** 5 **Target Year:** 2020 **Baseline:  Value:** 0 **Year:** 2019 **Note:** No systems in place but 2018 Gender budgeting statement by MoH was available **Source:** Liberia 2018/2019 FY budget MFDP | **Output 1.2.1 Output 4.1: Relevant government institutions draft, implement monitor and report on gender-responsive policies and plans at the national and sub-national levels.** | **Indicator 1.2.1A:** Number of relevant government institutions with the capacity to draft, implement, monitor and report on gender-responsive policies and plans at the national and subnational levels; **Targets:  Value:** 3 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Value:** 4 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 2 **Year:** 2019 **Source:** Development Planning Annual Financial Report- 2017 www.mfdp.gov.lr www.mgcsp.gov.lr   **Indicator 1.2.1B:** Number of relevant government institutions with gender-responsive policy and costed implementation plan **Targets:  Value:** 2 **Notes:** MOV: Consultant report and validated policies **Target Year:** 2020 **Value:** 2 **Target Year:** 2021 **Value:** 3 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 1 **Year:** 2019 **Source:** Ministry of Gender Children and Social Welfare Annual Report  **Indicator 1.2.1C:** Number of relevant government institutions with gender-responsive monitoring and reporting mechanism/tools to implement gender-responsive policies and plans **Targets:  Value:** 7 **Target Year:** 2021 **Value:** 4 **Notes:** MOV: Training report and attendance list **Target Year:** 2020 **Value:** 7 **Target Year:** 2021 **Value:** 6 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 1 **Year:** 2019 **Source:** Training report  **Indicator 1.2.1D:** Number of Government institutions with capacity to integrate GRB into the PFM system **Targets:  Value:** 1 **Target Year:** 2021 **Value:** 2 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 1 **Year:** 2020 **Source:** www.mfdp.gov.lr | 0.00 (core)  175,200.00 (non-core) | 0.00 (core)  387,140.00 (non-core) | 0.00 (core)  452,880.00 (non-core) | 0.00 (core)  460,560.00 (non-core) | 0.00 (core)  602,600.00 (non-core) | 0.00 (core)  2,078,380.00 (non-core) |
| **Output 1.2.3 Targeted members/committees of the National Legislature have strengthened capacity and skills in drafting Gender Responsive Laws and Policies and advocate for increased allocations to promote gender equality.** | **Indicator 1.2.3A:** Number of Legislative committees with strengthened capacities to draft gender-responsive laws and policies and advocate for gender-responsive budgets **Targets:  Value:** 2 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Value:** 3 **Target Year:** 2024 **Baseline:  Value:** 1 **Year:** 2019 **Source:** Capacity Building Report and Attendance   **Indicator 1.2.3B:** Legislators with GRB knowledge that would advocate for/promote increased allocations for gender equality **Targets:  Value:** 15 **Target Year:** 2020 **Value:** 25 **Target Year:** 2021 **Value:** 15 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 11 **Year:** 2019 **Source:** Consultancy Report and Training list  **Indicator 1.2.3C:** Number of gender equality initiatives developed and/or being implemented by parliamentary bodies (Legislative Parliamentary Committees/ Women’s Caucus/ Speaker of Parliament’s Office/Secretariat of the Parliament), with UN Women’s support **Targets:  Value:** 2 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Value:** 1 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 1 **Year:** 2019 **Source:** Training Report | 0.00 (core)  153,090.00 (non-core) | 0.00 (core)  104,750.00 (non-core) | 0.00 (core)  97,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  554,840.00 (non-core) |
| **Output 1.2.4 Women’s rights institutions and CSOs have strengthened capacities to better advocate for gender-responsive planning, programming, budgeting, and monitoring at the national and sub-national levels** | **Indicator 1.2.4A:** Number of women’s rights institutions with capacities to advocate for gender-responsive budgets with UN-Women's support **Targets:  Value:** 3 **Target Year:** 2020 **Value:** 5 **Target Year:** 2021 **Value:** 3 **Target Year:** 2023 **Value:** 12 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 1 **Year:** 2019 **Source:** Training Reports  **Indicator 1.2.4B:** Number of women’s rights advocates and other CSOs with the capacity to monitor annual allocation and expenditures to promote gender equality **Targets:  Value:** 3 **Target Year:** 2020 **Value:** 6 **Target Year:** 2021 **Value:** 8 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** 1 **Year:** 2019 **Source:** CSOs annual report  **Indicator 1.2.4C:** Number of gender budget watch dog reports developed by CSOs and women’s rights institutions **Targets:  Value:** 2 **Target Year:** 2020 **Value:** 4 **Target Year:** 2021 **Value:** 4 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 0 **Year:** 2019 **Source:** gender Budget Watchdog reports | 0.00 (core)  287,929.00 (non-core) | 0.00 (core)  190,000.00 (non-core) | 0.00 (core)  225,000.00 (non-core) | 0.00 (core)  300,000.00 (non-core) | 0.00 (core)  275,000.00 (non-core) | 0.00 (core)  1,277,929.00 (non-core) |
| **Output 1.2.5 Strengthened capacities of political institutions and electoral stakeholders to promote gender balance (The National Legislature, National Electoral Commission and political parties) to strengthen legal and policy frameworks to enable women’s leadership and participation** | **Indicator 1.2.5A:** Number of gender equality reforms developed and/or being implemented by electoral stakeholders with UN Women’s technical support **Targets:  Value:** 5 **Notes:** (targeting 2; the DVA, protocols on VAWiP/E) **Target Year:** 2020 **Value:** 6 **Notes:** 1 more on quotas for women/affirmative actions **Target Year:** 2021 **Value:** 2 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 3 **Year:** 2019 **Notes:** (LGA, Elections law, GRBP policy) **Source:** Gender equality reforms report  **Indicator 1.2.5B:** Number of political parties that have drafted rules, policies, and guidelines to promote women’s participation **Targets:  Value:** 5 **Target Year:** 2020 **Value:** 7 **Target Year:** 2021 **Value:** 12 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 2 **Year:** 2019 **Notes:** (UPP, LP) **Source:** Drafted rule and policies to promote women’s participation | 0.00 (core)  445,192.00 (non-core) | 0.00 (core)  68,000.00 (non-core) | 0.00 (core)  103,000.00 (non-core) | 0.00 (core)  113,000.00 (non-core) | 0.00 (core)  82,000.00 (non-core) | 0.00 (core)  811,192.00 (non-core) |
| **Output 1.2.6 Women leaders, including aspirants and elected women, in Liberia, have increased technical capacity to engage in leadership contests, apply leadership skills and mentor young women** | **Indicator 1.2.6A:** Number of women leaders, elected women, candidates and aspirants with strengthened capacities to engage in political life **Targets:  Value:** 125 **Target Year:** 2020 **Value:** 300 **Target Year:** 2021 **Value:** 75 **Notes:** Annual Report **Target Year:** 2022 **Value:** 75 **Target Year:** 2023 **Baseline:  Value:** 50 **Year:** 2019 **Source:** Training reports and attendance list  **Indicator 1.2.6B:** Number of Women leaders engaged in peer-to-peer exchanges and mentoring young women aspirants **Targets:  Value:** 40 **Target Year:** 2020 **Value:** 50 **Target Year:** 2021 **Value:** 75 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 30 **Year:** 2019 **Source:** Reports on peer-to-peer exchanges and mentoring | 0.00 (core)  328,803.00 (non-core) | 0.00 (core)  129,050.00 (non-core) | 0.00 (core)  175,550.00 (non-core) | 0.00 (core)  153,550.00 (non-core) | 0.00 (core)  108,550.00 (non-core) | 0.00 (core)  895,503.00 (non-core) |
| **Output 1.2.7 Communities and civil society have increased understanding of gender equality and women’s right to political participation through advocacy and social mobilization** | **Indicator 1.2.7A:** Number of CSO’s, women networks, the Media institutions, journalists, men, and boys that have increased understanding of gender equality and women’s right to political participation **Targets:  Value:** 356 **Notes:** 10 CSOs, 5 women networks, 15 Community radios (media institutions), 50 journalists and 200 men and boys. 280 plus 76 (baseline) gives the sum of 356 **Target Year:** 2020 **Value:** 30 **Target Year:** 2021 **Value:** 100 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** 76 **Year:** 2019 **Notes:** 10 CSOs, Women Networks TBD, 23 Media Institutions, Women Networks, TBD, 43 Journalists and Men and Boys TBD **Source:** Consultant training report and attendance list  **Indicator 1.2.7B:** Number of national dialogues and advocacy initiatives on women’s political participation supported. **Targets:  Value:** 20 **Target Year:** 2020 **Value:** 5 **Target Year:** 2021 **Value:** 5 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 6 **Year:** 2019 **Source:** Dialogues reports and attaendance list  **Indicator 1.2.7C:** Number of media companies and journalists with increased capacity on gender responsive media coverage **Targets:  Value:** 20 **Target Year:** 2020 **Value:** 10 **Target Year:** 2021 **Value:** 6 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 6 **Year:** 2019 **Source:**  Training reports and attendance list  **Indicator 1.2.7D:** Number of male political leaders publicly committed to taking action through different initiatives to promote women’s political participation. **Targets:  Value:** 200 **Target Year:** 2020 **Value:** 50 **Target Year:** 2021 **Value:** 45 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 0 **Year:** 2019 **Source:** Consultant training report and attendance list | 0.00 (core)  148,000.00 (non-core) | 0.00 (core)  61,634.00 (non-core) | 0.00 (core)  50,284.00 (non-core) | 0.00 (core)  97,234.00 (non-core) | 0.00 (core)  82,134.00 (non-core) | 0.00 (core)  439,286.00 (non-core) |
| **Outcome 1.3 By 2024, the UN system in Liberia coherently and systematically contributes to progress on gender equality and the empowerment of women and girls  Related SP Outcome/Output:** | **Output 1.3.1 UNCT in Liberia has enhanced capacities to deliver its coordiantion mandate coherently in line with UN principles.** |  | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 574,098.00 (core)  0.00 (non-core) | 574,098.00 (core)  0.00 (non-core) | 574,098.00 (core)  0.00 (non-core) | 1,722,294.00 (core)  0.00 (non-core) |
| **Total Resources for outcome 1.2 (core and non-core)** | | | 0.00 (core)  1,538,214.00 (non-core) | 0.00 (core)  940,574.00 (non-core) | 0.00 (core)  1,103,714.00 (non-core) | 0.00 (core)  1,224,344.00 (non-core) | 0.00 (core)  1,250,284.00 (non-core) | 0.00 (core)  6,057,130.00 (non-core) |
| **Total Resources for outcome 1.3 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 574,098.00 (core)  0.00 (non-core) | 574,098.00 (core)  0.00 (non-core) | 574,098.00 (core)  0.00 (non-core) | 1,722,294.00 (core)  0.00 (non-core) |
| **Total Resources for impact area 1** | | | 0.00 (core)  1,538,214.00 (non-core) | 0.00 (core)  940,574.00 (non-core) | 574,098.00 (core)  1,103,714.00 (non-core) | 574,098.00 (core)  1,224,344.00 (non-core) | 574,098.00 (core)  1,250,284.00 (non-core) | 1,722,294.00 (core)  6,057,130.00 (non-core) |
| **Impact2 Women in Liberia have income security, decent work, and economic autonomy.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Pillar II Outcome 2.2, 2.3 & 2.4, SN Outcome 2.2 Related national development priorities:** | | | | | | |
|  |  |  | **Year 2020** | **Year 2021** | **Year 2022** | **Year 2023** | **Year 2024** | **Total** |
| **Outcome 2.2 By 2024, Liberia has sustained, diversified and inclusive economic growth driven by investments in agriculture, food security and job creation and is resilient to climate change and natural disasters.  Related SP Outcome/Output:**   **Indicator 2.2A:** The proportion of Population below the national absolute poverty line, dis aggregated by sex, age, location (National, rural, and urban). **Targets:  Value:** 156.6 **Target Year:** 2024 **Value:** 50 **Target Year:** 2021 **Value:** 50 **Target Year:** 2022 **Value:** 50 **Target Year:** 2023 **Baseline:  Value:** 50 **Year:** 2020 **Source:** (HIES 2016) Reduction-PAPD (2018)  **Indicator 2.2B:** Employment rate disaggregated by Age, Sex, formality (formal and informal), activity (sector), vulnerability and Geographic location. **Targets:  Value:** (M)=(F)=58.3% **Target Year:** 2024 **Value:** 15 **Target Year:** 2021 **Value:** 20 **Target Year:** 2022 **Value:** 15 **Target Year:** 2023 **Value:** 20 **Target Year:** 2021 **Baseline:  Value:** (M)= 67.9%(2016)?? (F)= 91.1% (2016). **Year:** 2016 **Source:** HIES 2016 Frequency: 2-3 years | **Output 2.2.1 Rural women, including young women, rural communities and local authorities are aware of their rights and existing accountability mechanisms under the Land Rights Act for their equal access to, control and ownership of land for agricultural production.** | **Indicator 2.2.1A:** Number of rural women aware of their land rights for agricultural production **Targets:  Value:** 8051 **Target Year:** 2020 **Value:** 500 **Target Year:** 2021 **Value:** 750 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 6,051 **Year:** 2018 **Notes:** (JPRWEE Annual Reports 2016 - 2018) \_Baseline represents the total number of rural women UN Women has impacted in terms of awareness raising on land rights for agricultural production **Source:** Ministry of Agriculture bi-annual and annual reports, Data from agricultural surveys and censuses, O  **Indicator 2.2.1B:** Number of local authorities aware of existing accountability mechanisms under the Land Rights Act and are working to implement women’s land rights for agricultural production at local level **Targets:  Value:** 6 **Target Year:** 2020 **Value:** 1 **Notes:** in addition to already sensitized 6 local authorities UN Women will extend its efforts to capacitate on more local authority about the existing accountability mechanisms and etc. **Target Year:** 2021 **Value:** 15 **Notes:** Annual **Target Year:** 2024 **Baseline:  Value:** 4 **Year:** 2018 **Notes:** Baseline represents the total number local authorities UN Women has worked with in terms of them being aware of existing accountability mechanisms under the Land Rights Act and are working to implement women’s land rights for agricultural production at local level **Source:**  Liberia Land Authority progress reports, UN Women reports, Reports of local land committees, implem  **Indicator 2.2.1C:** Number of rural women aware of the processes in obtaining a land deed from the Liberia Land Authority **Targets:  Value:** 3801 **Target Year:** 2020 **Value:** 500 **Target Year:** 2021 **Value:** 500 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 2,801 **Year:** 2018 **Notes:** Baseline represents the total number of rural women UN Women has impacted in terms of awareness on the processes for obtaining a land deed from the Liberia Land Authority **Source:** Liberia Land Authority progress reports, UN Women reports, implementing partners report | 0.00 (core)  483,334.00 (non-core) | 0.00 (core)  284,000.00 (non-core) | 0.00 (core)  127,000.00 (non-core) | 0.00 (core)  2,000.00 (non-core) | 0.00 (core)  2,000.00 (non-core) | 0.00 (core)  898,334.00 (non-core) |
| **Output 2.2.2 Rural women have access to Second Chance Education, vocational skills, finance and are better organized in strong cooperatives around agricultural value chains.** | **Indicator 2.2.2A:** Number of rural women organized into cooperatives around agricultural value chains **Targets:  Value:** 1950 **Target Year:** 2020 **Value:** 500 **Target Year:** 2021 **Value:** 500 **Notes:** Annual Report **Target Year:** 2024 **Value:** 5 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 1,575 **Year:** 2018 **Notes:** Baseline represents the total number of rural women organized into cooperatives around agricultural value chains with support from UN Women **Source:** Ministry of Agriculture bi-annual and annual reports, implementing partners report     **Indicator 2.2.2B:** Number of rural women cooperatives accessing credit, other financial and business development services **Targets:  Value:** 31 **Target Year:** 2020 **Value:** 5 **Target Year:** 2021 **Value:** 5 **Notes:** Annual Report **Target Year:** 2022 **Value:** 5 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** 21 **Year:** 2018 **Notes:** \_Baseline represents the total number of rural women cooperatives accessing credit, other financial and business development services with support from UN Women **Source:** Orange Money reports from Orange Liberia, Reports of microcredit institutions, Ministry of Agricultu  **Indicator 2.2.2C:** Number of Village Savings and Loan Associations (VSLAs) providing access to sustainable credit to rural women **Targets:  Value:** 340 **Target Year:** 2020 **Value:** 20 **Notes:** 20 additional VSLAs comprised of 500 women will be cooperated ro attain access to sustainable credit **Target Year:** 2021 **Value:** 20 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** 290 **Year:** 2018 **Notes:** Baseline represents the total number of fully functional VSLAs supported by UN Women in Liberia **Source:** MGCSP and MoA reports, UN Women and FAO reports, National APEX on VSLAs, Reports of microcredit inst | 0.00 (core)  635,993.00 (non-core) | 0.00 (core)  578,883.00 (non-core) | 0.00 (core)  464,787.00 (non-core) | 0.00 (core)  609,425.00 (non-core) | 0.00 (core)  604,898.00 (non-core) | 0.00 (core)  2,893,986.00 (non-core) |
| **Output 2.2.3 Women entrepreneurs, including young women, have increased access to markets for their products through digital literacy, financial and digital services (ICT) (e.g. Buy from Women, Orange Money)** | **Indicator 2.2.3A:** Number of women using the Buy from Women platform to connect women farmers to information, markets and finance. **Targets:  Value:** 500 **Target Year:** 2020 **Value:** 500 **Target Year:** 2021 **Value:** 500 **Notes:** Annual **Target Year:** 2024 **Baseline:  Value:** 0 **Year:** 2019 **Notes:** Baseline is currently zero as the platform has never been deployed for use in Liberia **Source:** UN Women reports, FAO reports, WFP reports, MoA and MGCSP reports, Orange Money reports,    **Indicator 2.2.3B:** Number of women reporting increased access to markets through the use of BuyFromWomen Platform. **Targets:  Value:** 50 **Target Year:** 2020 **Value:** 75 **Target Year:** 2021 **Value:** 150 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 0 **Year:** 2019 **Source:** UN Women reports, FAO reports, WFP reports, MoA and MGCSP reports, Orange Money reports,    **Indicator 2.2.3C:** Number of women using other online financial platforms (e.g. Orange Money) to engage in financial transactions **Targets:  Value:** 2253 **Target Year:** 2020 **Value:** 250 **Target Year:** 2021 **Value:** 250 **Notes:** Annual **Target Year:** 2024 **Baseline:  Value:** 1,753 **Year:** 2018 **Notes:** Baseline represents the total number of women using other online financial platforms (e.g. Orange Money) to engage in financial transactions with support from UN Women **Source:** UN Women reports, FAO reports, WFP reports, Orange Money reports | 0.00 (core)  516,551.00 (non-core) | 0.00 (core)  351,000.00 (non-core) | 0.00 (core)  251,000.00 (non-core) | 0.00 (core)  297,000.00 (non-core) | 0.00 (core)  227,000.00 (non-core) | 0.00 (core)  1,642,551.00 (non-core) |
| **Output 2.2.4 Policy reform supported in the context of unpaid care work, decent work opportunities, and women’s access to social protection services as the most transformative way to promote their economic empowerment and the achievement of substantive gender equality** | **Indicator 2.2.4A:** Number of political consensus for macroeconomic policies reached that support employment creation for women **Targets:  Value:** 3 **Target Year:** 2021 **Value:** 2 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 1 **Year:** 2019 **Source:** TBD  **Indicator 2.2.4B:** Number of women organized in labour and product markets to improve the terms and conditions of employment and exchange **Targets:  Value:** 500 **Target Year:** 2021 **Value:** 11,243 **Target Year:** 2021 **Value:** 11243 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 10,743 **Year:** 2020 **Notes:** JP RWEE, UNW SN Project **Source:** TBD  **Indicator 2.2.4C:** The availability of a social protection floor that guarantees basic income security for women **Targets:  Value:** TBD **Target Year:** 2021 **Value:** Social protection floor available **Target Year:** 2021 **Value:** Social Protection Floor available **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** TBD **Year:** 2020 **Source:** TBD | 0.00 (core)  0.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  100,000.00 (non-core) |
| **Total Resources for outcome 2.2 (core and non-core)** | | | 0.00 (core)  1,635,878.00 (non-core) | 0.00 (core)  1,313,883.00 (non-core) | 0.00 (core)  842,787.00 (non-core) | 0.00 (core)  908,425.00 (non-core) | 0.00 (core)  833,898.00 (non-core) | 0.00 (core)  5,534,871.00 (non-core) |
| **Total Resources for impact area 2** | | | 0.00 (core)  1,635,878.00 (non-core) | 0.00 (core)  1,313,883.00 (non-core) | 0.00 (core)  842,787.00 (non-core) | 0.00 (core)  908,425.00 (non-core) | 0.00 (core)  833,898.00 (non-core) | 0.00 (core)  5,534,871.00 (non-core) |
| **Impact3 All women and girls live a life free from all forms of violence.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UN Pillar I Outcome 1.1 Related national development priorities:** | | | | | | |
|  |  |  | **Year 2020** | **Year 2021** | **Year 2022** | **Year 2023** | **Year 2024** | **Total** |
| **Outcome 3.2 By 2024, the most vulnerable and excluded groups have improved quality of life with rights-based, gender sensitive ,inclusive, equitable access and utilization of essential social services in an environment free of discrimination and violence including in humanitarian situations.  Related SP Outcome/Output:**   **Indicator 3.2A:** The proportion of ever-partnered women and girls aged 15 years and older subjected to physical, sexual or psychological violence by a current or former intimate partner in the previous 12 months, by form of violence and by age. **Targets:  Value:** 57 **Notes:** 15% Reduction of all forms of violence against of women aged 15-49 from the 5 targeted counties (Lofa, Nimba, Grand Gedeh, Montserrado and Grand Cape Mount) (Spotlight Initiative). **Target Year:** 2020 **Value:** 47 **Target Year:** 2021 **Value:** 37 **Target Year:** 2022 **Value:** 30 **Target Year:** 2023 **Value:** 42 **Target Year:** 2024 **Baseline:  Value:** 67 **Year:** 2019 **Note:** 44% (physical violence) 29% (violence in the last 12 months) 18% (sexual violence in the last 12 months) (Liberia DHS 2013) **Source:** DHS (Biennial) | **Output 3.2.1 OUTPUT 3.1: Harmful social norms and practices and other forms of GBV are eliminated through inclusive participation, awareness of the negative impacts and through community driven solutions at the national, county, community, household and individual levels** | **Indicator 3.2.1A:** Number of women, girls who participate in community capacity building programmes to promote gender equitable norms, attitudes and behaviours and understand the negative impacts of SGBV/HPs. **Targets:  Value:** 175 **Target Year:** 2020 **Value:** 200 **Target Year:** 2021 **Value:** 250 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 42 **Year:** 2018 **Source:**  Training reports and attendance sheets  **Indicator 3.2.1B:** Number of men and boys who participate in community capacity building programmes to promote gender equitable norms, attitudes and behaviours and understand the negative impacts of SGBV/HPs. **Targets:  Value:** 350 men and boys (175 men and 175 boys) **Target Year:** 2020 **Value:** 350 **Target Year:** 2020 **Value:** 350 **Target Year:** 2021 **Value:** 150 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 315 **Year:** 2018 **Source:**  Training reports and attendance sheets   **Indicator 3.2.1C:** Number of networks/platforms of men and boys developed/strengthened to promote gender equitable norms, attitudes and behaviours and understand the negative impacts of SGBV/HPs. **Targets:  Value:** 3 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Value:** 4 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 21 **Year:** 2019 **Source:** Projects reports of the establish community advocacy platform plans developed by networks  **Indicator 3.2.1D:** Number of Traditional and religious leaders, paramount chiefs and Elders, traditional Practitioners (including Zoes) with the capacity to prevent HPs, particularly FGM; **Targets:  Value:** 515 **Target Year:** 2021 **Value:** 500 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 440 **Year:** 2019 **Source:** Capacity Building Reports  **Indicator 3.2.1E:** Number of community-driven programmes/ solutions developed and implemented to prevent FGM. **Targets:  Value:** 5 **Target Year:** 2021 **Value:** 5 **Notes:** Annual Report **Target Year:** 2024 **Value:** 5 **Notes:** Annual Report **Target Year:** 2023 **Value:** 5 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2019 **Source:** CSO and implementing partners Reports | 0.00 (core)  495,318.00 (non-core) | 0.00 (core)  206,000.00 (non-core) | 0.00 (core)  306,000.00 (non-core) | 0.00 (core)  283,500.00 (non-core) | 0.00 (core)  176,000.00 (non-core) | 0.00 (core)  1,466,818.00 (non-core) |
| **Output 3.2.4 OUTPUT 6.1: A coherent, inclusive, and empowered CSO and Women’s movement framework to eliminate violence against women and girls is strengthened and operationalized at the national, subnational and community levels.** | **Indicator 3.2.4A:** Number of women's rights groups and relevant CSOs that have strengthened organizational capacities and support to design, implement, monitor and evaluate their own programmes on SGBV/HP **Targets:  Value:** 15 **Target Year:** 2020 **Value:** 15 **Target Year:** 2021 **Value:** 15 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 13 **Year:** 2019 **Notes:** (Girls for change Network; Association of Female Lawyers (AFELL), Women and children development secretariat; WONGOSOL; SEWODA-South Eastern Women Development Association; WIPNET; Women in Cross Border Trade); Liberia Feminist Forum; Sister 4 Sister Int'l; LIWEN; Her Voice Liberia; YWCA; Women Solidarity Int'l.) **Source:** Reports on the number of women rights groups and CSOs that have the capacity to design, implement, m  **Indicator 3.2.4B:** Number of womens’ rights groups and relevant CSOs with strengthened capacities to network, partner and jointly advocate for progress on ending SGBV and HPs; **Targets:  Value:** 15 **Target Year:** 2020 **Value:** 50 **Target Year:** 2021 **Value:** 50 **Notes:** Annual report **Target Year:** 2023 **Baseline:  Value:** 13 **Year:** 2019 **Notes:** (Girls for change Network; Association of Female Lawyers (AFELL), Women and children development secretariat; WONGOSOL; SEWODA-South Eastern Women Development Association; WIPNET; Women in Cross Border Trade); Liberia Feminist Forum; Sister 4 Sister Int'l; LIWEN; Her Voice Liberia; YWCA; Women Solidarity Int'l.) **Source:** Capacity assessment survey, directory of representatives of women rights groups and trained CSOs   **Indicator 3.2.4C:** Number of supported women’s right groups and relevant CSOs using the appropriate accountability mechanisms for advocacy on VAWG including SGBV/HPs. **Targets:  Value:** 15 **Target Year:** 2020 **Value:** 50 **Target Year:** 2021 **Value:** 50 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 13 **Year:** 2019 **Notes:** (Girls for change Network; Association of Female Lawyers (AFELL), Women and children development secretariat; WONGOSOL; SEWODA-South Eastern Women Development Association; WIPNET; Women in Cross Border Trade); Liberia Feminist Forum; Sister 4 Sister Int'l; LIWEN; Her Voice Liberia; YWCA; Women Solidarity Int'l.) **Source:** Reports on the level of participation of women rights groups on the use of accountability mechnasim | 228,920.00 (core)  1,579,347.00 (non-core) | 0.00 (core)  157,200.00 (non-core) | 0.00 (core)  187,200.00 (non-core) | 0.00 (core)  187,200.00 (non-core) | 0.00 (core)  187,200.00 (non-core) | 228,920.00 (core)  2,298,147.00 (non-core) |
| **Total Resources for outcome 3.2 (core and non-core)** | | | 228,920.00 (core)  2,074,665.00 (non-core) | 0.00 (core)  363,200.00 (non-core) | 0.00 (core)  493,200.00 (non-core) | 0.00 (core)  470,700.00 (non-core) | 0.00 (core)  363,200.00 (non-core) | 228,920.00 (core)  3,764,965.00 (non-core) |
| **Total Resources for impact area 3** | | | 228,920.00 (core)  2,074,665.00 (non-core) | 0.00 (core)  363,200.00 (non-core) | 0.00 (core)  493,200.00 (non-core) | 0.00 (core)  470,700.00 (non-core) | 0.00 (core)  363,200.00 (non-core) | 228,920.00 (core)  3,764,965.00 (non-core) |
| **Impact4 Women and girls contribute to, and have influence in, building sustainable peace and resilience and benefit equally from the prevention of conflicts and disasters, and from humanitarian action.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNDAF Pillar I Outcome 1.2 & 1.  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2020** | **Year 2021** | **Year 2022** | **Year 2023** | **Year 2024** | **Total** |
| **Outcome 4.2 By 2024, women, girls, men and boys in Liberia experience more sustained peace, inclusive and sustainable growth and development through strengthened formal and informal institutions providing access to effective and equitable justice and security services; promoting and protecting human rights; and strengthening social cohesion and reconciliation.  Related SP Outcome/Output:**   **Indicator 4.2A:** Percentage of cases of SGBV and other forms of violence reported to recognized authorities, as well as percentage of cases addressed by the same, disaggregated by types, sex, gender and age (UNSDCF) **Targets:  Value:** 10,000 SGBV cases by 2024 (2000 per annum) **Target Year:** 2020 **Value:** 2000 **Target Year:** 2024 **Value:** 2000 **Target Year:** 2021 **Value:** 2000 **Target Year:** 2022 **Value:** 2000 **Target Year:** 2023 **Baseline:  Value:** 1,664 SGBV case in 2018 (WAPCS’ 2018 Annual Report) **Year:** 2019 **Source:** WACPs annual report   **Indicator 4.2B:** Share of women (%) in leadership, elected or appointed (in cabinet positions, legislative, judiciary, private sector, community councils (UNSDCF) **Targets:  Value:** • LNP 30% Females • LIS 30% • AFL 10% • DEA 20% **Target Year:** 2024 **Value:** 10 **Target Year:** 2021 **Value:** 10 **Target Year:** 2022 **Value:** 10 **Target Year:** 2023 **Baseline:  Value:** • As of 2018, 29% women in the Liberia Immigration Service (Source: LIS) • As of 2018, 19% in Liberia National Police (LNP). (Source: LNP) • As of 2017, 3% women in the arm forces (Source: Gender and Security Sector National Taskforce) • As of 2018, 5.88% women held Ministerial positions (Source: IPU) • As of 2018,15% women in the Liberia Drug Enforcement Agency (LDEA); • Judiciary -7.7% • Corrections -21% • Prosecution-5.4% **Year:** 2019 **Source:** Justice & Security sector data survey;  MoJ & Judiciary Annual reports | **Output 4.2.1 Targeted line Ministries and institutions, local Government and CSOs have the capacities to allocate financial resources, coordinate, monitor and report on the implementation of the National Action Plan for Women Peace and Security.** | **Indicator 4.2.1A:** Number of targeted Line Ministries, Government Agencies, and local Governments have enhanced capacity to allocate resources **Targets:  Value:** 1 **Target Year:** 2020 **Value:** 2 **Target Year:** 2021 **Value:** 2 **Notes:** Annual report **Target Year:** 2024 **Value:** 8 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 0 **Year:** 2019 **Source:** Pre and post test from training  **Indicator 4.2.1B:** Number of targeted Government Agencies, CSOs and local Government with appropriate mechanisms and tools in place to monitor the implementation of the LNAP WPS. **Targets:  Value:** 1 LM-3 CSOs **Target Year:** 2020 **Value:** 4 **Target Year:** 2020 **Value:** 4 **Target Year:** 2021 **Value:** 4 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 0 **Year:** 2019 **Source:** Reports from consultant   **Indicator 4.2.1C:** Existence of an Annual Report on the implementation of the NAP WPS **Targets:  Value:** Yes **Target Year:** 2020 **Value:** yes **Target Year:** 2021 **Value:** 1 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** No **Year:** 2019 **Source:** Annual report | 0.00 (core)  988,496.00 (non-core) | 0.00 (core)  300,000.00 (non-core) | 29,310.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 29,310.00 (core)  1,588,496.00 (non-core) |
| **Output 4.2.2 Targeted Line Ministries, Security and Justice Institutions have the capacity to promote gender equality.** | **Indicator 4.2.2A:** Number of Gender Policies with costed actions plans drafted **Targets:  Value:** 3 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 1 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** 2 **Year:** 2019 **Source:** Consultant final report and approved gender policies  **Indicator 4.2.2B:** Number of targeted officers and civil servants with enhanced knowledge and skills on gender mainstreaming **Targets:  Value:** 91 **Target Year:** 2020 **Value:** 25 **Target Year:** 2021 **Value:** 50 **Notes:** Annual Report **Target Year:** 2022 **Baseline:  Value:** 41 **Year:** 2019 **Source:** Pre and post test and report from consultant | 0.00 (core)  775,016.00 (non-core) | 0.00 (core)  230,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  1,305,016.00 (non-core) |
| **Output 4.2.3 Targeted local Peace infrastructure and CSOs are strengthened to prevent and address conflict, sustain peace and enhance social cohesion in a more effective and inclusive manner** | **Indicator 4.2.3A:** Number of members from women’s organizations, and gender advocates with enhanced knowledge and skills on advocacy to promote social cohesion and gender responsive legal framework **Targets:  Value:** 40 **Target Year:** 2020 **Value:** 10 **Target Year:** 2021 **Value:** 10 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2019 **Source:** Pre and post test and report from consultant  **Indicator 4.2.3B:** Number of women and young women with strengthened skills and knowledge to participate in national and, conflict prevention, management and resolution infrastructure and community-based dialogues. **Targets:  Value:** 340 **Target Year:** 2020 **Value:** 50 **Target Year:** 2020 **Value:** 100 **Target Year:** 2021 **Value:** 100 **Notes:** Annual Report **Target Year:** 2024 **Baseline:  Value:** 280 **Year:** 2018 **Notes:** 280 women from 8 peace huts with enhanced knowledge on conflict prevention **Source:** Pre and post test and report from consultant  **Indicator 4.2.3C:** Number of members from targeted peace infrastructure with strengthened skills and knowledge on Gender mainstreaming and gender responsive conflict prevention, and mediation. **Targets:  Value:** 40 **Target Year:** 2020 **Value:** 40 **Target Year:** 2021 **Value:** 40 **Notes:** Annual Report **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2019 **Source:** Pre and post test and report from consultant | 0.00 (core)  478,233.00 (non-core) | 0.00 (core)  170,418.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  948,651.00 (non-core) |
| **Total Resources for outcome 4.2 (core and non-core)** | | | 0.00 (core)  2,241,745.00 (non-core) | 0.00 (core)  700,418.00 (non-core) | 29,310.00 (core)  300,000.00 (non-core) | 0.00 (core)  300,000.00 (non-core) | 0.00 (core)  300,000.00 (non-core) | 29,310.00 (core)  3,842,163.00 (non-core) |
| **Total Resources for impact area 4** | | | 0.00 (core)  2,241,745.00 (non-core) | 0.00 (core)  700,418.00 (non-core) | 29,310.00 (core)  300,000.00 (non-core) | 0.00 (core)  300,000.00 (non-core) | 0.00 (core)  300,000.00 (non-core) | 29,310.00 (core)  3,842,163.00 (non-core) |