

UN Women Strategic Note 2018-2022

**UN WOMEN Republic of Moldova COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact1 Women lead, participate in and benefit equally from governance systems** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Pillar 1 – Governance, Human Rights and Gender Equality Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 1.1 More women fully participate and lead in gender responsive governance processes and institutions, including in the security sector  Related SP Outcome/Output:**   **Indicator 1.1A:** % of implementation of National Strategy on Gender Equality in the areas of 1) promoting women in decision-making and 2) gender responsive budgeting, since 2017 **Targets:  Value:** 40 **Notes:** cumulative **Target Year:** 2018 **Value:** 60 **Notes:** cumulative **Target Year:** 2019 **Value:** 80 **Notes:** cumulative **Target Year:** 2020 **Value:** 80 **Notes:** cumulative **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Government reports, CEDAW reports, UN Women Reports | **Output 1.1.1 Public institutions have capacities to analyze and improve legislation, policies , regulations and budgets in order to fulfill gender equality commitments** | **Indicator 1.1.1A:** Number of national policies and regulations that advance gender equality and women’s participation, developed with UN Women support **Targets:  Value:** 1+ **Notes:** per year **Target Year:** 2018 **Value:** 1+ **Notes:** per year **Target Year:** 2019 **Value:** 2+ **Notes:** per year **Target Year:** 2020 **Value:** 2+ **Notes:** per year ( 6 new legislative amendments , policies and regulationas by 2022) **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 5 **Year:** 2017 **Source:** Parliament's web page, particip.gov, official gazette  **Indicator 1.1.1B:** Number of gender equality initiatives developed and/or being implemented by legislative bodies at central and local level with UN-Women’s support,per year **Targets:  Value:** 2+ **Target Year:** 2019 **Value:** 2+ **Target Year:** 2020 **Value:** 2+ **Notes:** by 2022 to reach 11 **Target Year:** 2021 **Value:** 2+ **Target Year:** 2018 **Value:** 2 **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2017 **Notes:** One Public Forum **Source:** UN Women's reports, Women Caucus articles  **Indicator 1.1.1C:** Number of civil servants (per year, per institution/ministry) with capacities to develop and implement gender responsive policies, plans and budgets (200 at local& district level/ 200 at national level;) **Targets:  Value:** 400+ **Target Year:** 2018 **Value:** 400+ **Target Year:** 2019 **Value:** 400+ **Target Year:** 2020 **Value:** 400+ **Notes:** by 2022 - 2000 persons **Target Year:** 2021 **Value:** 400 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** line ministries reports   **Indicator 1.1.1D:** Number of civil servants and general public with knowledge and skills about WPS agenda **Targets:  Value:** 150+ **Target Year:** 2021 **Value:** 150 **Target Year:** 2022 **Baseline:  Value:** 323 **Year:** 2020 **Source:** UN Women reports | 47,997.00 (core)  500,378.00 (non-core) | 44,997.00 (core)  594,021.00 (non-core) | 44,997.00 (core)  776,720.00 (non-core) | 0.00 (core)  505,527.00 (non-core) | 40,600.00 (core)  585,456.00 (non-core) | 178,591.00 (core)  2,962,102.00 (non-core) |
| **Output 1.1.2 A new generation of women from diverse groups have skills, knowledge and support networks for civic and political activism.** | **Indicator 1.1.2A:** Number of new women who acquire knowledge and tools to engage in political life (including Roma women and women with disabilities) **Targets:  Value:** 2700 **Notes:** by 2022 in total - 1500 new women with knowledge (100 women with disabilities, 100 Roma women) since 2017 (baseline) **Target Year:** 2022 **Value:** 300+ **Notes:** per year **Target Year:** 2018 **Value:** 300+ **Notes:** per year **Target Year:** 2019 **Value:** 300+ **Notes:** per year **Target Year:** 2020 **Value:** 300+ **Notes:** per year **Target Year:** 2021 **Value:** 300+ **Target Year:** 2021 **Baseline:  Value:** 1200 **Year:** 2015 **Notes:** UN Supported around 1200 women during 2010/2011 and 2014/2015 elections. (50 Roma/ 40 with disabilities) **Source:** training events report   **Indicator 1.1.2B:** Number of Organizations that received capacity development support and supporting women candidates and demanding women’s equal participation. **Targets:  Value:** 75 **Notes:** cumulative **Target Year:** 2022 **Value:** 15 **Target Year:** 2018 **Value:** 15+ **Target Year:** 2019 **Value:** 15+ **Target Year:** 2020 **Value:** 15+ **Target Year:** 2021 **Value:** 15 **Target Year:** 2022 **Baseline:  Value:** 10 **Year:** 2017 **Notes:** Over 10 organizations have been receiving capacity development support during 2014-2017 (7 political clubs established in 7 districts, 3 women’s organizations of 3 political parties, Romani Women and Girls Network, Gender Equality Platform consisting of 28 organizations) **Source:** UN Women's reports  **Indicator 1.1.2C:** Number of new advocacy products\* produced by women’s organizations/platforms with UN Women's support and shared with decision-makers through dialogue forums and other means **Targets:  Value:** 5 **Notes:** per year **Target Year:** 2018 **Value:** 5 + **Notes:** per year **Target Year:** 2019 **Value:** 5+ **Notes:** per year **Target Year:** 2020 **Value:** 5+ **Notes:** per year **Target Year:** 2021 **Value:** 25 **Notes:** in total for 5 year **Target Year:** 2022 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** UN Women's reports | 17,949.00 (core)  253,686.00 (non-core) | 18,300.00 (core)  94,123.00 (non-core) | 18,300.00 (core)  97,572.00 (non-core) | 0.00 (core)  90,000.00 (non-core) | 0.00 (core)  1,000.00 (non-core) | 54,549.00 (core)  536,381.00 (non-core) |
| **Output 1.1.3 Elected and appointed women have skills and knowledge to promote gender sensitive governance, in alliance with men** | **Indicator 1.1.3A:** Number of newly elected and appointed women at national and local level with strengthened capacities on gender sensitive governance since 2017. **Targets:  Value:** 1000 **Notes:** 1000 elected and appointed women will be covered by 2022, cumulative **Target Year:** 2022 **Value:** 200+ **Target Year:** 2018 **Value:** 200+ **Target Year:** 2019 **Value:** 200+ **Target Year:** 2020 **Value:** 200+ **Target Year:** 2021 **Value:** 194 **Target Year:** 2022 **Baseline:  Value:** 1000 **Year:** 2017 **Notes:** Over 1000 elected women at local level received capacity building with UN Women support during 2015-2017 **Source:** UN Women's reports | 9,600.00 (core)  33,067.00 (non-core) | 6,751.00 (core)  69,123.00 (non-core) | 7,500.00 (core)  79,572.00 (non-core) | 0.00 (core)  130,000.00 (non-core) | 0.00 (core)  321,025.00 (non-core) | 23,851.00 (core)  632,787.00 (non-core) |
| **Output 1.1.4 Local public authorities and local stakeholders have knowledge and skills to apply gender mainstreaming in elaboration of public policies for community development** | **Indicator 1.1.4A:** Share of local public authorities, from two districts, involved in capacity/ skills development events on gender mainstreaming **Targets:  Value:** 10% **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** project reports  **Indicator 1.1.4B:** Number of local CSOs, community groups working on advocacy for gender equality, supported by UN Women **Targets:  Value:** 8 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2020 **Source:** project reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  388,922.00 (non-core) | 0.00 (core)  783,683.00 (non-core) | 0.00 (core)  817,360.00 (non-core) | 0.00 (core)  1,989,965.00 (non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | | | 75,546.00 (core)  787,131.00 (non-core) | 70,048.00 (core)  757,267.00 (non-core) | 70,797.00 (core)  1,342,786.00 (non-core) | 0.00 (core)  1,509,210.00 (non-core) | 40,600.00 (core)  1,724,841.00 (non-core) | 256,991.00 (core)  6,121,235.00 (non-core) |
| **Total Resources for impact area 1** | | | 75,546.00 (core)  787,131.00 (non-core) | 70,048.00 (core)  757,267.00 (non-core) | 70,797.00 (core)  1,342,786.00 (non-core) | 0.00 (core)  1,509,210.00 (non-core) | 40,600.00 (core)  1,724,841.00 (non-core) | 256,991.00 (core)  6,121,235.00 (non-core) |
| **Impact2 Women have income security, decent work and economic autonomy** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Pillar 2 – Sustainable, Inclusive and Equitable Economic Growth  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 2.1 Parliament and Government adopt and implement legislation, policies, and services that address unpaid domestic and care work and improve income security and decent work for women.  Related SP Outcome/Output:**   **Indicator 2.1A:** Number of labor and social protection legislation, regulations and policies that address unpaid domestic and care work and increase women’s economic autonomy since 2017 **Targets:  Value:** 1 **Target Year:** 2018 **Value:** 1+ **Notes:** cumulative **Target Year:** 2019 **Value:** 1+ **Notes:** cumulative **Target Year:** 2020 **Value:** 1+ **Notes:** cumulative **Target Year:** 2021 **Value:** 1 **Target Year:** 2021 **Value:** 1 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Government Reports, CEDAW Report, UN Women reports | **Output 2.1.1 Parliament and Government have capacities to develop and implement laws, policies and services that positively impacts women’s income and decent employment and recognize, reduce and redistribute unpaid care work.** | **Indicator 2.1.1A:** Number of laws, regulations, policies, and services that enhance decent work for women and address unpaid care work, developed and/or upscale with UN Women support since 2017 **Targets:  Value:** 5 **Notes:** cumulative **Target Year:** 2022 **Value:** 1 **Target Year:** 2018 **Value:** 1+ **Target Year:** 2019 **Value:** 1+ **Target Year:** 2020 **Value:** 4 **Target Year:** 2021 **Baseline:  Value:** 1 (draft programme on women's entrepreneurship **Year:** 2017 **Source:** Government Legal Base (justice.lex.md) | 44,497.00 (core)  282,188.00 (non-core) | 49,997.00 (core)  272,403.00 (non-core) | 51,997.00 (core)  232,266.00 (non-core) | 48,997.00 (core)  569,604.00 (non-core) | 0.00 (core)  373,000.00 (non-core) | 195,488.00 (core)  1,729,461.00 (non-core) |
| **Output 2.1.2 Women, including those from excluded groups, have skills and knowledge to access economic opportunities.** | **Indicator 2.1.2A:** Number of women, ( including Roma women, with disabilities, leaving with HIV, survivor of violence, migrant women returnees) with acquired knowledge to access STEM and other income generating opportunities ( with UN Women’s support), since 2017 **Targets:  Value:** 1000 **Notes:** including at least 100 women from each of the group, cumulative **Target Year:** 2022 **Value:** 200 **Target Year:** 2018 **Value:** 400 **Target Year:** 2019 **Value:** 600 **Target Year:** 2020 **Value:** 800 **Target Year:** 2021 **Baseline:  Value:** 164 **Year:** 2017 **Notes:** 46.4% have witnessed or experienced domestic violence 64.3% Have/had close family members (parents, siblings, grandfathers) working abroad. **Source:** UN Women reports | 25,957.00 (core)  182,000.00 (non-core) | 20,957.00 (core)  172,500.00 (non-core) | 17,995.00 (core)  660,000.00 (non-core) | 21,457.00 (core)  600,000.00 (non-core) | 0.00 (core)  727,000.00 (non-core) | 86,366.00 (core)  2,341,500.00 (non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | | | 70,454.00 (core)  464,188.00 (non-core) | 70,954.00 (core)  444,903.00 (non-core) | 69,992.00 (core)  892,266.00 (non-core) | 70,454.00 (core)  1,169,604.00 (non-core) | 0.00 (core)  1,100,000.00 (non-core) | 281,854.00 (core)  4,070,961.00 (non-core) |
| **Total Resources for impact area 2** | | | 70,454.00 (core)  464,188.00 (non-core) | 70,954.00 (core)  444,903.00 (non-core) | 69,992.00 (core)  892,266.00 (non-core) | 70,454.00 (core)  1,169,604.00 (non-core) | 0.00 (core)  1,100,000.00 (non-core) | 281,854.00 (core)  4,070,961.00 (non-core) |
| **Impact3 all women and girls live free from all forms of violence** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Pillar 4 - Inclusive and Equitable Social Development, Pillar 1 – Governance, Human Rights and Gender Equality Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 3.1 Parliament and Government adopt and implement laws, policies and strategies to prevent violence against women and girls and deliver quality essential services  Related SP Outcome/Output:**   **Indicator 3.1A:** number of new laws, by-laws, regulations to combat violence against women and girls in line with CAHVIO, CEDAW, and UPR **Targets:  Value:** 1 **Target Year:** 2018 **Value:** 1+ **Target Year:** 2019 **Value:** 1+ **Target Year:** 2020 **Value:** 2+ **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2017 **Note:** Draft national comprehensive strategy /program **Source:** Government reports, CEDAW Reports, official gazette | **Output 3.1.1 Public institutions have capacities to apply international norms and standards in developing and implementing laws, policies and services towards eliminating VAW** | **Indicator 3.1.1A:** Number of guidelines, protocols, standard operating procedures on prevention and the provision of quality services for survivors, developed by the central authorities with support of UN Women in line with CEDAW, CAHVIO and UPR recommendations, since 2017 **Targets:  Value:** 1 **Target Year:** 2018 **Value:** 1+ **Target Year:** 2019 **Value:** 1+ **Target Year:** 2020 **Value:** 2+ **Target Year:** 2021 **Value:** 6 **Notes:** cumulative **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** national legislation base (justice.lex.md), UN Women reports  **Indicator 3.1.1B:** Number of individuals/service providers who are part of the multi-disciplinary teams with improved knowledge, PPE and skills on survivor-focused and coordinated response to cases of VAW **Targets:  Value:** 80+ **Target Year:** 2018 **Value:** 120+ **Target Year:** 2019 **Value:** 100+ **Target Year:** 2020 **Value:** 100+ **Target Year:** 2021 **Value:** 580 **Target Year:** 2022 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 80 **Year:** 2017 **Source:** UN Women reports | 45,997.00 (core)  269,144.00 (non-core) | 46,997.00 (core)  253,951.00 (non-core) | 0.00 (core)  258,435.00 (non-core) | 45,997.00 (core)  643,880.00 (non-core) | 70,400.00 (core)  484,335.00 (non-core) | 209,391.00 (core)  1,909,745.00 (non-core) |
| **Output 3.1.2 Target communities, institutions and CSOs, including in the field of education, have knowledge and tools to combat stereotypes and gender discrimination and advance favorable social norms that prevent VAWG.** | **Indicator 3.1.2A:** Number of institutions that have knowledge to apply innovative EVAW tools towards combating gender stereotypes and discrimination, since 2017 **Targets:  Value:** 10 **Notes:** 10 institutions out of which at least 5 are in the field of education **Target Year:** 2022 **Value:** 1 **Target Year:** 2018 **Value:** 2+ **Target Year:** 2019 **Value:** 2+ **Target Year:** 2020 **Value:** 2+ **Target Year:** 2021 **Value:** 3 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** UN Women Reports  **Indicator 3.1.2B:** Number of new communities with community based initiatives supported by UN Women to promote positive social norms, respectful relationships and gender equality **Targets:  Value:** 7 **Target Year:** 2018 **Value:** 8+ **Target Year:** 2019 **Value:** 9+ **Target Year:** 2020 **Value:** 9+ **Target Year:** 2021 **Value:** 40 **Target Year:** 2022 **Value:** 7 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** UN women report, RP s reports | 10,000.00 (core)  180,000.00 (non-core) | 11,000.00 (core)  85,000.00 (non-core) | 13,000.00 (core)  35,000.00 (non-core) | 13,000.00 (core)  0.00 (non-core) | 0.00 (core)  500,384.00 (non-core) | 47,000.00 (core)  800,384.00 (non-core) |
| **Output 3.1.3 Women and girls, especially from excluded groups, have knowledge and skills to exercise their rights to essential services** | **Indicator 3.1.3A:** Number of women,especially from the excluded groups, who have knowledge about their rights and are informed on available services with UN Women support, since 2017 **Targets:  Value:** 5000 **Notes:** at least 1000 persons per target district (in 5 target districts) and by 2022 to get to 5000 women. (to include at least 100 women of each of the following groups: Roma women, Women living with HIV, women with disabilities) **Target Year:** 2022 **Value:** 1000+ **Target Year:** 2018 **Value:** 1000+ **Target Year:** 2019 **Value:** 1000+ **Target Year:** 2020 **Value:** 1000+ **Target Year:** 2021 **Value:** 1000 **Target Year:** 2022 **Baseline:  Value:** 1000 **Year:** 2017 **Source:** IPs reports   **Indicator 3.1.3B:** Number of women from the excluded groups who have received support as part of COVID-19 response, by type of support. **Targets:  Value:** 750 **Target Year:** 2020 **Value:** 500 **Target Year:** 2021 **Value:** 500 **Target Year:** 2021 **Value:** 3500 **Target Year:** 2022 **Baseline:  Value:** 1000 **Year:** 2020 **Source:** project reports on delivered PPE, food pachages , services etc | 13,002.00 (core)  412,000.00 (non-core) | 11,000.00 (core)  1,318,000.00 (non-core) | 10,251.00 (core)  1,130,000.00 (non-core) | 9,751.00 (core)  1,045,000.00 (non-core) | 0.00 (core)  192,101.00 (non-core) | 44,004.00 (core)  4,097,101.00 (non-core) |
| **Output 3.1.4 Local public authorities (MDT’s, Local Employment Agency, etc) have skills and tools to provide survivor-focused multi-disciplinary services for women subject to violence** | **Indicator 3.1.4A:** Number of multidisciplinary teams, from two districts, with strengthened capacities to provide specialized services for women survivor of violence. **Targets:  Value:** 13 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** project reports  **Indicator 3.1.4B:** The standard operation procedures (SOP) for specialist service for victims of sexual violence available. **Targets:  Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Source:** project reports  **Indicator 3.1.4C:** Number of people at district level who have received support as part of COVID -19 response, by groups and dizagregation. **Targets:  Value:** 500 **Target Year:** 2020 **Value:** 100 **Target Year:** 2021 **Baseline:  Value:** 4600 **Year:** 2020 **Source:** EVA project report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  606,450.00 (non-core) | 0.00 (core)  864,396.00 (non-core) | 0.00 (core)  1,398,099.00 (non-core) | 0.00 (core)  2,868,945.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 68,999.00 (core)  861,144.00 (non-core) | 68,997.00 (core)  1,656,951.00 (non-core) | 23,251.00 (core)  2,029,885.00 (non-core) | 68,748.00 (core)  2,553,276.00 (non-core) | 70,400.00 (core)  2,574,919.00 (non-core) | 300,395.00 (core)  9,676,175.00 (non-core) |
| **Total Resources for impact area 3** | | | 68,999.00 (core)  861,144.00 (non-core) | 68,997.00 (core)  1,656,951.00 (non-core) | 23,251.00 (core)  2,029,885.00 (non-core) | 68,748.00 (core)  2,553,276.00 (non-core) | 70,400.00 (core)  2,574,919.00 (non-core) | 300,395.00 (core)  9,676,175.00 (non-core) |