

UN Women Strategic Note 2020-2025

**UN WOMEN Mexico COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |
| --- | --- |
| **Impact6Governance and national planning fully reflect accountability for gender equality commitments and priorities** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: UNSDCF 2020-2025/I. Inclusion and equiality/Direct Effect: 1Related national development priorities:** |
|  |  |  | **Year2020** | **Year2021** | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Total** |
| **Outcome 6.1By 2025, the Mexican State has a comprehensive strategy for social development, combating multidimensional poverty and inequality, with an integrated approach to human rights, gender, interculturality, life cycle and territory, which incorporates re-distributive mechanisms without leaving anyone behind.Related SP Outcome/Output:** | **Output 6.1.1National government, civil society, private sector, academy, international cooperation institutions and the UN promote coordinated actions and increase their capabilities to comply with international instruments, follow-up on global women’s Human Rights and 2030 Agenda and promote socio-cultural transformation in order not to leave any woman or girl behind.** | **Indicator 6.1.1A:** Number of joint initiatives with civil society and UNW to advocate for or monitor women's Human Rights and sustainable development (SDG) agendas.**Targets: Value:** 1**Target Year:** 2020**Value:** 2**Notes:** 1 in 2021**Target Year:** 2021**Value:** 3**Notes:** 1 in 2022**Target Year:** 2022**Value:** 4**Notes:** 1 in 2023**Target Year:** 2023**Value:** 5**Notes:** 1 in 2024**Target Year:** 2024**Value:** 6**Notes:** 1 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** internal documents**Indicator 6.1.1B:** Number of meetings between UN Women and the Civil Society Advisory Group**Targets: Value:** 2**Target Year:** 2020**Value:** 4**Notes:** 2 in 2021**Target Year:** 2021**Value:** 6**Notes:** 2 in 2022**Target Year:** 2022**Value:** 8**Notes:** 2 in 2023**Target Year:** 2023**Value:** 10**Notes:** 2 in 2024**Target Year:** 2024**Value:** 12**Notes:** 2 in 2025**Target Year:** 2025**Baseline: Value:** 3 **Year:** 2019**Source:** UN Women internal records**Indicator 6.1.1C:** Number of joint initiatives developed in partnership with International cooperation institutions or the International Cooperation Round table for Gender Equality to advance towards substantive equality**Targets: Value:** 1**Target Year:** 2020**Value:** 2**Notes:** 1 in 2021**Target Year:** 2021**Value:** 3**Notes:** 1 in 2022**Target Year:** 2022**Value:** 4**Notes:** 1 in 2023**Target Year:** 2023**Value:** 5**Notes:** 1 in 2024**Target Year:** 2024**Value:** 6**Notes:** 1 in 2025**Target Year:** 2025**Baseline: Value:** 1 **Year:** 2019**Source:** Annual project reports**Indicator 6.1.1D:** Number of reporting processes of National Institutions supported by UN Women through technical assistance or provision of evidence and data.**Targets: Value:** 2**Target Year:** 2020**Value:** 4**Notes:** 2 in 2021**Target Year:** 2021**Value:** 6**Notes:** 2 in 2022**Target Year:** 2022**Value:** 8**Notes:** 2 in 2023**Target Year:** 2023**Value:** 10**Notes:** 2 in 2024**Target Year:** 2024**Value:** 12**Notes:** 2 in 2025**Target Year:** 2025**Baseline: Value:** 8 **Year:** 2018**Source:** UNW internal documents**Indicator 6.1.1E:** Number of new institutions, private sector and non-traditional actors engaging in campaigns or socio-cultural transformation initiatives implemented by UN Women.**Targets: Value:** 3**Target Year:** 2020**Value:** 6**Notes:** 3 in 2021**Target Year:** 2021**Value:** 9**Notes:** 3 in 2022**Target Year:** 2022**Value:** 12**Notes:** 3 in 2023**Target Year:** 2023**Value:** 15**Notes:** 3 in 2024**Target Year:** 2024**Value:** 18**Notes:** 3 in 2025**Target Year:** 2025**Baseline: Value:** 57 **Year:** 2018**Source:** Campaigns, Social Media and Media Reports (Communications Department).**Indicator 6.1.1F:** Percentage of partners who consider that UN Women has improved its advocacy capacities.**Targets: Value:** 30%**Target Year:** 2021**Value:** 40%**Target Year:** 2023**Value:** 50%**Target Year:** 2025**Baseline: Value:** 0% **Year:** 2019**Source:** Via a partner’s survey applied by UNW communication area | 85,142.00(core)262,558.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 510,852.00(core)512,558.00(non-core) |
| **Total Resources for outcome 6.1 (core and non-core)** | 85,142.00(core)262,558.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 510,852.00(core)512,558.00(non-core) |
| **Total Resources for impact area 6** | 85,142.00(core)262,558.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 85,142.00(core)50,000.00(non-core) | 510,852.00(core)512,558.00(non-core) |
| **Impact1Political participation, gender responsive budgets, plans and statistics** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: UNSDCF 2020-2025/II. Prosperity and innovation/Direct Effect: 3Related national development priorities:** |
|  |  |  | **Year2020** | **Year2021** | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Total** |
| **Outcome 1.1By 2025, the Mexican State plans with territorial, population and gender perspective, inclusive strategies to generate shared prosperity that reduces inequality and poverty.Related SP Outcome/Output:** | **Output 1.1.1National institutions strengthen their technical capacities to produce and use gender-sensitive statistics and design, implement, monitor and evaluate gender-responsive budgets and public policies for GEWE to advance the 2030 Agenda.** | **Indicator 1.1.1A:** Number of knowledge products/methodologies/tools to advance the production and use of gender sensitive statistics produced with UN Women support**Targets: Value:** 2**Target Year:** 2020**Value:** 4**Notes:** 2 in 2021**Target Year:** 2021**Value:** 6**Notes:** 2 in 2022**Target Year:** 2022**Value:** 8**Notes:** 2 in 2023**Target Year:** 2023**Value:** 10**Notes:** 2 in 2024**Target Year:** 2024**Value:** 12**Notes:** 2 in 2025**Target Year:** 2025**Baseline: Value:** 13 **Year:** 2018**Source:** UN Women internal records**Indicator 1.1.1B:** Number of knowledge-sharing events and communities of practices, fora and webinars co-organized by UNW.**Targets: Value:** 10**Target Year:** 2020**Value:** 20**Notes:** 10 in 2021**Target Year:** 2021**Value:** 30**Notes:** 10 in 2022**Target Year:** 2022**Value:** 40**Notes:** 10 in 2023**Target Year:** 2023**Value:** 50**Notes:** 10 in 2024**Target Year:** 2024**Value:** 60**Notes:** 10 in 2025**Target Year:** 2025**Baseline: Value:** 10 **Year:** 2019**Source:** UN Women internal records | 86,768.00(core)199,159.00(non-core) | 86,768.00(core)130,077.00(non-core) | 86,768.00(core)130,077.00(non-core) | 86,768.00(core)130,077.00(non-core) | 86,768.00(core)130,077.00(non-core) | 86,768.00(core)130,077.00(non-core) | 520,608.00(core)849,544.00(non-core) |
| **Output 1.1.2Federal and local stakeholders strengthen their capacities to guarantee women´s social, public and political participation, based on the parity principle, to influence decision-making in all areas, supported on data and evidence.** | **Indicator 1.1.2A:** Number of UN Women advocacy actions/high level policy dialogue co-organized with Federal or State authorities to advance women’s political and electoral rights, and the parity principle**Targets: Value:** 4**Target Year:** 2020**Value:** 8**Notes:** 4 in 2021**Target Year:** 2021**Value:** 12**Notes:** 4 in 2022**Target Year:** 2022**Value:** 16**Notes:** 4 in 2023**Target Year:** 2023**Value:** 20**Notes:** 4 in 2024**Target Year:** 2024**Value:** 24**Notes:** 4 in 2025**Target Year:** 2025**Baseline: Value:** 18 **Year:** 2018**Source:** UN Women internal records | 23,000.00(core)130,077.00(non-core) | 23,000.00(core)130,077.00(non-core) | 23,000.00(core)130,077.00(non-core) | 23,000.00(core)130,077.00(non-core) | 23,000.00(core)130,077.00(non-core) | 23,000.00(core)130,077.00(non-core) | 138,000.00(core)780,462.00(non-core) |
| **Output 1.1.3National Statistics Offices drive analysis, research and innovation on gender statistics through the exchange of best practices at global, regional and national level to track progress of gender equality and women’s empowerment.** | **Indicator 1.1.3A:** Number of knowledge products and tools to disseminate or exchange best practices in gender-sensitive statistics and in gender-sensitive geospatial analysis produced by national, regional and global institutions in partnership with UNW.**Targets: Value:** 2**Target Year:** 2020**Value:** 4**Notes:** 2 in 2021**Target Year:** 2021**Value:** 6**Notes:** 2 in 2022**Target Year:** 2022**Value:** 8**Notes:** 2 in 2023**Target Year:** 2023**Value:** 10**Notes:** 2 in 2024**Target Year:** 2024**Value:** 12**Notes:** 2 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women internal records**Indicator 1.1.3B:** Number of multi stakeholder events linking users, producers, policymakers, civil society organizations and academia to support user-producer dialogues, organized per year.**Targets: Value:** 2**Target Year:** 2020**Value:** 4**Notes:** 2 in 2021**Target Year:** 2021**Value:** 6**Notes:** 2 in 2022**Target Year:** 2022**Value:** 8**Notes:** 2 in 2023**Target Year:** 2023**Value:** 10**Notes:** 2 in 2024**Target Year:** 2024**Value:** 12**Notes:** 2 in 2025**Target Year:** 2025**Baseline: Value:** 3 **Year:** 2019**Source:** UN Women internal records | 0.00(core)643,682.00(non-core) | 0.00(core)130,077.00(non-core) | 0.00(core)130,077.00(non-core) | 0.00(core)130,077.00(non-core) | 0.00(core)130,077.00(non-core) | 0.00(core)130,077.00(non-core) | 0.00(core)1,294,067.00(non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | 109,768.00(core)972,918.00(non-core) | 109,768.00(core)390,231.00(non-core) | 109,768.00(core)390,231.00(non-core) | 109,768.00(core)390,231.00(non-core) | 109,768.00(core)390,231.00(non-core) | 109,768.00(core)390,231.00(non-core) | 658,608.00(core)2,924,073.00(non-core) |
| **Total Resources for impact area 1** | 109,768.00(core)972,918.00(non-core) | 109,768.00(core)390,231.00(non-core) | 109,768.00(core)390,231.00(non-core) | 109,768.00(core)390,231.00(non-core) | 109,768.00(core)390,231.00(non-core) | 109,768.00(core)390,231.00(non-core) | 658,608.00(core)2,924,073.00(non-core) |
| **Impact2Women, especially the poorest and most excluded, are economically empowered and benefit from development** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: UNSDCF 2020-2025/I. Inclusion and equiality/Direct Effect: 2 and 5UNSDCF 2020-2025/III. Green economy and climate change/Direct Effect: 7Related national development priorities:** |
|  |  |  | **Year2020** | **Year2021** | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Total** |
| **Outcome 2.1By 2025, the population in conditions of greatest vulnerability has access to universal health, education and culture, food, social protection and a comprehensive quality care system.Related SP Outcome/Output:** | **Output 2.1.1Public, private and civil society institutions strengthen their capacity to generate and use knowledge, evidence and statistics to design and implement policies that promote WEE and contribute to national and local care strategies implementation.** | **Indicator 2.1.1A:** Number of programmes/policies designed for the promotion of women’s economic empowerment with technical support of UN Women**Targets: Value:** 1**Target Year:** 2020**Value:** 2**Notes:** 1 in 2021**Target Year:** 2021**Value:** 3**Notes:** 1 in 2022**Target Year:** 2022**Value:** 4**Notes:** 1 in 2023**Target Year:** 2023**Value:** 5**Notes:** 1 in 2024**Target Year:** 2024**Value:** 6**Notes:** 1 in 2025**Target Year:** 2026**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women internal records**Indicator 2.1.1B:** Number of evidence-based knowledge products/key analyses on time use/women´s unpaid care work produced or supported by UN Women.**Targets: Value:** 1**Target Year:** 2020**Value:** 2**Notes:** 1 in 2021**Target Year:** 2021**Value:** 3**Notes:** 1 in 2022**Target Year:** 2022**Value:** 4**Notes:** 1 in 2023**Target Year:** 2023**Value:** 5**Notes:** 1 in 2024**Target Year:** 2024**Value:** 6**Notes:** 1 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women internal records | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)600,000.00(non-core) |
| **Output 2.1.2Women in vulnerable situations and employers improve their access to information on labor rights and integrated social protection systems (domestic workers and migrants / asylum seekers and refugees / returnees)** | **Indicator 2.1.2A:** Number of women with improved access to information and knowledge on labor rights and integrated social protection systems.**Targets: Value:** 50**Target Year:** 2020**Value:** 100**Notes:** 50 in 2021**Target Year:** 2021**Value:** 155**Notes:** 55 in 2022**Target Year:** 2022**Value:** 210**Notes:** 55 in 2023**Target Year:** 2023**Value:** 265**Notes:** 55 in 2024**Target Year:** 2024**Value:** 320**Notes:** 55 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2018**Source:** UN Women internal records**Indicator 2.1.2B:** Number of employers with improved access to information and knowledge on labor rights and integrated social protection systems.**Targets: Value:** TBD**Notes:** TBD (SDG Fund scope 2020-2021).**Target Year:** 2020**Value:** TBD**Notes:** TBD (SDG Fund scope 2020-2021).**Target Year:** 2021**Value:** TBD**Notes:** TBD (SDG Fund scope 2020-2021).**Target Year:** 2022**Value:** TBD**Notes:** TBD (SDG Fund scope 2020-2021).**Target Year:** 2023**Value:** TBD**Notes:** TBD (SDG Fund scope 2020-2021).**Target Year:** 2024**Value:** TBD**Notes:** TBD (SDG Fund scope 2020-2021).**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2018**Source:** UN Women internal records | 0.00(core)57,000.00(non-core) | 0.00(core)256,635.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)713,635.00(non-core) |
| **Output 2.1.3Public, private and civil society institutions involved in care work, increase their analysis capabilities and access evidence to formulate and implement a care strategy at the national and local level.** | **Indicator 2.1.3A:** Number of capacity development and technical assistance initiatives designed to improve awareness of care strategy supported by UNW.**Targets: Value:** 1**Target Year:** 2020**Value:** 2**Target Year:** 2021**Value:** 3**Target Year:** 2022**Value:** 4**Target Year:** 2023**Value:** 5**Target Year:** 2024**Value:** 6**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women internal records | 0.00(core)229,218.00(non-core) | 0.00(core)256,635.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)885,853.00(non-core) |
| **Outcome 2.2By 2025, the Mexican State has decent work programs to address labor market needs, including institutional strengthening, job training, formalization, women's economic participation, protection of rights, social mobility and labor justice.Related SP Outcome/Output:** | **Output 2.2.1Women and young women belonging to left behind groups increase their access to innovative programs of study (STEM), training, labor opportunities and productive assets for entrepreneurship (migrants, youth, rural women)** | **Indicator 2.2.1A:** Number of women and young women that access programs of study and training supported by UNW.**Targets: Value:** 2200**Target Year:** 2020**Value:** 4700**Notes:** 2500 in 2021**Target Year:** 2021**Value:** TBD**Target Year:** 2022**Value:** TBD**Target Year:** 2023**Value:** TBD**Target Year:** 2024**Value:** TBD**Target Year:** 2025**Baseline: Value:** 300 **Year:** 2019**Source:** M&E Framework for Second Chance Education**Indicator 2.2.1B:** Number of women and young women that access productive assets for entrepreneurship.**Targets: Value:** 660**Target Year:** 2020**Value:** 1410**Notes:** 750 in 2021**Target Year:** 2021**Value:** TBD**Target Year:** 2022**Value:** TBD**Target Year:** 2023**Value:** TBD**Target Year:** 2024**Value:** TBD**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** M&E Framework for Second Chance Education**Indicator 2.2.1C:** Number of women and young women that access labor opportunities.**Targets: Value:** 400**Target Year:** 2020**Value:** 940**Notes:** 500 in 2021**Target Year:** 2021**Value:** TBD**Target Year:** 2022**Value:** TBD**Target Year:** 2023**Value:** TBD**Target Year:** 2024**Value:** TBD**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** M&E Framework for Second Chance Education | 0.00(core)786,601.00(non-core) | 0.00(core)213,717.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)1,400,318.00(non-core) |
| **Output 2.2.2Local communities, companies, national and local institutions strength their capacities to promote positive masculinities and the transformation of social norms and cultural practices that discriminate women access to educational labor and entrepreneurship opportunities.** | **Indicator 2.2.2A:** Number of partners that make public statements against gender discrimination, design and/or implement gender equality policies, and/or commit financial resources to fight against gender discrimination.**Targets: Value:** 1**Target Year:** 2020**Value:** 2**Notes:** 1 in 2021**Target Year:** 2021**Value:** 3**Notes:** 1 in 2022**Target Year:** 2022**Value:** 4**Notes:** 1 in 2023**Target Year:** 2023**Value:** 6**Notes:** 2 in 2024**Target Year:** 2024**Value:** 8**Notes:** 2 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal records | 0.00(core)296,644.00(non-core) | 0.00(core)213,717.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)910,361.00(non-core) |
| **Output 2.2.3Public, private and civil society institutions strength their coordination and their capacities to prioritize education, vocational training and access to employment or business development opportunities for women in a situation of greater vulnerability.** | **Indicator 2.2.3A:** Number of public, private and civil society partnerships created by UNW to include more women and young women in education, vocational training and employment opportunities.**Targets: Value:** 4**Target Year:** 2020**Value:** 8**Notes:** 4 in 2021**Target Year:** 2021**Value:** 12**Notes:** 4 in 2022**Target Year:** 2022**Value:** 16**Notes:** 4 in 2023**Target Year:** 2023**Value:** 20**Notes:** 4 in 2024**Target Year:** 2024**Value:** 25**Notes:** 5 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico | 0.00(core)143,311.00(non-core) | 0.00(core)213,717.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)757,028.00(non-core) |
| **Output 2.2.4Private companies implement gender equality policies and are committed to economic development, access to the labor market and the autonomy of women and girls. (WEPS)** | **Indicator 2.2.4A:** Annual percentage increase of the number of companies that sign the WEPS.**Targets: Value:** 10%**Target Year:** 2021**Value:** 20%**Notes:** 10% in 2022**Target Year:** 2022**Value:** 40%**Notes:** 20% in 2023**Target Year:** 2023**Value:** 60%**Notes:** 20% in 2025**Target Year:** 2024**Baseline: Value:** 20% **Year:** 2019**Source:** UN Women Mexico internal records | 4,000.00(core)30,000.00(non-core) | 4,000.00(core)213,717.00(non-core) | 4,000.00(core)0.00(non-core) | 4,000.00(core)0.00(non-core) | 4,000.00(core)0.00(non-core) | 4,000.00(core)0.00(non-core) | 24,000.00(core)243,717.00(non-core) |
| **Outcome 2.3By 2025, the Mexican State strengthens its capacities for adaptation and resilience to climate variability and change through multisectoral policies, programs, tools and services, with a focus on the most vulnerable groups and territories; consolidating the perspectives of interculturality, human rights and gender, which consider the integral management of water, disaster risks and based on the sustainable management of terrestrial, coastal and marine ecosystems.Related SP Outcome/Output:** | **Output 2.3.1Women affected by humanitarian situations and living in areas of greater vulnerability to disasters develop capacities to design and manage innovative and sustainable businesses.** | **Indicator 2.3.1A:** Number of women affected by disasters or in humanitarian situations that develop capacities to design and manage businesses.**Targets: Value:** 500**Target Year:** 2020**Value:** 1000**Notes:** 500 in 2021**Target Year:** 2021**Value:** 1450**Notes:** 450 in 2022**Target Year:** 2022**Value:** 1900**Notes:** 450 in 2023**Target Year:** 2023**Value:** 2350**Notes:** 450 in 2024**Target Year:** 2024**Value:** 405**Notes:** 405 in 2025**Target Year:** 2025**Baseline: Value:** 755 **Year:** 2019**Source:** UN Women Mexico internal records**Indicator 2.3.1B:** Number of women led businesses directly supported with funding or technical assistance from UNW.**Targets: Value:** TBD**Target Year:** 2020**Value:** TBD**Target Year:** 2021**Value:** TBD**Target Year:** 2022**Value:** TBD**Target Year:** 2023**Value:** TBD**Target Year:** 2024**Value:** TBD**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women internal records | 0.00(core)669,820.00(non-core) | 0.00(core)160,667.00(non-core) | 0.00(core)160,667.00(non-core) | 0.00(core)160,667.00(non-core) | 0.00(core)160,667.00(non-core) | 0.00(core)160,667.00(non-core) | 0.00(core)1,473,155.00(non-core) |
| **Output 2.3.2Local institutions generate economic empowerment and entrepreneurship policies based on evidence of the impact of climate change and human mobility on women.** | **Indicator 2.3.2A:** Number of local institutions that design and implement economic empowerment and entrepreneurship policies based on evidence.**Targets: Value:** 1**Target Year:** 2020**Value:** 2**Notes:** 1 in 2021**Target Year:** 2021**Value:** 3**Notes:** 1 in 2022**Target Year:** 2022**Value:** 4**Notes:** 1 in 2023**Target Year:** 2023**Value:** 5**Notes:** 1 in 2024**Target Year:** 2024**Value:** 6**Notes:** 1 in 2025**Target Year:** 2025**Baseline: Value:** 1 **Year:** 2019**Source:** UN Women Mexico internal records | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 54,000.00(core)964,002.00(non-core) |
| **Output 2.3.3Civil society organizations (including women defenders of the environment, or in a situation of mobility), strengthen their participation in disaster risks management and their capacity to influence climate change responses, mitigation policies and programs.** | **Indicator 2.3.3A:** Number of civil society organizations that participate in the definition of disaster risk management policies and programs with the support of UN Women.**Targets: Value:** 1**Target Year:** 2021**Value:** 2**Notes:** 1 in 2023**Target Year:** 2023**Value:** 3**Notes:** 1 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal records**Indicator 2.3.3B:** Number of civil society organizations that participate in the design of climate change adaptation and mitigation policies**Targets: Value:** 1**Target Year:** 2021**Value:** 2**Notes:** 1 in 2023**Target Year:** 2023**Value:** 3**Notes:** 1 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal records | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 9,000.00(core)160,667.00(non-core) | 54,000.00(core)964,002.00(non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | 0.00(core)386,218.00(non-core) | 0.00(core)613,270.00(non-core) | 0.00(core)300,000.00(non-core) | 0.00(core)300,000.00(non-core) | 0.00(core)300,000.00(non-core) | 0.00(core)300,000.00(non-core) | 0.00(core)2,199,488.00(non-core) |
| **Total Resources for outcome 2.2 (core and non-core)** | 4,000.00(core)1,256,556.00(non-core) | 4,000.00(core)854,868.00(non-core) | 4,000.00(core)300,000.00(non-core) | 4,000.00(core)300,000.00(non-core) | 4,000.00(core)300,000.00(non-core) | 4,000.00(core)300,000.00(non-core) | 24,000.00(core)3,311,424.00(non-core) |
| **Total Resources for outcome 2.3 (core and non-core)** | 18,000.00(core)991,154.00(non-core) | 18,000.00(core)482,001.00(non-core) | 18,000.00(core)482,001.00(non-core) | 18,000.00(core)482,001.00(non-core) | 18,000.00(core)482,001.00(non-core) | 18,000.00(core)482,001.00(non-core) | 108,000.00(core)3,401,159.00(non-core) |
| **Total Resources for impact area 2** | 22,000.00(core)2,633,928.00(non-core) | 22,000.00(core)1,950,139.00(non-core) | 22,000.00(core)1,082,001.00(non-core) | 22,000.00(core)1,082,001.00(non-core) | 22,000.00(core)1,082,001.00(non-core) | 22,000.00(core)1,082,001.00(non-core) | 132,000.00(core)8,912,071.00(non-core) |
| **Impact3Women and girls live a life free from violence** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: UNSDCF 2020-2025/IV. Peace, Justice and Rule of Law/Direct Effect: 8Related national development priorities:** |
|  |  |  | **Year2020** | **Year2021** | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Total** |
| **Outcome 3.1By 2025, the Mexican State effectively implements regulatory frameworks, public policies and quality mechanisms that prevent and sanction all forms and manifestations of violence, particularly against women, girls and adolescents, to while guaranteeing access to quality services for proper care and protection for victims.Related SP Outcome/Output:** | **Output 3.1.1World-class quality, disaggregated and comparable data on the different forms of VAWG are collected, analyzed and used in accordance with international standards to have an impact on political laws and programs(Spotlight Outcome 5)** | **Indicator 3.1.1A:** Number of knowledge products developed and disseminated among relevant players to inform of the decision-making process, based on evidence.(Spotlight Indicator 5.2.1)**Targets: Value:** 2**Target Year:** 2020**Value:** 4**Notes:** 2 in 2021**Target Year:** 2021**Value:** 6**Notes:** 2 in 2022**Target Year:** 2022**Value:** 8**Notes:** 2 in 2023**Target Year:** 2023**Value:** 10**Notes:** 2 in 2024**Target Year:** 2024**Value:** 12**Notes:** 2 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal records**Indicator 3.1.1B:** Number of government staff, including service providers from various sectors and human rights defenders for women, with reinforced capabilities for analysis and dissemination of information on the prevalence and/or incidence of VAWG (Spotlight Indicator 5.2.3)**Targets: Value:** 100**Target Year:** 2020**Value:** 200**Notes:** 100 in 2021**Target Year:** 2021**Value:** 300**Notes:** 100 in 2022**Target Year:** 2022**Value:** 400**Notes:** 100 in 2023**Target Year:** 2023**Value:** 500**Notes:** 100 in 2024**Target Year:** 2024**Value:** 600**Notes:** 100 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal records | 0.00(core)113,213.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)613,213.00(non-core) |
| **Output 3.1.2Social standards, mindsets, and behaviors on general equality change at a community and individual level to prevent VAWG through the adoption of positive masculinities. (Spotlight outcome 3)** | **Indicator 3.1.2A:** Number of men and boys that regularly attend gender transformation programmes that address violent masculinities and violence among men against women and girls that are implemented in community centers, schools, and other relevant spaces. (Spotlight Indicator 3.2.3)**Targets: Value:** 100**Target Year:** 2020**Value:** 200**Notes:** 100 in 2021**Target Year:** 2021**Value:** 300**Notes:** 100 in 2022**Target Year:** 2022**Value:** 400**Notes:** 100 in 2023**Target Year:** 2023**Value:** 500**Notes:** 100 in 2024**Target Year:** 2024**Value:** 600**Notes:** 100 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico**Indicator 3.1.2B:** Number of news and other media stories/reports that sensitively report on VAWG/Femicide and GEWE more broadly (Spotlight Indicator 3.3.3).**Targets: Value:** TBD**Notes:** TBD after Spotlight baseline study is concluded**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** Media Report (Communications Department) and /or UN Women’s website in Mexico (https://mexico.unwome**Indicator 3.1.2C:** 0.3.a Number of qualitative reviews undertaken to advance evidence and knowledge on methods to assess, monitor and/or achieve behaviour and social norms change**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UN Women Reports | 0.00(core)74,567.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)574,567.00(non-core) |
| **Output 3.1.3Legal frameworks and policies, based on evidence and according to the human rights standards on all forms of VAWG, are currently active and enforced. (Spotlight outcome 1)** | **Indicator 3.1.3A:** Number of institutions receiving technical assistance by UN Women to develop/revise laws, policies and strategies on VAW prevention.**Targets: Value:** TBD**Notes:** To be defined after Spotlight baseline study is concluded**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico**Indicator 3.1.3B:** Number of draft new and/or strengthened laws and/or policies to prevent, and sanction feminicide and other forms of VAWG developed or supported. (Spotlight 1.1.1.)**Targets: Value:** TBD**Notes:** To be defined after Spotlight baseline study is concluded**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico**Indicator 3.1.3C:** 0.1.d Number of partners that have increased capacities to promote/influence gender-responsive legislation and its implementation (UNAIDS, UNDP, UNICEF)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UNSDCF Annual Report**Indicator 3.1.3D:** 0.1.e Number of partners that have increased capacities to advance gender equality and women’s empowerment through national and/or local (multi)sectoral strategies, policies and/or action plans (UNAIDS, UNDP)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UNSDCF Annual Report**Indicator 3.1.3E:** 0.1.f Number of institutions that have increased capacities to design and implement institutional reforms/strategies/policies that promote gender equality and women’s empowerment (UNAIDS, UNDP, UNICEF, WHO)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UNSDCF Annual Report | 0.00(core)329,554.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)829,554.00(non-core) |
| **Output 3.1.4Women rights groups, autonomous social movements, and relevant civil society organizations, including those that represents young individuals and groups that fight cross-sectional forms of discrimination, impact and make progress more effectively in the elimination of VAWG (Spotlight outcome 6)** | **Indicator 3.1.4A:** Number of women rights groups, networks, and relevant CSO’s with strengthened capabilities to form networks, partnerships, and joint impact on the progress to eradicate feminicide at a local, national, regional, and global level. (Spotlight indicator Indicator 6.1.4)**Targets: Value:** 2**Target Year:** 2020**Value:** 4**Notes:** 2 in 2021**Target Year:** 2021**Value:** 6**Notes:** 2 in 2022**Target Year:** 2022**Value:** 8**Notes:** 2 in 2023**Target Year:** 2023**Value:** 10**Notes:** 2 in 2024**Target Year:** 2024**Value:** 12**Notes:** 2 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal records**Indicator 3.1.4B:** Number of official dialogues with relevant government authorities with the meaningful participation of women's rights groups and relevant CSOs, including representatives of groups facing multiple and intersecting forms of discrimination (Spotlight 6.1.2)**Targets: Value:** 1**Target Year:** 2021**Value:** 2**Notes:** 1 in 2023**Target Year:** 2023**Value:** 3**Notes:** 1 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal records**Indicator 3.1.4C:** 0.4.c Number of women’s organizations with increased capacities to deliver and/or monitor the quality of services, resources and goods for women in humanitarian and development settings (UNAIDS, UNFPA)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UNSDCF Annual Report**Indicator 3.1.4D:** 0.4.d Number of women accessing information, goods, resources and/or services through UN-Women-supported platforms and programmes in humanitarian and development settings (UNDP, UNFPA, UNICEF, WHO)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UN Women Reports**Indicator 3.1.4E:** 0.5.c Number of dialogues, mechanisms, platforms and/or coalitions created and sustained that enable meaningful and safe participation and engagement by gender equality advocates and civil society organizations working on gender equality and women’s empowerment, especially women’s organizations, in decision making (UNAIDS, UNDP, UNFPA, UNICEF)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UNSDCF Annual Report | 0.00(core)449,050.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)949,050.00(non-core) |
| **Output 3.1.5More cities and other work, digital and educational settings have safe and empowering spaces for women and girls that promote the transformation of social norms and positive masculinities. (Safe cities)** | **Indicator 3.1.5A:** Number of municipalities that implement strategies to increase safety in public spaces.**Targets: Value:** 1**Target Year:** 2020**Value:** 2**Notes:** 1 in 2021**Target Year:** 2021**Value:** 3**Notes:** 1 in 2022**Target Year:** 2022**Value:** 4**Notes:** 1 in 2023**Target Year:** 2023**Value:** 5**Notes:** 1 in 2024**Target Year:** 2024**Value:** 6**Notes:** 1 in 2025**Target Year:** 2025**Baseline: Value:** 5 **Year:** 2018**Source:** UN Women Mexico**Indicator 3.1.5B:** Number of men and boys that participate in local initiative promoting positive masculinities.**Targets: Value:** 100**Target Year:** 2020**Value:** 200**Notes:** 100 in 2021**Target Year:** 2021**Value:** 300**Notes:** 100 in 2022**Target Year:** 2022**Value:** 400**Notes:** 100 in 2023**Target Year:** 2023**Value:** 500**Notes:** 100 in 2024**Target Year:** 2024**Value:** 600**Notes:** 100 in 2025**Target Year:** 2024**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal records**Indicator 3.1.5C:** 0.3.a Number of qualitative reviews undertaken to advance evidence and knowledge on methods to assess, monitor and/or achieve behaviour and social norms change**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UN Women Reports**Indicator 3.1.5D:** 0.3.e Number of draft policies with monitoring/reporting mechanism to address institutionalized gender discriminatory or inequitable practices developed by partners (UNDP, UNFPA)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UN Women Reports**Indicator 3.1.5F:** 0.4.e Number of countries with multi stakeholder initiatives in place to prevent and respond to sexual violence including sexual harassment in public and/or private spaces (UNDP, UNICEF, WHO)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UN Women Report | 0.00(core)1,180,137.00(non-core) | 0.00(core)898,666.00(non-core) | 0.00(core)208,666.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)100,000.00(non-core) | 0.00(core)2,587,469.00(non-core) |
| **Output 3.1.6Institutions and society have access to knowledge, statistics, tools as well as communication campaigns to prevent all forms of violence against women and girls while promoting the transformation of social norms and positive masculinities for the full exercise of economic, social, cultural and political women´s rights.** | **Indicator 3.1.6A:** Number of campaigns/communication initiatives implemented by UN Women to prevent VAWG and promote positive masculinities.**Targets: Value:** 2**Target Year:** 2020**Value:** 4**Notes:** 2 in 2021**Target Year:** 2021**Value:** 6**Notes:** 2 in 2022**Target Year:** 2022**Value:** 8**Notes:** 2 in 2023**Target Year:** 2023**Value:** 10**Notes:** 2 in 2024**Target Year:** 2024**Value:** 12**Notes:** 2 in 2025**Target Year:** 2025**Baseline: Value:** 2 **Year:** 2019**Notes:** (1 Monterrey and 1 in Guadalajara)**Source:** Campaign, social media and media reports (Communications Department).**Indicator 3.1.6B:** Number of public servants that access new knowledge products, statistics and tools that help them improving the fulfillment of their duties**Targets: Value:** 50**Target Year:** 2020**Value:** 100**Notes:** 50 in 2021**Target Year:** 2021**Value:** 150**Notes:** 50 in 2022**Target Year:** 2022**Value:** 200**Notes:** 50 in 2023**Target Year:** 2023**Value:** 250**Notes:** 50 in 2024**Target Year:** 2024**Value:** 300**Notes:** 50 in 2025**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal records**Indicator 3.1.6C:** 0.4.d Number of women accessing information, goods, resources and/or services through UN-Women-supported platforms and programmes in humanitarian and development settings (UNDP, UNFPA, UNICEF, WHO)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UN Women Reports**Indicator 3.1.6D:** 0.5.c Number of dialogues, mechanisms, platforms and/or coalitions created and sustained that enable meaningful and safe participation and engagement by gender equality advocates and civil society organizations working on gender equality and women’s empowerment, especially women’s organizations, in decision making (UNAIDS, UNDP, UNFPA, UNICEF)**Targets: Value:** 1**Target Year:** 2023**Baseline: Value:** 1 **Year:** 2021**Source:** UN Women Reports | 71,600.00(core)0.00(non-core) | 71,600.00(core)0.00(non-core) | 71,600.00(core)0.00(non-core) | 71,600.00(core)0.00(non-core) | 71,600.00(core)0.00(non-core) | 71,600.00(core)0.00(non-core) | 429,600.00(core)0.00(non-core) |
| **Output 3.1.7Spotlight Project Management Cost** |  | 0.00(core)261,138.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)0.00(non-core) | 0.00(core)261,138.00(non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | 71,600.00(core)2,407,659.00(non-core) | 71,600.00(core)1,298,666.00(non-core) | 71,600.00(core)608,666.00(non-core) | 71,600.00(core)500,000.00(non-core) | 71,600.00(core)500,000.00(non-core) | 71,600.00(core)500,000.00(non-core) | 429,600.00(core)5,814,991.00(non-core) |
| **Total Resources for impact area 3** | 71,600.00(core)2,407,659.00(non-core) | 71,600.00(core)1,298,666.00(non-core) | 71,600.00(core)608,666.00(non-core) | 71,600.00(core)500,000.00(non-core) | 71,600.00(core)500,000.00(non-core) | 71,600.00(core)500,000.00(non-core) | 429,600.00(core)5,814,991.00(non-core) |
| **Impact4Women, especially that found in contexts of greater vulnerability, access to justice and reparation** | **Related UN-Women SP Impact Area: Related UNDAF/ CCPD priority: UNSDCF 2020-2025/IV. Peace, Justice and Rule of Law/Direct Effect: 10Related national development priorities:** |
|  |  |  | **Year2020** | **Year2021** | **Year2022** | **Year2023** | **Year2024** | **Year2025** | **Total** |
| **Outcome 4.1Mexican State advance in the promotion, protection and respect of the full exercise of women human rights to access to justice and reparation for the entire population , especially that found in contexts of greater vulnerability, in conditions of equality and under the principle of leaving no one behindRelated SP Outcome/Output:** | **Output 4.1.1Competent institutions strengthen their capacities to guarantee access to justice for women and girls survivors of violence, as well as women human rights defenders, journalists, activists and relatives of victims of human rights violations which accordingly increase their capacity to participate and influence peacebuilding and conflict reduction processes.** | **Indicator 4.1.1A:** Number of women's organizations with increased capacities to support the implementation of the WPS agenda and to advocate for women's participation in peace building, with support of UN Women.**Targets: Value:** 3**Target Year:** 2020**Value:** 5**Notes:** 2 in 2023**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal reports**Indicator 4.1.1B:** Increase of women participating in peacekeeping forces, armed forces and security institutions.**Targets: Value:** 12.0%/18.5%/22.0%/16.0%**Notes:** Defense, marine, national guard and UN Peacekeeping Ops**Target Year:** 2020**Value:** 12.5%/19.0%/22.5%/18.0%**Notes:** Defense, marine, national guard and UN Peacekeeping Ops**Target Year:** 2021**Value:** 13.0%/19.5%/24.0%/20.0%**Notes:** Defense, marine, national guard and UN Peacekeeping Ops**Target Year:** 2022**Value:** 15.0%/20.0%/25.0%/22.0%**Notes:** Defense, marine, national guard and UN Peacekeeping Ops**Target Year:** 2023**Value:** 16.0%/22.0%/27.0%/25.0%**Notes:** Defense, marine, national guard and UN Peacekeeping Ops**Target Year:** 2024**Value:** 18.0%/24.0%/30.0%/30.0%**Notes:** Defense, marine, national guard and UN Peacekeeping Ops**Target Year:** 2025**Baseline: Value:** 11.9% defense/18.3% marine/21.1% national guard/15.0% UN Peacekeeping Ops **Year:** 2019**Notes:** The considered forces are 4: army, navy, national guard and forces that participate in UN Peace Operations.**Source:** Secretary of National Defense, Secretary of the Navy, Secretary of Public Safety and Citizen Protect**Indicator 4.1.1C:** Number of peacekeeping forces, armed forces and security institutions that operates with gender-sensitive protocols.**Targets: Value:** 1**Target Year:** 2021**Value:** 3**Notes:** 2 in 2023**Target Year:** 2023**Value:** 4**Notes:** 1 in 2024**Target Year:** 2024**Baseline: Value:** 0 **Year:** 2019**Notes:** The considered forces are 4: army, navy, national guard and forces that participate in UN Peace Operations.**Source:** President’s Annual Report. Secretary of National Defense Annual Report. **Indicator 4.1.1D:** Number of institutions that strengthen their capacities to guarantee access to justice and comprehensive reparation for women and girls survivor of violence, as well as women human rights defenders, journalists and activists.**Targets: Value:** 2**Target Year:** 2020**Value:** 3**Notes:** 1 in 2023**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal reports**Indicator 4.1.1E:** Number of women and girls’ survivors of violence, as well as women human rights defenders, journalists and activists that can access to justice and comprehensive reparation**Targets: Value:** TBD**Notes:** Milestone overall value yearly values will be defined based on resources mobilization and the milestones established in the National Policy for Attention to Victims 2019-2024.**Target Year:** 2020**Value:** TBD**Notes:** Milestone overall value yearly values will be defined based on resources mobilization and the milestones established in the National Policy for Attention to Victims 2019-2024.**Target Year:** 2021**Value:** TBD**Notes:** Milestone overall value yearly values will be defined based on resources mobilization and the milestones established in the National Policy for Attention to Victims 2019-2024.**Target Year:** 2022**Value:** TBD**Notes:** Milestone overall value yearly values will be defined based on resources mobilization and the milestones established in the National Policy for Attention to Victims 2019-2024.**Target Year:** 2023**Value:** TBD**Notes:** Milestone overall value yearly values will be defined based on resources mobilization and the milestones established in the National Policy for Attention to Victims 2019-2024.**Target Year:** 2024**Value:** TBD**Notes:** Milestone overall value yearly values will be defined based on resources mobilization and the milestones established in the National Policy for Attention to Victims 2019-2024.**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal reports**Indicator 4.1.1F:** Number of mechanisms, services, and immediate responses for women affected by crisis that include a gender and human rights perspective.**Targets: Value:** 2**Target Year:** 2023**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal reports**Indicator 4.1.1G:** Number of women and girls in humanitarian response contexts that access improved gender sensitive services of protection and development opportunities (study, work, training).**Targets: Value:** TBD**Notes:** Milestone overall value and 2021-2025 values will be defined based on resources mobilization.**Target Year:** 2020**Value:** TBD**Notes:** Milestone overall value and 2021-2025 values will be defined based on resources mobilization.**Target Year:** 2021**Value:** TBD**Notes:** Milestone overall value and 2021-2025 values will be defined based on resources mobilization.**Target Year:** 2022**Value:** TBD**Notes:** Milestone overall value and 2021-2025 values will be defined based on resources mobilization.**Target Year:** 2023**Value:** TBD**Notes:** Milestone overall value and 2021-2025 values will be defined based on resources mobilization.**Target Year:** 2024**Value:** TBD**Notes:** Milestone overall value and 2021-2025 values will be defined based on resources mobilization.**Target Year:** 2025**Baseline: Value:** 0 **Year:** 2019**Source:** UN Women Mexico internal reports | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 162,000.00(core)2,838,000.00(non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 162,000.00(core)2,838,000.00(non-core) |
| **Total Resources for impact area 4** | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 27,000.00(core)473,000.00(non-core) | 162,000.00(core)2,838,000.00(non-core) |