

UN Women Strategic Note 2018-2022

**UN WOMEN Niger COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact2 Women have income security, decent work, and economic autonomy.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: 3.2. Strategic Priority 1. Resilience: By 2021, the resilience of the populations in the targeted areas of Niger is improved, with increased livelihoods, a level of poverty and reduced food and nutrition insecurity, in a context of participation institutions and local communities. Outcome 1: By 2021, targeted rural populations access innovative and decent job creation value chains, participate in food and nutrition and disaster prevention and management mechanisms, and sustainable resource management energy and natural resources adapted to the effects of climate change. Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 2.1 Women agricultural producers have better access to productive resources adapted to the arid climate and to markets to improve their income in a sustainable way  Related SP Outcome/Output:**   **Indicator 2.1B:** Number of productive women with facilitation to access markets and technology **Targets:  Value:** 10000 **Notes:** Women with access to productive resources **Target Year:** 2019 **Value:** 200 **Target Year:** 2022 **Baseline:  Value:** 5000 **Year:** 2017 **Note:** Women with access to Productive Resources **Source:** Annual Report  **Indicator 2.1C:** Improved time use by women in farm and house use **Targets:  Value:** 10000 **Target Year:** 2019 **Baseline:  Value:** 5000 **Year:** 2017 **Note:** Improved labour saving devices **Source:** Annual report  **Indicator 2.1D:** Increased number of Village savings and loan associations **Targets:  Value:** 342 **Notes:** Village savings and loans associations **Target Year:** 2019 **Baseline:  Value:** 150 **Year:** 2018 **Source:** Annual Report | **Output 2.1.1 Improved access to productive, time-saving and climate-resilient assets, tools and technologies** | **Indicator 2.1.1G:** Number of elected women and authorities trained on Gender planning and budgeting for decision makers and women on positive masculinities, non-violence at the national and community levels **Targets:  Value:** 5000 **Target Year:** 2021 **Value:** 5000 **Target Year:** 2020 **Value:** 40 **Target Year:** 2022 **Value:** 200 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN W NIGER report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  169,393.00 (non-core) | 0.00 (core)  169,393.00 (non-core) | 0.00 (core)  200,000.00 (non-core) | 0.00 (core)  538,786.00 (non-core) |
| **Output 2.1.4 rural women and young men are aware of the risks associated with migration** | **Indicator 2.1.4B:** Number of processing units established **Targets:  Value:** 5 **Target Year:** 2021 **Value:** 5 **Target Year:** 2020 **Value:** TBM **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** UNW NIger report  **Indicator 2.1.4C:** Existence of the final evaluation on the projet Zinder **Targets:  Value:** Yes **Target Year:** 2022 **Baseline:  Value:** NO **Year:** 2021 **Source:** UN Women report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  778,656.00 (non-core) | 0.00 (core)  778,656.00 (non-core) | 0.00 (core)  90,000.00 (non-core) | 0.00 (core)  1,647,312.00 (non-core) |
| **Output 2.1.6 More marginalised women and young girls access and benefit from financial and other recovery policies/ stimulus package** | **Indicator 2.1.6B:** number of studies produced for advocacy **Targets:  Value:** 2 **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2020 **Source:** UN W Partner report   **Indicator 2.1.6C:** Number of managers trained in gender statstcs **Targets:  Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UNW Partner report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  75,000.00 (non-core) | 12,500.00 (core)  0.00 (non-core) | 12,500.00 (core)  75,000.00 (non-core) |
| **Output 2.1.8 Program activities/outcomes are better monitored and the capacities of the Kandadji Dam Agency and its partners are strengthened on gender** | **Indicator 2.1.8A:** % of Kandadji Dam Agency staff trained on gender **Targets:   Baseline:  Value:** TBM **Year:** 2021 **Source:** the finale evaluation report of the project | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  200,000.00 (non-core) | 0.00 (core)  200,000.00 (non-core) |
| **Outcome 2.2 Economic migration is safe and regular for migrant women and girls  Related SP Outcome/Output:**   **Indicator 2.2A:** Number of leaders? women organization trained for the promotion on the empowerment and rights of women migrants gender sensitive land laws **Targets:  Value:** 200 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women and RP report   **Indicator 2.2B:** Number of structures trained on how to implement the NMP from a gender perspective **Targets:  Value:** 10 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2022 **Source:** UN Women and RP report | **Output 2.2.1 Migration is safe for women migrating from, into and through Niger** | **Indicator 2.2.1A:** Number of national policies laws developed/reviewed Number of national policies laws developed/reviewed **Targets:  Value:** 2 **Target Year:** 2021 **Value:** 2 **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UNW Niger report   **Indicator 2.2.1B:** Number of initatives by migrant women and their organisation advocating for their rights **Targets:  Value:** 5 **Target Year:** 2021 **Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UNW Niger annual report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  270,332.00 (non-core) | 0.00 (core)  519,297.00 (non-core) | 0.00 (core)  789,629.00 (non-core) |
| **Output 2.2.2 The socio-economic protection for migrant women is strengthened by improving services for them** | **Indicator 2.2.2A:** Existence of the final evaluation report of the project migration Tahoua **Targets:  Value:** 35 **Target Year:** 2021 **Value:** yes **Target Year:** 2022 **Baseline:  Value:** no **Year:** 2020 **Source:** UN Women Niger annual report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  691,278.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  741,278.00 (non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  948,049.00 (non-core) | 0.00 (core)  1,023,049.00 (non-core) | 12,500.00 (core)  490,000.00 (non-core) | 12,500.00 (core)  2,461,098.00 (non-core) |
| **Total Resources for outcome 2.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  961,610.00 (non-core) | 0.00 (core)  569,297.00 (non-core) | 0.00 (core)  1,530,907.00 (non-core) |
| **Total Resources for impact area 2** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  948,049.00 (non-core) | 0.00 (core)  1,984,659.00 (non-core) | 12,500.00 (core)  1,059,297.00 (non-core) | 12,500.00 (core)  3,992,005.00 (non-core) |
| **Impact3 Alll women and girls live a life free from all forms of violence.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: 3.4. Strategic Priority 3. Social Development and Demographic Dividends By 2021, the most vulnerable populations, especially girls and boys, and children in targeted areas, and equitable and continuous quality education and training services, both formal and non-formal, Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 3.1 Normative and policy frameworks are promoted and adapted in line with international standards and institutions have the commitment, knwoledge and capacities to legislate, plan, implement, and monitor policies to adress VAWG, GBV and HP  Related SP Outcome/Output:**   **Indicator 3.1A:** Number of persons mobilized against SGBV **Targets:  Value:** 2 million persons **Target Year:** 2018 **Baseline:  Value:** 100,000 **Year:** 2017 **Source:** MUSKOKA annual reports  **Indicator 3.1B:** Increased sensitivity of the population on GBV **Targets:  Value:** 250000 PERSONS SENSITIZED **Notes:** Persons sensitized **Target Year:** 2019 **Baseline:  Value:** 7500 **Year:** 2018 **Note:** Persons sensitized **Source:** Spotlight Report MUSKOKA Report  **Indicator 3.1C:** Existence and application of legal framework **Targets:  Value:** 1 law against SGBV **Notes:** Existence of Legal frameworks **Target Year:** 2019 **Baseline:  Value:** 0 legal framework for SGBV **Year:** 2018 **Note:** REDUCED VIOLENCE **Source:** National journal  **Indicator 3.1D:** Number of support and materials product and disseminate for information's and knowledges on policies, strategies, legislations, statistics among key actors by strengthening their capacities in promoting women's rights and advocacy **Targets:  Value:** 4 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women and RP reports | **Output 3.1.2 Legislative and policy frameworks in line with international human rights standards relating to violence against women and girls and harmful practices are in place and translated into plan.** | **Indicator 3.1.2A:** Niger has adopted laws and policies on VAWG/SGBV/HP that adequately respond to the rights of all women and girls, including access to SRHR, are evidence-based and in line with international norms and standards ( Draft of law on EVAWG). **Targets:  Value:** yes **Target Year:** 2021 **Value:** yes **Target Year:** 2021 **Value:** Yes **Target Year:** 2020 **Value:** Yes **Target Year:** 2022 **Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Source:** UN Women Report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  513,173.00 (non-core) | 0.00 (core)  513,173.00 (non-core) | 0.00 (core)  151,127.00 (non-core) | 0.00 (core)  1,177,473.00 (non-core) |
| **Output 3.1.3 National and regional systems and institutions are empowered to plan, fund and implement multisectoral programmes to prevent and respond to violence against women and girls, as well as harmfull practices especially through the implementation of the SDG** | **Indicator 3.1.3A:** The country established a GRB institutional mechanisms   : put in place the GRB focal points from keys targeted lines minister's **Targets:  Value:** yes **Target Year:** 2021 **Value:** Yes **Target Year:** 2020 **Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2020 **Source:** UN WOMEN | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  265,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  60,000.00 (non-core) | 0.00 (core)  325,000.00 (non-core) |
| **Output 3.1.4 Gender equitable social norms, attitudes and behaviours change at the community and individual levels to prevent VAWG/SGBV/HP and promote womens and girls sexual and reproductive health rights** | **Indicator 3.1.4A:** Number (By age and sex) of persons who are trained and engaged to protect and promote women's and girl's rights to avoid harmfull practicies **Targets:  Value:** 3000 **Target Year:** 2021 **Value:** 3000 **Target Year:** 2020 **Value:** 1000 **Target Year:** 2022 **Baseline:  Value:** 3700 **Year:** 2021 **Source:** UN WOMEN REPORT | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  232,052.00 (non-core) | 0.00 (core)  232,052.00 (non-core) | 0.00 (core)  70,000.00 (non-core) | 0.00 (core)  534,104.00 (non-core) |
| **Output 3.1.5 Women and girls who experience violence and harmful practices use available, accessible, acceptable, and quality essential services including for long term recovery from violence** | **Indicator 3.1.5A:** Number of women and girls who benefic one form of holestic care provided services supported by UNWomen **Targets:  Value:** 40 **Target Year:** 2021 **Value:** 40 **Target Year:** 2020 **Value:** 40 **Target Year:** 2022 **Baseline:  Value:** 40 **Year:** 2021 **Source:** REGISTER  **Indicator 3.1.5B:** proportion of women and girls survivors supported who are refered for a legal support **Targets:  Value:** 50% **Target Year:** 2021 **Value:** 50% **Target Year:** 2020 **Value:** 50% **Target Year:** 2022 **Baseline:  Value:** TBM **Year:** 2020 **Source:** Register | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  222,640.00 (non-core) | 0.00 (core)  222,640.00 (non-core) | 0.00 (core)  250,000.00 (non-core) | 0.00 (core)  695,280.00 (non-core) |
| **Output 3.1.7 Women's and girl's rights organizations and civil society, including those representing young people and groups facing cross-forms of discrimination/marginalization, influence and make More effectively advancing gender equality, empowering women and girls and contributing to the elimination of violence against them** | **Indicator 3.1.7A:** platform of women leaders is established and advocates for EVAWG/SGBV/HP **Targets:  Value:** yes **Target Year:** 2021 **Value:** Yes **Target Year:** 2020 **Value:** YES **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2021 **Source:** Report Platform  **Indicator 3.1.7B:** Number of advacacy activities on EVAWG/SGBV/HP supported by the platform **Targets:  Value:** 5 **Target Year:** 2021 **Value:** 5 **Target Year:** 2021 **Value:** 5 **Target Year:** 2021 **Value:** 3 **Target Year:** 2020 **Value:** 2 **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2020 **Source:** Report platform | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  222,640.00 (non-core) | 0.00 (core)  222,640.00 (non-core) | 0.00 (core)  533,053.00 (non-core) | 0.00 (core)  978,333.00 (non-core) |
| **Output 3.1.8 Spotlight Programme Management cost (PMC)** | **Indicator 3.1.8A:** ameliorate the capacity of delivery on the program Spotlight **Targets:  Value:** High **Target Year:** 2021 **Value:** high **Target Year:** 2020 **Value:** High **Target Year:** 2022 **Baseline:  Value:** Medium **Year:** 2020 **Source:**  Rapport financier Spotligh | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  670,874.00 (non-core) | 0.00 (core)  705,369.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,376,243.00 (non-core) |
| **Output 3.1.9 Quality, disaggregated and globally comparable data on different forms of violence against women and girls and harmful practices are collected, analyzed and used in accordance with international standards to inform laws, policies and programs.** | **Indicator 3.1.9A:** existence of a report on gender and policies **Targets:  Value:** Yes **Target Year:** 2022 **Baseline:  Value:** NO **Year:** 2021 **Source:** UN WOMMEN ANNUAL REPORT | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  72,857.00 (non-core) | 0.00 (core)  72,857.00 (non-core) |
| **Outcome 3.2 Increased access to essential services  Related SP Outcome/Output:**   **Indicator 3.2A:** Increased access to essential services **Targets:  Value:** 18500 **Notes:** Access to essential services **Target Year:** 2019 **Baseline:  Value:** 0 SURVIVOR **Year:** 2018 **Note:** Access to essential services **Source:** Annual report  **Indicator 3.2B:** Number of survivors of violence from 18 years old trained on how to use the kit and how to make their own and supported with a provide socio-economic kits, or menstrual hygiene management kits **Targets:  Value:** 100 **Target Year:** 2022 **Baseline:  Value:** 120 **Year:** 2022 **Source:** UN Women report | **Output 3.2.1 Women’s voice and agency strengthened to advocate to improve women's acces to quality health services** | **Indicator 3.2.1A:** umber of women, girls and men supported with a socio economic ,dignity kits NFI or Managing menstrual hygiene kits **Targets:  Value:** 2000 **Target Year:** 2021 **Value:** 2000 **Target Year:** 2020 **Value:** 100 **Target Year:** 2022 **Baseline:  Value:** 200 **Year:** 2019 **Source:** Un Women contry office reporting  **Indicator 3.2.1B:** Number of midwives trained in communication techniques for a better reception of women in labor in maternity hospitals; **Targets:  Value:** 40 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Un Women contry office reporting  **Indicator 3.2.1C:** n operational monitoring framework for the implementation of activities is produced and put in place **Targets:  Value:** Yes **Target Year:** 2022 **Baseline:  Value:** NO **Year:** 2022 **Source:** UN Women annual report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  105,880.00 (non-core) | 0.00 (core)  113,400.00 (non-core) | 0.00 (core)  120,000.00 (non-core) | 0.00 (core)  339,280.00 (non-core) |
| **Output 3.2.2 Girls voice , goverment and agencies strengthened to advocate to improve girls's acces to quality education services** | **Indicator 3.2.2A:** Existing of a update performance measurement framework for the implementation of the project PAEF **Targets:  Value:** Yes **Target Year:** 2022 **Baseline:  Value:** NO **Year:** 2021 **Source:** Management unit of the project   **Indicator 3.2.2B:** Number of knowledge and communication supports ( event reports, media reports and  press releases, photos, videos, success stories,) **Targets:  Value:** 10 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2011 **Source:** UN WOMEN KM center | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  114,160.00 (non-core) | 0.00 (core)  114,160.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  2,126,379.00 (non-core) | 0.00 (core)  1,895,874.00 (non-core) | 0.00 (core)  1,137,037.00 (non-core) | 0.00 (core)  5,159,290.00 (non-core) |
| **Total Resources for outcome 3.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  105,880.00 (non-core) | 0.00 (core)  113,400.00 (non-core) | 0.00 (core)  234,160.00 (non-core) | 0.00 (core)  453,440.00 (non-core) |
| **Total Resources for impact area 3** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  2,232,259.00 (non-core) | 0.00 (core)  2,009,274.00 (non-core) | 0.00 (core)  1,371,197.00 (non-core) | 0.00 (core)  5,612,730.00 (non-core) |
| **Impact4 Women and girls contribute to, and have influence in, building sustainable peace and resilience and benefit equally from the prevention of conflicts and disasters, and from humanitarian action.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Strategic Priority : Governance, Peace and Security  By 2021, Niger has improved its political, economic, administrative, judicial and security governance, accelerated its diversification and structural transformation for more inclusive and resilient growth and a reduction in gender inequalities. By 2021, management of development and statistical data at all levels; cross-border and community security as well as the judicial system are improved and guarantee human rights with institutions capable of leading democratic processes and local authorities capable of meeting the specific needs of the most vulnerable groups. The following outputs: Output 2.2: Targeted communities and institutions responsible for cross-border and domestic security have the capacity to prevent and mitigate threats, promote social cohesion and consolidate peace and stability • Output 2.3: Judicial and human rights institutions have the capacity to ensure access for the most vulnerable to effective just  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 4.1 Outcome 5: Women participate in and inform decision-making processes & responses related to conflict prevention, protection and peacebuilding in Niger  Related SP Outcome/Output:**   **Indicator 4.1A:** % of gender sensitive projects posted at OPS **Targets:  Value:** 50% **Target Year:** 2018 **Baseline:  Value:** TBD **Year:** 2017 **Source:** OCHA OPS  **Indicator 4.1B:** Number of quick impact income generating activities still functional **Targets:  Value:** 350 **Target Year:** 2018 **Baseline:  Value:** 350 **Year:** 2017 **Note:** fField visits will be made to follow up activities of the previous project on gender and humanitarian actions **Source:** UN Women reports  **Indicator 4.1C:** Number of survivors still accessing holistic services **Targets:  Value:** 5000 **Target Year:** 2018 **Baseline:  Value:** 5000 **Year:** 2017 **Source:** UN Women field reports  **Indicator 4.1D:** Number of Women and young girls whose have effectively access to mental health and psychosocial support **Targets:  Value:** 20 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women and RP report | **Output 4.1.10 Needs and Interests of Women affected by conflicts are adressed/** | **Indicator 4.1.10A:** number of Women trained to be resilient **Targets:  Value:** 400 **Target Year:** 2021 **Value:** 400 **Target Year:** 2022 **Baseline:  Value:** 400 **Year:** 2020 **Source:** UN Women Niger report  **Indicator 4.1.10B:** number for Women organizations strengthened on management of conflicts and COVID-19 impacts **Targets:  Value:** 2 **Target Year:** 2021 **Value:** 20 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women annual report   **Indicator 4.1.10C:** UN Women annual report indicator Indicator 4.1.10 C: Number of advocacy activities with defence and security forces **Targets:  Value:** 2 **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2021 **Source:** UN Women annual report  **Indicator 4.1.10D:** : Number of women and girl victims who have acces to mental health and psychosocial assistance **Targets:  Value:** 200 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** the final Evaluation report of the project | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  543,107.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,887,500.00 (non-core) | 0.00 (core)  2,430,607.00 (non-core) |
| **Output 4.1.11 Women improve social cohesion and participate in local governance** | **Indicator 4.1.11A:** number of women mediators, victims of conflicts and GBV who benefit new economic opportunities **Targets:  Value:** 200 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:**  UN Women Niger country   **Indicator 4.1.11B:** number of women mediators trained in leadership and local governance **Targets:  Value:** 40 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2022 **Source:** UN Women Niger annual report    **Indicator 4.1.11C:** number of advocacy activities organized with traditional autorities and political actors **Targets:  Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2022 **Source:** UN Women Niger annual report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  305,000.00 (non-core) | 0.00 (core)  161,250.00 (non-core) | 0.00 (core)  466,250.00 (non-core) |
| **Output 4.1.9 Women have more active roles in conflict prevention and peacebuilding** | **Indicator 4.1.9A:** number of women in deployment reserves **Targets:  Value:** 1 **Target Year:** 2021 **Value:** 100 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women Niger country   **Indicator 4.1.9B:** number of women trained to prevent and taking care of GBV **Targets:  Value:** 4 **Target Year:** 2021 **Value:** 40 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women Niger annual report   **Indicator 4.1.9C:** number of vulnerable women and girls sensitized against radicalization and violent extremism **Targets:  Value:** 1000 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN WOMEN annual report   **Indicator 4.1.9D:** number of gender sensitive policy adopted by armed forces **Targets:  Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women Niger annual report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,148,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,139,439.00 (non-core) | 0.00 (core)  2,287,439.00 (non-core) |
| **Outcome 4.2 Humanitarian /crisis response planning, frameworks & programming are gender inclusive and responsive  Related SP Outcome/Output:**   **Indicator 4.2A:** Women's engagement i n peace building **Targets:  Value:** 2 gender responsive land ordinances **Notes:** Gender responsive lantenure **Target Year:** 2019 **Baseline:  Value:** 0 gender responsive land ordinances **Year:** 2018 **Note:** Women's engagement in peace buidling **Source:** PBF Report  **Indicator 4.2B:** Women mediators trained **Targets:  Value:** 600 **Notes:** Women trained as mediators **Target Year:** 2019 **Baseline:  Value:** 0 **Year:** 2018 **Note:** Number of Women trained as mediators **Source:** PBF Report  **Indicator 4.2C:** Reduced abuse of women and girls in the Niger Mali frontiers **Targets:  Value:** 10% reduction **Target Year:** 2019 **Baseline:  Value:** TBD **Year:** 2018 **Note:** Reduction in abuses **Source:** PBF report  **Indicator 4.2D:** Number of social cohesion spaces for women functional in crisis areas whose provided services to women **Targets:  Value:** 3 **Target Year:** 2022 **Baseline:  Value:** 8 **Year:** 2020 **Source:** UN Women report | **Output 4.2.1 Women cohesion spaces are functional in refugee sites and high concentration zones in Niger** | **Indicator 4.2.1A:** Number of new Cohesion spaces created and functional **Targets:  Value:** 6 **Target Year:** 2022 **Value:** 6 **Target Year:** 2021 **Baseline:  Value:** 8 **Year:** 2021 **Source:** UNW partner report   **Indicator 4.2.1B:** Number of social issues covered by the existing COGES (leadership, management of space, SGBV etc) **Targets:  Value:** 15 **Target Year:** 2021 **Value:** 15 **Target Year:** 2021 **Value:** 15 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2020 **Source:** UNW partner report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  180,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  475,380.00 (non-core) | 0.00 (core)  161,250.00 (non-core) | 0.00 (core)  816,630.00 (non-core) |
| **Output 4.2.5 National, UN and Aid coordination mechanisms strengthened to identify, address and monitor the needs of women and girls for effective response during and post disaster** | **Indicator 4.2.5A:** Exitence of a functional mechanism for collection and analyssis of data **Targets:  Value:** yes **Target Year:** 2021 **Value:** Yes **Target Year:** 2020 **Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2019 **Source:** Report Unw Niger   **Indicator 4.2.5B:** Number of stakeholders trained to conduct the PDNA exercise **Targets:  Value:** 20 **Target Year:** 2021 **Value:** 20 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UNW Niger annual report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  32,000.00 (non-core) | 0.00 (core)  82,000.00 (non-core) |
| **Output 4.2.6 New sources of Income and economic opportunities created for women and girls through targeted education & development of capacities/skills** | **Indicator 4.2.6A:** Number of Women who have diversified skills to generate income **Targets:  Value:** 3 **Target Year:** 2021 **Value:** yes **Target Year:** 2021 **Value:** 250 **Target Year:** 2020 **Value:** 20 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2020 **Source:** Report Unw Niger   **Indicator 4.2.6B:** Number of women s groups who set up market linkage for sustained income **Targets:  Value:** 90 **Target Year:** 2021 **Value:** 20 **Target Year:** 2022 **Baseline:  Value:** 240 **Year:** 2020 **Source:** UNW annual report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  50,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  58,211.00 (non-core) | 0.00 (core)  108,211.00 (non-core) |
| **Outcome 4.4 An enabling environment for implementation of WPS commitments is created in Niger  Related SP Outcome/Output:**   **Indicator 4.4A:** Existence of an operational framework for the implementation and monitoring-evaluation of the new NAP **Targets:  Value:** yes **Notes:** Ministry of gender report **Target Year:** 2022 **Baseline:  Value:** NO **Year:** 2021 **Source:** Ministry of gender report | **Output 4.4.2 Accountability frameworks exists for the implementation of the UN WPS agenda** | **Indicator 4.4.2A:** Number of reports elaborated and published on the NAP  Target: Year: 2022 Value: 1  Baseline: Year: 2021 Value: 0 Source: **Targets:  Value:** 1 **Target Year:** 2021 **Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women Niger annual report   **Indicator 4.4.2B:** existence of a monitoring and evaluation systemt for NAP **Targets:  Value:** yes **Target Year:** 2021 **Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2021 **Source:** UN Women annual report   **Indicator 4.4.2C:** Number of knowledge and communication supports ( event reports, media reports and  press releases, photos, videos, success stories,) **Targets:  Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Wmen partners report on NAP | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  400,000.00 (non-core) | 0.00 (core)  400,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  800,000.00 (non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,691,107.00 (non-core) | 0.00 (core)  305,000.00 (non-core) | 0.00 (core)  3,188,189.00 (non-core) | 0.00 (core)  5,184,296.00 (non-core) |
| **Total Resources for outcome 4.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  180,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  475,380.00 (non-core) | 0.00 (core)  251,461.00 (non-core) | 0.00 (core)  1,006,841.00 (non-core) |
| **Total Resources for outcome 4.4 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  400,000.00 (non-core) | 0.00 (core)  400,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  800,000.00 (non-core) |
| **Total Resources for impact area 4** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  180,000.00 (non-core) | 0.00 (core)  2,191,107.00 (non-core) | 0.00 (core)  1,180,380.00 (non-core) | 0.00 (core)  3,439,650.00 (non-core) | 0.00 (core)  6,991,137.00 (non-core) |
| **Impact1 Women fully and equally participate in leadership and decision-making and women and girls benefit from gender responsive governance.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Effect 3. By 2021, women and youth/adolescents in targeted areas will benefit from viable economic opportunities, acquire skills and skills necessary for their empowerment, and participate in decision-making and promotion processes practices aimed at eliminating gender-based inequality and violence, including child marriage. Implementing Partner: unwomen  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 1.1 Women’s leadership and political participation is promoted in the democratic governance system in Niger  Related SP Outcome/Output:**   **Indicator 1.1A:** Number of Women leaders, political leaders, authorities trained on gender responsive planning and budgeting plan at national and local level **Targets:  Value:** 500 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women and RP reports   **Indicator 1.1B:** Existing of a modernized online database of women's competencies that can be accessed by anyone at any time and that can be updated. **Targets:  Value:** yes **Target Year:** 2022 **Baseline:  Value:** NO **Year:** 2021 **Source:** website | **Output 1.1.1 Strengthen the technical capacity of women to competing for political and leadership positions.** | **Indicator 1.1.1A:** The implementation decree is in place and implemented **Targets:  Value:** yes **Target Year:** 2021 **Value:** Yes **Target Year:** 2020 **Baseline:  Value:** No **Year:** 2019 **Source:** decree of the quotas Low  **Indicator 1.1.1B:** Exitence of a functional mechanism for collection and analyssis of data **Targets:  Value:** yes **Target Year:** 2021 **Baseline:  Value:** No **Year:** 2020 **Source:** Ceni report   **Indicator 1.1.1C:** % of political partis who have effectively applied the quota law for administrative position. **Targets:  Value:** 25% **Target Year:** 2021 **Baseline:  Value:** 0% **Year:** 2021 **Source:** UNW annual report   **Indicator 1.1.1D:** Number of youth and women leaders and their organisation trained in the incubation rooms and number of incubation rooms created **Targets:  Value:** 40 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women NIGER and partner report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 37,000.00 (core)  35,000.00 (non-core) | 65,000.00 (core)  150,000.00 (non-core) | 30,000.00 (core)  60,000.00 (non-core) | 132,000.00 (core)  245,000.00 (non-core) |
| **Output 1.1.2 The capacities of key administrative authorities (local and national) are strengthened on the gender budget** | **Indicator 1.1.2A:** % of elected women trained on their mandate **Targets:  Value:** 100% **Target Year:** 2021 **Value:** 100% **Target Year:** 2021 **Value:** Yes **Target Year:** 2020 **Baseline:  Value:** 0% **Year:** 2020 **Source:** UN Women progress reports  **Indicator 1.1.2B:** %of elected woment parlementarian trained on gender responsive Budget **Targets:  Value:** 100% **Target Year:** 2021 **Value:** 500 **Target Year:** 2020 **Value:** 100 **Target Year:** 2020 **Baseline:  Value:** 0% **Year:** 2020 **Source:** UN WOMEN report  **Indicator 1.1.2C:** Number of documentation or communication produced broadcasts produce and disseminate on the spots of women participation in the electoral process (in french and local languages) **Targets:  Value:** 4 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2022 **Source:** UN WOMEN REPORT   **Indicator 1.1.2D:** Number of local and national autorities and elected women and girls trained on gender budget **Targets:  Value:** TBM **Target Year:** 2022 **Baseline:  Value:** TBM **Year:** 2021 **Source:**  MPFPE reports, unwomen reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 10,000.00 (core)  25,000.00 (non-core) | 35,000.00 (core)  250,000.00 (non-core) | 0.00 (core)  45,000.00 (non-core) | 45,000.00 (core)  320,000.00 (non-core) |
| **Output 1.1.5 gender-sensitive data is collected in the area of entrepreneurship and political participation for knowledge management and policy development** | **Indicator 1.1.5A:** A quality assessment of existing mechanisms and the gaps thereof **Targets:  Value:** yes **Target Year:** 2021 **Value:** 6 **Target Year:** 2022 **Baseline:  Value:** no **Year:** 2020 **Source:** UN Women NIGER assessment report   **Indicator 1.1.5B:** Number of Knowledge products generated and shared for policy dialogue initiatives (in french and local languages) **Targets:  Value:** 6 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women Niger annual and knowledge center    **Indicator 1.1.5C:** existing of a modernized online database of women's competencies **Targets:  Value:** yes **Target Year:** 2022 **Baseline:  Value:** no **Year:** 2021 **Source:** Website | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  57,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  57,000.00 (non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 47,000.00 (core)  60,000.00 (non-core) | 100,000.00 (core)  457,000.00 (non-core) | 30,000.00 (core)  105,000.00 (non-core) | 177,000.00 (core)  622,000.00 (non-core) |
| **Total Resources for impact area 1** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 47,000.00 (core)  60,000.00 (non-core) | 100,000.00 (core)  457,000.00 (non-core) | 30,000.00 (core)  105,000.00 (non-core) | 177,000.00 (core)  622,000.00 (non-core) |