

UN Women Strategic Note 2022-2025

**UN WOMEN Somalia COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact4  Women and girls contribute to, and have influence in, building sustainable peace and resilience and benefit equally from the prevention of conflicts and disasters, and from humanitarian action** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNCF Result 2: Security and Rule of Law (UNW SP Impact 4) Related national development priorities:** | | | | | |
|  |  |  | **Year 2022** | **Year 2023** | **Year 2024** | **Year 2025** | **Total** |
| **Outcome 4.2 Respect, protection, and promotion of human rights, gender equality, tolerance, climate security, and environmental governance would be sustained by strengthened Security and Rule of Law institutions and improved accountability mechanisms and legal frameworks  Related SP Outcome/Output:**   **Indicator 4.2A:** Proportion of the population who have experienced a dispute in the past two years and who accessed a formal or informal dispute resolution mechanism, by type of mechanism and disaggregated by gender and displacement status (Indicator A of UNCF Outcome 2.1) **Targets:  Value:** 700 **Target Year:** 2025 **Baseline:  Value:** 500 **Year:** 2021 **Source:** Annual reports  **Indicator 4.2B:** Proportion of citizens who believe that decision-making processes are inclusive and that government is responsive to citizens’ needs (Indicator C of UNCF Outcome 1.2) **Targets:  Value:** 1000 **Target Year:** 2025 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Annual Reports | **Output 4.2.1 Capacity and gender-responsiveness of the existing rule of law and security sector institutions improved, particularly in handling cases of conflict-related sexual violence (CRSV)** | **Indicator 4.2.1A:** % Budget allocated to relevant FGS and FMS institutions, including MOWHRD, other justice-sector institutions to address conflict-related sexual and gender-based violence **Targets:  Value:** 10% **Target Year:** 2022 **Value:** 10% **Target Year:** 2025 **Value:** 10% **Target Year:** 2024 **Value:** 10% **Target Year:** 2024 **Value:** 10% **Target Year:** 2024 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Reports | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  97,293.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  197,293.00 (non-core) |
| **Output 4.2.2 Women-led conflict early-warning system and preparedness plans developed and operationalized.** | **Indicator 4.2.2A:** # Community-level early warning mechanisms in place **Targets:  Value:** 2 **Target Year:** 2019 **Value:** 6 **Target Year:** 2020 **Value:** 3 **Target Year:** 2022 **Value:** 3 **Target Year:** 2025 **Baseline:  Value:** 0 **Year:** 2021 **Notes:** As per UN Women and Line Ministry Progress Reports **Source:** Progress reports  **Indicator 4.2.2B:** # Capacity development and refresher trainings for CSOs, government stakeholders on early warning mechanisms conducted. **Targets:  Value:** 1 **Target Year:** 2019 **Value:** 5 **Target Year:** 2020 **Value:** 18 **Target Year:** 2022 **Value:** 18 **Target Year:** 2025 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Progress reports | 0.00 (core)  199,495.00 (non-core) | 0.00 (core)  149,192.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  348,687.00 (non-core) |
| **Output 4.2.3 More justice institutions are accessible to and deliver for women and girls** |  | 0.00 (core)  40,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  140,000.00 (non-core) |
| **Outcome 4.5 UN SYSTEM COORDINATION FOR GENDER EQUALITY  Related SP Outcome/Output:**   **Indicator 4.5A:** a. Proportion of seats held by women in (a) Federal and (b) Federal Member State parliaments (Indicator A of UNCF Outcome 1.2) **Targets:  Value:** 30% **Target Year:** 2023 **Baseline:  Value:** 24% **Year:** 2021 **Source:** 2022 elections reports in Somalia | **Output 4.5.1 The UN system coherently and systematically contributes to progress on gender equality and the empowerment of women and girls** |  | 32,000.00 (core)  2,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 32,000.00 (core)  2,000.00 (non-core) |
| **Output 4.5.2 Changes attributed to UN-Women in skills or abilities and capacities of individuals or institutions and/or the availability of new products and services contributing to UN system coordination for gender equality** |  | 17,000.00 (core)  5,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 17,000.00 (core)  5,000.00 (non-core) |
| **Total Resources for outcome 4.2 (core and non-core)** | | | 0.00 (core)  339,495.00 (non-core) | 0.00 (core)  346,485.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  685,980.00 (non-core) |
| **Total Resources for outcome 4.5 (core and non-core)** | | | 49,000.00 (core)  7,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 49,000.00 (core)  7,000.00 (non-core) |
| **Total Resources for impact area 4** | | | 49,000.00 (core)  346,495.00 (non-core) | 0.00 (core)  346,485.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 49,000.00 (core)  692,980.00 (non-core) |
| **Impact2  Women fully and equally participate in leadership and decision making and women and girls benefit from gender-responsive governance** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNCF Result area 1 Inclusive, Accountable Politics & Reconciliation (UNW SP Impact 1) Related national development priorities:** | | | | | |
|  |  |  | **Year 2022** | **Year 2023** | **Year 2024** | **Year 2025** | **Total** |
| **Outcome 2.1 Somalis, particularly women and female youth, benefit from and participate in functional, inclusive, accountable and transparent democratic systems across all levels of government and governmental institutions  Related SP Outcome/Output:** | **Output 2.1.1 Inclusive and responsive infrastructures for peace to support women’s participation and leadership in national and local level peace processes are established** |  | 0.00 (core)  440,000.00 (non-core) | 0.00 (core)  208,128.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  648,128.00 (non-core) |
| **Output 2.1.2 Operationalization of NAP on UNSCR 1325 to promote women’s meaningful participation in peacebuilding at the national and local levels.** |  | 0.00 (core)  557,362.00 (non-core) | 0.00 (core)  264,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  821,362.00 (non-core) |
| **Output 2.1.3 Women leaders, peace networks, and forums (Hayaanka Nabadda-Hope for Peace Networks) were established to engage in peace mediation, reconciliation, and social cohesion at community levels** |  | 0.00 (core)  261,000.00 (non-core) | 0.00 (core)  232,662.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  493,662.00 (non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | | | 0.00 (core)  1,258,362.00 (non-core) | 0.00 (core)  704,790.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,963,152.00 (non-core) |
| **Total Resources for impact area 2** | | | 0.00 (core)  1,258,362.00 (non-core) | 0.00 (core)  704,790.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  1,963,152.00 (non-core) |
| **Impact5 Women have income security, decent work, and economic autonomy** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNCF result 3- Economic Development Related national development priorities:** | | | | | |
|  |  |  | **Year 2022** | **Year 2023** | **Year 2024** | **Year 2025** | **Total** |
| **Outcome 5.1 Outcome A: An integrated national programme for human capital development is established, increasing access to market-based skills for all – including the most marginalized and vulnerable groups – and safeguarding their rights  Related SP Outcome/Output:**   **Indicator 5.1A:** Vulnerable employment among women (Indicator C of UNCF outcome 3.3) **Targets:  Value:** 1000 **Target Year:** 2025 **Baseline:  Value:** 600 **Year:** 2021 **Source:** Annual Reports | **Output 5.1.1 Output 3.1.Crisis-affected and at-risk women have enhanced access to livelihood skills, training, tools, and technologies in relation to climate-smart agriculture** |  | 0.00 (core)  60,000.00 (non-core) | 0.00 (core)  500,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  560,000.00 (non-core) |
| **Output 5.1.2 Output 3.2: Women micro and small entrepreneurs are supported to set up and improve their operations in agriculture and non-agricultural sectors** |  | 0.00 (core)  70,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  70,000.00 (non-core) |
| **Output 5.1.3 Output 3.3: Women’s access to savings and credit is enhanced** |  | 0.00 (core)  125,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  125,000.00 (non-core) |
| **Outcome 5.2 Outcome B: An integrated national programme for human capital development is established, increasing access to market-based skills for all – including the most marginalized and vulnerable groups – and safeguarding their rights  Related SP Outcome/Output:** | **Output 5.2.1 Output 5.1: Initiatives promoting positive gender norms in support of women's leadership and protection from violence are scaled up with the support of humanitarian actors** |  | 0.00 (core)  24,000.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  124,000.00 (non-core) |
| **Output 5.2.2 Output 5.2: Refugee, IDP women and women in host communities have increased capacities and skills to participate in and lead settlement management and local decision-making processes** |  | 0.00 (core)  10,000.00 (non-core) | 0.00 (core)  60,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  70,000.00 (non-core) |
| **Total Resources for outcome 5.1 (core and non-core)** | | | 0.00 (core)  255,000.00 (non-core) | 0.00 (core)  500,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  755,000.00 (non-core) |
| **Total Resources for outcome 5.2 (core and non-core)** | | | 0.00 (core)  34,000.00 (non-core) | 0.00 (core)  160,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  194,000.00 (non-core) |
| **Total Resources for impact area 5** | | | 0.00 (core)  289,000.00 (non-core) | 0.00 (core)  660,000.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  949,000.00 (non-core) |