

UN Women Strategic Note 2022-2025

**UN WOMEN Serbia COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact3 All women and girls live a life free from all forms of violence** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: United Nations Sustainable Development Cooperation Framework Result 2: Well-being, social equity and the human potential are at the heart of systems, policies and practices; Outcome 2.1. : Universal and inclusive access to quality health, social and protection services is improved  Related national development priorities:** | | | | | |
|  |  |  | **Year 2022** | **Year 2023** | **Year 2024** | **Year 2025** | **Total** |
| **Outcome 3.1 Universal and inclusive access to quality health, social and protection services is improved (UNSDCF Outcome 2.1.)  Related SP Outcome/Output:**   **Indicator 3.1A:** Number of laws, policies and procedures that are amended to enable services for women who survived violence are fully aligned with key provisions set in IC and CEDAW **Targets:  Value:** 5 **Target Year:** 2021 **Value:** 6 **Target Year:** 2022 **Value:** 7 **Target Year:** 2023 **Baseline:  Value:** 5 **Year:** 2021 **Source:** UN Women Projects reports, Evaluation reports, Interviews with Beneficiaries. | **Output 3.1.1 General and specialist service providers have knowledge to effectively deliver integrated service for protection of women and girls survivors of violence.** | **Indicator 3.1.1A:** Number of fully functional Centers for VAWG Victims **Targets:  Value:** 6 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2021 **Source:** UN Women Project reports, Government partner reports   **Indicator 3.1.1C:** Number of case conferences organized **Targets:  Value:** 40 **Target Year:** 2021 **Value:** 40 **Target Year:** 2022 **Baseline:  Value:** 20 **Year:** 2019 **Source:** UN Women Project reports, Government partner reports | 0.00 (core)  261,400.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  261,400.00 (non-core) |
| **Output 3.1.2 Woman’s NGO have knowledge and skills to provide services to women and girls victims of violence.** | **Indicator 3.1.2A:** Number of supported NGOs/networks of women's civil society organizations, including those representing women from disadvantaged groups, that provide services to women and girls victims of violence **Targets:  Value:** 15 **Target Year:** 2020 **Value:** 17 **Target Year:** 2021 **Value:** 19 **Target Year:** 2022 **Value:** 21 **Target Year:** 2023 **Baseline:  Value:** 10 **Year:** 2019 **Source:** UN Women Project reports, Women’s NGOs reports  **Indicator 3.1.2B:** Number of specialist service providers with increased knowledge and/or capacity to manage cases in line with international standards **Targets:  Value:** 7 **Target Year:** 2021 **Value:** 20 **Target Year:** 2023 **Value:** 14 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women Project reports, Women’s NGOs reports | 0.00 (core)  259,999.00 (non-core) | 0.00 (core)  142,184.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  402,183.00 (non-core) |
| **Output 3.1.3 The Ministry of Justice and Human and Minority Rights of Government of Montenegro, Commissioner for Protection of Equality, women CSOs and media have increased capacities to combat gender-based discrimination, stereotypes and violence against women and girls in targeted communities.** | **Indicator 3.1.3A:** Number of Women CSOs supported by the Project **Targets:  Value:** 3 **Target Year:** 2020 **Value:** 6 **Target Year:** 2021 **Value:** 10 **Target Year:** 2022 **Value:** 6 **Target Year:** 2022 **Value:** 5 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2019 **Source:** UN Women Project reports, CSO reports   **Indicator 3.1.3B:** Number of women and girls reached by outreach programmes and awareness raising activities **Targets:  Value:** 1500 **Target Year:** 2021 **Value:** 3000 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** UN Women Project reports, Government partner reports | 0.00 (core)  759,500.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  759,500.00 (non-core) |
| **Output 3.1.4 National and local authorities have knowledge and skills to prevent and respond to gender-based violence against women and girls, in public and private spaces and to improve accessibility of services.** | **Indicator 3.1.4A:** National survey on safety of public places for women and girls, including prevalence of sexual harassment, stalking and sexual violence conducted **Targets:  Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** National Survey  **Indicator 3.1.4B:** Number of representatives of local authorities and stakeholders (including women CSOs) mentored to use tailored tool for responding to VAGW in public domain **Targets:  Value:** 3 **Target Year:** 2022 **Value:** 5 **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Reports  **Indicator 3.1.4C:** Number of national measures to prevent and respond to violence against women and girls in public spaces drafted **Targets:  Value:** 2 **Target Year:** 2022 **Value:** 5 **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2021 **Source:** National measures  **Indicator 3.1.4D:** Number of cities/municipalities that have assessed women and girl’s public safety concerns using tailored tool **Targets:  Value:** 2 **Target Year:** 2022 **Value:** 5 **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Assessments  **Indicator 3.1.4E:** Number of service providers (providing shelters) supported to increase performance/increase capacity **Targets:  Value:** 3 **Target Year:** 2022 **Value:** 7 **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Performance or capacity assessment | 0.00 (core)  514,470.00 (non-core) | 0.00 (core)  214,405.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  728,875.00 (non-core) |
| **Outcome 3.2 UN system is accountable to measure, monitor and drive progress towards the achievement of gender equality and the empowerment of women.  Related SP Outcome/Output:**   **Indicator 3.2A:** Capacity building and gender related inputs provided to UNCT **Targets:  Value:** yes **Target Year:** 2022 **Value:** yes **Target Year:** 2023 **Value:** yes **Target Year:** 2022 **Value:** yes **Target Year:** 2023 **Baseline:  Value:** yes **Year:** 2021 **Source:** Training reports, meeting minutes | **Output 3.2.1 UN Women effectively leads, coordinates and promotes accountability for the implementation of gender equality commitments across the UN system in Serbia** | **Indicator 3.2.1A:** UNSDCF 2021-2025 features gender results **Targets:  Value:** yes **Target Year:** 2022 **Value:** yes **Target Year:** 2023 **Baseline:  Value:** yes **Year:** 2021 **Source:** UNSDCF JWPs, Annual Result Reports, UN Info  **Indicator 3.2.1B:** Percentage of UNCT Gender Scorecard recommendations implemented by UNCT **Targets:  Value:** 85 **Target Year:** 2022 **Value:** 85 **Target Year:** 2023 **Baseline:  Value:** 85 **Year:** 2021 **Source:** UNCT SWAP GE Scorecard Reports and Action Plans  **Indicator 3.2.1C:** Number of GTG Meetings **Targets:  Value:** 4 **Target Year:** 2022 **Value:** 4 **Target Year:** 2023 **Baseline:  Value:** 4 **Year:** 2021 **Source:** GTG Meeting Minutes, GTG TOT | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 0.00 (core)  1,795,369.00 (non-core) | 0.00 (core)  356,589.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  2,151,958.00 (non-core) |
| **Total Resources for outcome 3.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) |
| **Total Resources for impact area 3** | | | 0.00 (core)  1,795,369.00 (non-core) | 0.00 (core)  356,589.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  2,151,958.00 (non-core) |
| **Impact1 Governance and Participation in Public Life** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: United Nations Sustainable Development Cooperation Framework 2021-20215 Result 3 Building trust and mutual accountability through the rule of law, rights and duties agenda Outcome 3.1 All people, especially the more vulnerable, benefit from the realization of human rights, gender equality, social cohesion and enhanced rule of law in line with international commitments  Related national development priorities:** | | | | | |
|  |  |  | **Year 2022** | **Year 2023** | **Year 2024** | **Year 2025** | **Total** |
| **Outcome 1.1 All people, especially the more vulnerable, benefit from the realization of human rights, gender equality, social cohesion and enhanced rule of law in line with international commitments (UNSDCF Outcome 3.1)  Related SP Outcome/Output:**   **Indicator 1.1B:** Number of selected programmes, policies and budgets that include gender objectives and indicators **Targets:  Value:** 68 **Notes:** MV: Programmes, policies and budgets **Target Year:** 2021 **Value:** 61 **Notes:** MV: Programmes, policies and budgets **Target Year:** 2019 **Value:** 65 **Notes:** MV: Programmes, policies and budgets **Target Year:** 2020 **Value:** 72 **Target Year:** 2022 **Value:** 78 **Target Year:** 2023 **Baseline:  Value:** 47 **Year:** 2018 **Note:** MV: Programmes, policies and budgets **Source:** Programmes, policies and budgets  **Indicator 1.1E:** Number of the EU Sector Planning Documents that are gender mainstreamed and/or have gender specific sections **Targets:  Value:** 5 **Notes:** MV: EU Sector Planning Documents **Target Year:** 2021 **Value:** 3 **Target Year:** 2020 **Value:** 1 **Target Year:** 2019 **Value:** 5 **Target Year:** 2022 **Value:** 5 **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2018 **Note:** MV: EU Sector Planning Documents **Source:** EU Sector Planning Documents  **Indicator 1.1F:** Number of measures from the National Action Plan for Gender Equality implemented by women NGOs **Targets:  Value:** 25 **Target Year:** 2021 **Value:** 10 **Target Year:** 2019 **Value:** 20 **Target Year:** 2020 **Value:** 25 **Target Year:** 2023 **Value:** 25 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2018 **Note:** MV: Annual Report on the implementation of the National Action Plan for Gender Equality **Source:** MV: Annual Report on the implementation of the National Action Plan for Gender Equality | **Output 1.1.1 Gender equality mechanisms, key national institutions and women' NGOs have knowledge and skills to fulfill their mandates and advance gender responsive governance and gender responsive budgeting.** | **Indicator 1.1.1A:** Number of budget users that integrated gender responsive budgeting in public finance management systems with UN-Women’s support. **Targets:  Value:** 65 **Target Year:** 2020 **Value:** 68 **Target Year:** 2021 **Value:** 72 **Target Year:** 2022 **Value:** 78 **Target Year:** 2023 **Baseline:  Value:** 54 **Year:** 2019 **Source:** UN Women Training Reports, UN Women Project Reports    **Indicator 1.1.1D:** Number of women benefiting from the support provided by women's NGOs related to implementation of measures on WE specified in the National Strategy for Gender Equality **Targets:  Value:** 2000 **Target Year:** 2019 **Value:** 2500 **Target Year:** 2020 **Value:** 3000 **Target Year:** 2021 **Value:** 4000 **Target Year:** 2022 **Value:** 4500 **Target Year:** 2023 **Baseline:  Value:** 1500 **Year:** 2018 **Source:** Report from NGOs, Project Cooperation Agreements     **Indicator 1.1.1E:** Change in knowledge of representatives from GEMs, key national institutions and women's NGOs on how to advance gender responsive governance. **Targets:  Value:** 30 **Target Year:** 2019 **Value:** 30 **Target Year:** 2020 **Value:** 30 **Target Year:** 2021 **Value:** 30 **Target Year:** 2022 **Value:** 30 **Target Year:** 2023 **Baseline:  Value:** 0 **Year:** 2018 **Source:** Project reports  **Indicator 1.1.1F:** Number of gender analysis/gender impact assessments performed to serve as basis for national strategic and IPA programming process **Targets:  Value:** 8 **Target Year:** 2021 **Value:** 10 **Target Year:** 2022 **Value:** 12 **Target Year:** 2023 **Baseline:  Value:** 6 **Year:** 2020 **Source:** Gender analysis | 0.00 (core)  1,517,612.00 (non-core) | 0.00 (core)  761,946.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  2,279,558.00 (non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | | | 0.00 (core)  1,517,612.00 (non-core) | 0.00 (core)  761,946.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  2,279,558.00 (non-core) |
| **Total Resources for impact area 1** | | | 0.00 (core)  1,517,612.00 (non-core) | 0.00 (core)  761,946.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  2,279,558.00 (non-core) |