

UN Women Strategic Note 2019-2022

**UN WOMEN South Sudan COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/10/2022

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact6 A comprehensive and dynamic set of norms, policies and standards on gender equality and empowerment of all women and girls is strengthened and implemented.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNCF: Priority Area 1: Building Peace and Strengthening Governance Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 6.1 Government of South Sudan fulfils international reporting obligations on CEDAW, Beijing Platform for Action, UNSCR 1325, Maputo Plan of Action and SDGs  Related SP Outcome/Output:**   **Indicator 6.1A:** # of Country Reports submitted to the UN and African Union on progress on gender equality in the implementation of CEDAW, Beijing Platform for Action, UNSC 1325, Maputo Plan of Action and SDGs **Targets:  Value:** 0 **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2021 **Source:** Government of South Sudan Reports, UN Women/UN agencies reports, Partners reports (e.g. IPs)  **Indicator 6.1B:** # of recommendations from South Sudan on women and girls’ empowerment, including on access to sexual and reproductive health and rights and GBV reflected in the annual Africa Position to Commission on Status of Women (CSW) **Targets:  Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Africa/South Sudan Position Papers to the annual Commission on the Status of Women through African   **Indicator 6.1C:** # of key principles of CEDAW, Beijing Platform for Action, UNCSR 1325, Maputo Plan of Action and SDGs that are included in the new Constitutional and legislative frameworks of South Sudan **Targets:  Value:** TBD **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2018 **Source:**  The new Constitutional and legislative frameworks of South Sudan | **Output 6.1.1 The Ministry of Gender, Child and Social Welfare and women organizations/CSOs are capacitated to systematically assess progress on implementation of CEDAW, Beijing Platform for Action, UNSCR 1325, Maputo Plan of Action and SDGs** | **Indicator 6.1.1A:** # of assessments conducted and/or progress reports produced on CEDAW/Beijing Platform for Action/UNSCR 1325/Maputo Plan of Action and SDGs with women organizations/CSOs **Targets:  Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2021 **Source:** Government Reports (e.g. Ministry of Gender)  **Indicator 6.1.1B:** # of women organizations/CSOs actively participating/involved in national reporting processes (CEDAW, Maputo, UNSCR 1325, Beijing Platform for Action, SDGs) **Targets:  Value:** 10 **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2021 **Source:** UN Women annual and assessment report , Government Reports (e.g. Ministry of Gender) | 0.00 (core)  530,963.00 (non-core) | 0.00 (core)  320,000.00 (non-core) | 0.00 (core)  270,000.00 (non-core) | 0.00 (core)  275,603.00 (non-core) | 0.00 (core)  1,396,566.00 (non-core) |
| **Output 6.1.2 The Ministry of Gender, Child and Social Welfare capacitated to present evidence-based positions on gender equality norms and standards** | **Indicator 6.1.2B:** # of position papers developed by the Ministry of Gender, Child and Social Welfare informed by key normative frameworks, targeting the advancement of South Sudan’s normative GEWE commitments within the new Constitution and related policies and legislation **Targets:  Value:** 1 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Government Reports (Ministry of Gender), CSOs reports, National Constitutional Amendment Committee  **Indicator 6.1.2C:** % of ministries producing gender disaggregated data and analysis (esp. on sexual and reproductive health and rights, violence against women and girls, women in leadership, humanitarian support) in collaboration with Ministry of Gender, Child and Social Welfare on status of women and girls to inform government reporting on key normative frameworks **Targets:  Value:** 30 **Target Year:** 2022 **Baseline:  Value:** 5 **Year:** 2020 **Source:** Government Reports (e.g. Ministry of Gender, Bureau of Statistics) | 0.00 (core)  132,000.00 (non-core) | 70,000.00 (core)  150,000.00 (non-core) | 70,000.00 (core)  125,000.00 (non-core) | 0.00 (core)  163,900.00 (non-core) | 140,000.00 (core)  570,900.00 (non-core) |
| **Total Resources for outcome 6.1 (core and non-core)** | | | 0.00 (core)  662,963.00 (non-core) | 70,000.00 (core)  470,000.00 (non-core) | 70,000.00 (core)  395,000.00 (non-core) | 0.00 (core)  439,503.00 (non-core) | 140,000.00 (core)  1,967,466.00 (non-core) |
| **Total Resources for impact area 6** | | | 0.00 (core)  662,963.00 (non-core) | 70,000.00 (core)  470,000.00 (non-core) | 70,000.00 (core)  395,000.00 (non-core) | 0.00 (core)  439,503.00 (non-core) | 140,000.00 (core)  1,967,466.00 (non-core) |
| **Impact4 More women of all ages fully participate, lead and engage in political institutions and processes. More commitments on women, peace and security are implemented by Member States and the UN system, and more gender equality advocates influence peace and security processes. More women play a greater role in and are better served by humanitarian response and recovery efforts.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNCF: Priority Area 1: Building Peace and Strengthening Governance; Priority Area 4: Empowering Women and Youth Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 4.1 Government of South Sudan budgets for and fully implements its Women Peace and Security commitments  Related SP Outcome/Output:**   **Indicator 4.1A:** # of commitments within the National Action Plan on 1325 that are budgeted for and implemented **Targets:  Value:** TBD **Target Year:** 2022 **Baseline:  Value:** TBD **Year:** 2021 **Source:** Joint Monitoring and Evaluation Commission, IGAD, UN Women Reports, UN SRSG’s reports to SC  **Indicator 4.1B:** % of women included in all tiers of transitional government and at all levels according to the Peace Agreement **Targets:  Value:** 35 **Target Year:** 2022 **Baseline:  Value:** TBD **Year:** 2021 **Source:** Government Reports (e.g. Ministry of Gender) | **Output 4.1.1 Government of South Sudan has increased access to information and capacity supports to implement WPS commitments in the reform proposals agreed in the Revitalized Peace Agreement and the new Constitution, through UN Women support** | **Indicator 4.1.1A:** # of position papers developed by JMEC, CTSAMM, NCAC, IGAD and women’s organizations to inform gender sensitive reforms in transitional justice, electoral and security sector reforms) to inform the operationalization of the revitalized Peace Agreement, and the new Constitution, through UN Women support **Targets:  Value:** 9 **Target Year:** 2022 **Baseline:  Value:** 5 **Year:** 2021 **Source:** UN Women annual report, JMEC report to IGAD and JMEC Plenary  **Indicator 4.1.1C:** # of national peacebuilding institutions with dedicated gender expertise **Targets:  Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2021 **Source:** UN Women annual report, JMEC report to IGAD and JMEC Plenary  **Indicator 4.1.1D:** # of positions and reviews presented by the Women Parliamentary Caucus on legislative reforms and presented to Transitional Legislative Assembly for gender responsiveness through UN Women’s support **Targets:  Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Government Reports (e.g. Women Parliamentary Caucus)  **Indicator 4.1.1E:** # of policy makers in the security sector- and technical staff trained to support the implementation of WPS commitments incl. in the Peace Agreement **Targets:  Value:** 120 **Target Year:** 2022 **Baseline:  Value:** 148 **Year:** 2021 **Source:** UN Women annual report, Government reports (e.g. NTLI)  **Indicator 4.1.1F:** # of timely, relevant and consistent research on transformational leadership in South Sudan by NTLI to inform policies, legislations and strategies to advance women’s leadership and participation in politics **Targets:  Value:** 3 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women Reports, National Transformational Leadership Institute | 0.00 (core)  1,411,525.00 (non-core) | 0.00 (core)  1,945,000.00 (non-core) | 0.00 (core)  1,215,000.00 (non-core) | 0.00 (core)  1,558,276.00 (non-core) | 0.00 (core)  6,129,801.00 (non-core) |
| **Output 4.1.2 Women’s organizations and individuals have enhanced capacities to influence international, regional, national and local peacebuilding processes** | **Indicator 4.1.2A:** # of women leaders trained in leadership, mediation and peace-building skills to facilitate their engagement in community peacebuilding initiatives and processes to strengthen government accountability on WPS commitments **Targets:  Value:** 200 **Target Year:** 2022 **Baseline:  Value:** 397 **Year:** 2020 **Source:** Partners reports (e.g. Women bloc, Women coalition)  **Indicator 4.1.2B:** % of women, including those living with disabilities who participate in local governance structures, including in the transitional government at the local levels **Targets:  Value:** 35 **Target Year:** 2022 **Baseline:  Value:** 43.26 **Year:** 2020 **Source:** Transitional government reports to JMEC, IGAD, UN Women/UNMISS/UNDP reports  **Indicator 4.1.2C:** # of advocacy initiatives undertaken by women peace networks, including Women Bloc and Women coalition on the implementation of the Peace Agreement, targeting the advancement of the government’s WPS commitments **Targets:  Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** UN Women annual report, Partners reports | 0.00 (core)  905,415.00 (non-core) | 0.00 (core)  1,000,000.00 (non-core) | 0.00 (core)  1,000,000.00 (non-core) | 0.00 (core)  156,030.00 (non-core) | 0.00 (core)  3,061,445.00 (non-core) |
| **Outcome 4.2 Humanitarian actors promote gender responsive humanitarian/crisis response planning frameworks and programmes in South Sudan  Related SP Outcome/Output:**   **Indicator 4.2A:** % of humanitarian actors apply gender analysis in humanitarian/crisis response **Targets:  Value:** 70 **Target Year:** 2022 **Baseline:  Value:** TBD **Year:** 2021 **Note:** To be collected in 2021 and will be updated when the data is available **Source:** UN Women assessment report | **Output 4.2.1 Humanitarian country team/clusters have strengthened capacities to mainstream GEWE issues in their efforts through UN Women support** | **Indicator 4.2.1A:** # of initiatives undertaken to promote gender equality, social inclusion and women empowerment in humanitarian clusters and other relevant strategic platforms. (e.g.: Sensitize on IASC Gender policy and accountability framework, Gender and age Marker (GAM) and Gender responsive DRM) **Targets:  Value:** 5 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2021 **Source:** Humanitarian Response Plan and reports  **Indicator 4.2.1B:** # of women organizations, community-based organisations, national institutions capacitated to promote gender responsive COVID-19 response and mitigation through UN Women's support **Targets:  Value:** 4 **Target Year:** 2022 **Baseline:  Value:** 5 **Year:** 2021 **Source:** UN Women annual report | 80,000.00 (core)  30,000.00 (non-core) | 0.00 (core)  190,000.00 (non-core) | 0.00 (core)  190,000.00 (non-core) | 0.00 (core)  328,912.00 (non-core) | 80,000.00 (core)  738,912.00 (non-core) |
| **Outcome 4.3 Women and girls affected by the conflict access protection and economic opportunities  Related SP Outcome/Output:**   **Indicator 4.3A:** # of displaced and other vulnerable women accessing economic recovery services **Targets:  Value:** 3500 **Target Year:** 2022 **Baseline:  Value:** TBD **Year:** 2021 **Source:** UNDP/WFP/FAO/UN Women agencies’ reports | **Output 4.3.1 Displaced women (incl. women with disabilities, GBV survivors, older women) have increased access to economic recovery assistance and safe spaces, through UN Women’s support** | **Indicator 4.3.1B:** # of women savings clubs/cooperatives established and/or operational for women in conflict-affected areas **Targets:  Value:** 150 **Target Year:** 2022 **Baseline:  Value:** 175 **Year:** 2020 **Notes:** Village savings and loans **Source:** UN Women annual report  **Indicator 4.3.1D:** # of women in conflict-affected areas accessing protection (Sexual and reproductive health and rights, SGBV services and information, legal and rights support) and economic recovery services (technology, skills, cash for assets) in Women Empowerment Centers **Targets:  Value:** 3500 **Target Year:** 2022 **Baseline:  Value:** 7259 **Year:** 2020 **Notes:** To be collected and will be updated when the data is available **Source:** UN Women annual report, Partners reports  **Indicator 4.3.1E:** # of (land) acres allocated by local authorities/communities to support displaced women/returnees with their economic recovery efforts **Targets:  Value:** 150 **Target Year:** 2022 **Baseline:  Value:** 310 **Year:** 2020 **Notes:** acres **Source:** UN Women annual report, Partners reports  **Indicator 4.3.1F:** # of Neighborhood Watch groups formed and self-sustaining **Targets:  Value:** 0 **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2021 **Source:** Implementing Partners' reports  **Indicator 4.3.1G:** # of community-level multi-stakeholder coordination and reporting mechanisms on VAWG **Targets:  Value:** 3 **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2021 **Source:** Implementing partners' reports | 0.00 (core)  1,127,125.00 (non-core) | 76,000.00 (core)  1,520,475.00 (non-core) | 56,000.00 (core)  1,520,475.00 (non-core) | 0.00 (core)  1,023,861.00 (non-core) | 132,000.00 (core)  5,191,936.00 (non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | | | 0.00 (core)  2,316,940.00 (non-core) | 0.00 (core)  2,945,000.00 (non-core) | 0.00 (core)  2,215,000.00 (non-core) | 0.00 (core)  1,714,306.00 (non-core) | 0.00 (core)  9,191,246.00 (non-core) |
| **Total Resources for outcome 4.2 (core and non-core)** | | | 80,000.00 (core)  30,000.00 (non-core) | 0.00 (core)  190,000.00 (non-core) | 0.00 (core)  190,000.00 (non-core) | 0.00 (core)  328,912.00 (non-core) | 80,000.00 (core)  738,912.00 (non-core) |
| **Total Resources for outcome 4.3 (core and non-core)** | | | 0.00 (core)  1,127,125.00 (non-core) | 76,000.00 (core)  1,520,475.00 (non-core) | 56,000.00 (core)  1,520,475.00 (non-core) | 0.00 (core)  1,023,861.00 (non-core) | 132,000.00 (core)  5,191,936.00 (non-core) |
| **Total Resources for impact area 4** | | | 80,000.00 (core)  3,474,065.00 (non-core) | 76,000.00 (core)  4,655,475.00 (non-core) | 56,000.00 (core)  3,925,475.00 (non-core) | 0.00 (core)  3,067,079.00 (non-core) | 212,000.00 (core)  15,122,094.00 (non-core) |