

UN Women Strategic Note 2019-2022

**UN WOMEN Thailand COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/11/2022

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact6 A comprehensive and dynamic set of global norms, policies and standards on gender equality and women's empowerment is in place and is applied through action by Government and other stakeholders at all levels** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: By 2021, inclusive systems, structures and processes advance sustainable people-centred, equitable development for all people in Thailand Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 6.1 A comprehensive and dynamic set of global norms, policies and standards on gender equality and women's empowerment is in place and is applied through action by Governments and other stakeholders at all levels  Related SP Outcome/Output:**   **Indicator 6.1A:** Number of inter governmental dialogues supported by UN Women **Targets:  Value:** 6 **Target Year:** 2020 **Value:** 7 **Target Year:** 2021 **Value:** 5 **Target Year:** 2019 **Value:** 8 **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2018 **Source:** Progress Report  **Indicator 6.1B:** Number of policy advocacy / initiatives to promote localization of GEWE, SDG, GEF, CEDAW **Targets:  Value:** 2 **Target Year:** 2021 **Value:** 4 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Source:** Progress report | **Output 6.1.1 Governments, CSOs, Gender Equality advocates and the UN system understand, influence and participate in inter-governmental processes related to GEEW** | **Indicator 6.1.1A:** Number of inter governmental dialogues supported by UN Women **Targets:  Value:** 6 **Notes:** Collaboration with the Department of ASEAN Affairs and ACWC **Target Year:** 2019 **Value:** 10 **Target Year:** 2020 **Value:** 11 **Target Year:** 2021 **Value:** 12 **Notes:** Collaboration with the Department of ASEAN Affairs and ACWC **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2018 **Notes:** Collaboration with the Department of ASEAN Affairs and ACWC **Source:** Progress report | 0.00 (core)  0.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  120,000.00 (non-core) | 0.00 (core)  58,000.00 (non-core) | 0.00 (core)  278,000.00 (non-core) |
| **Outcome 6.2 Legal frameworks and policies to advance women's leadership, women's rights to participate in decision making at national and local levels, and women's access to justice are reformed/ adopted and implemented.  Related SP Outcome/Output:**   **Indicator 6.2A:** Number of consultations supported by UN Women **Targets:  Value:** 4 **Target Year:** 2020 **Value:** 6 **Target Year:** 2021 **Value:** 8 **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2022 **Source:** Progress and annual reports, Policy recommendations | **Output 6.2.1 Women at national and local levels fully participate, lead and engage in political decision making process and local governance.** | **Indicator 6.2.1A:** Number of gender advocates and politicians attending the consultations/ workshops who demonstrate better understanding of benefits and challenges of special measures and gender policies in electoral management/ relevant laws **Targets:  Value:** 300 **Notes:** Through series of consultations **Target Year:** 2019 **Value:** 325 **Target Year:** 2020 **Value:** 350 **Target Year:** 2021 **Value:** 372 **Notes:** Through series of consultation **Target Year:** 2022 **Baseline:  Value:** 250 **Year:** 2018 **Notes:** 2 National Consultations **Source:** Progress and annual reports, Policy recommendations | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) |
| **Output 6.2.2 Capacity of multi-disciplinary team and women's machinery to implement laws and policies to protect women and girls is strengthened to promote access to justice and the rule of law and to end gender based violence.** | **Indicator 6.2.2A:** Number of women from civil society and communities trained on gender based violence, human trafficking and criminal justice system in protection of women and girls **Targets:  Value:** 500 **Target Year:** 2020 **Value:** 600 **Target Year:** 2021 **Value:** 700 **Target Year:** 2022 **Baseline:  Value:** 400 **Year:** 2019 **Source:** Progress and annual reports, Policy recommendations to the government | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) |
| **Output 6.2.3 Women's leaders and women's organizations have enhanced capacities and opportunities to participate in local development initiatives and play greater roles in promoting peaceful, cohesive and resilient communities** | **Indicator 6.2.3A:** Consultations, trainings, capacity development workshops to test and upscale new approaches to implement n NAP WPS, including conflict prevention at national level supported by UN Women. **Targets:  Value:** 4 **Target Year:** 2019 **Value:** 5 **Target Year:** 2020 **Value:** 6 **Target Year:** 2021 **Value:** 7 **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2018 **Source:** Progress and annual reports, Policy briefs submitted to the government  **Indicator 6.2.3B:** Number of local women-led initiatives and knowledge tools translated into practice to promote social cohesion and resilient communities **Targets:  Value:** 10 **Target Year:** 2019 **Value:** 12 **Target Year:** 2020 **Value:** 13 **Target Year:** 2021 **Value:** 14 **Target Year:** 2022 **Baseline:  Value:** 6 **Year:** 2018 **Source:** Progress and annual reports  **Indicator 6.2.3C:** Number of local women participating in capacity building activities who demonstrate enhanced understanding/ capacities to influence peace and security **Targets:  Value:** 400 **Target Year:** 2019 **Value:** 500 **Target Year:** 2020 **Value:** 600 **Target Year:** 2021 **Value:** 700 **Target Year:** 2022 **Baseline:  Value:** 300 **Year:** 2018 **Source:** Progress and annual reports  **Indicator 6.2.3D:** Percentage of State actors at national and sub-national level who report increased skills/willingness to elaborate/strengthen, implement, and measure policies and programmes to promote WPS supported by UN Women. **Targets:  Value:** TBD **Notes:** TBD during the inception phase. **Target Year:** 2021 **Value:** 50 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Progress report and survey | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  150,000.00 (non-core) | 0.00 (core)  160,000.00 (non-core) | 0.00 (core)  310,000.00 (non-core) |
| **Total Resources for outcome 6.1 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  120,000.00 (non-core) | 0.00 (core)  58,000.00 (non-core) | 0.00 (core)  278,000.00 (non-core) |
| **Total Resources for outcome 6.2 (core and non-core)** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  150,000.00 (non-core) | 0.00 (core)  160,000.00 (non-core) | 0.00 (core)  310,000.00 (non-core) |
| **Total Resources for impact area 6** | | | 0.00 (core)  0.00 (non-core) | 0.00 (core)  100,000.00 (non-core) | 0.00 (core)  270,000.00 (non-core) | 0.00 (core)  218,000.00 (non-core) | 0.00 (core)  588,000.00 (non-core) |
| **Impact3 The Royal Thai Government, in collaboration with civil society, will be better able to implement actions to prevent and respond to violence against women and girls.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: Goal: Promoting anti-corruption, inclusive engagement, and social cohesion: Strategy 5: Security, Strategy 6: Improved effectiveness and good governance in administration.  Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 3.1 Laws, policies and strategies adopted and implemented in line with international standards and informed by voices of women survivors of violence to prevent and respond to VAWG  Related SP Outcome/Output:**   **Indicator 3.1A:** 2.3.1 Number of users of community-based and women-led networks supported by UN Women active in preventing VAW and trafficking **Targets:  Value:** 100 **Target Year:** 2020 **Value:** 100 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** User registries Quantitative calculation based on technical progress reports of implementing partner  **Indicator 3.1B:** 2.3.2 Number of women migrants who are provided with information by networks **Targets:  Value:** 300 **Target Year:** 2020 **Value:** 300 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** User registries Quantitative calculation based on technical progress reports of implementing partner  **Indicator 3.1C:** 2.4.1. Number of women migrants who receive assistance from front-line service providers **Targets:  Value:** 80 **Target Year:** 2020 **Value:** 80 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** User registries Quantitative calculation based on technical progress reports of implementing partner  **Indicator 3.1D:** 2.1 Extent to which national laws, policies, plans and strategies are in-line with the normative frameworks on prevention and response to violence against women **Targets:  Value:** 0 **Target Year:** 2020 **Value:** 1 **Notes:** Yr 2021 target is 1. Accumulative target Yr 2020-2021 is 1. **Target Year:** 2021 **Value:** 1 **Notes:** Yr 2022 target is 1. Accumulative target Yr 2020-2022 is 2. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** User registries Quantitative calculation based on technical progress reports of implementing partner | **Output 3.1.1 Increased access to information, coordinated quality services and supportive networks (local, national and regional groups) are strengthened for WMWs, including through survivor-centered laws, policies and research.** | **Indicator 3.1.1A:** 2.3.1 Number of users of community-based and women-led networks supported by UN Women active in preventing VAW and trafficking **Targets:  Value:** 200 **Notes:** Year 2019 target number 100 Year 2020 target number 100 **Target Year:** 2020 **Value:** 300 **Notes:** Accumulative Yr 2019 - 2021 **Target Year:** 2021 **Value:** 400 **Notes:** Accumulative Yr 2019-2022 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2018 **Source:** User registries Quantitative calculation based on technical progress reports of implementing partner  **Indicator 3.1.1B:** 2.3.2 Number of women migrants who are provided with information by networks. **Targets:  Value:** 500 **Notes:** Target number in 2019 is 200 Target number in 2020 is 300 **Target Year:** 2020 **Value:** 800 **Notes:** Target number in 2021 is 300 Accumulative Year 2019 - 2021 is 800 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2018 **Source:** User registries Quantitative calculation based on technical progress reports of implementing partner  **Indicator 3.1.1C:** 2.4.1. Number of women migrants who receive assistance from front-line service providers **Targets:  Value:** 130 **Notes:** 2019 target number is 50 2020 target number is 80 **Target Year:** 2020 **Value:** 210 **Notes:** 2021 target number is 80; Accumulative Year 2019 - 2021 is 210 **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2018 **Source:** Quantitative calculation based on technical progress reports of implementing partners  **Indicator 3.1.1D:** 2.2.1: Number of information systems strengthened for women migrants who access support services (health, welfare, police, justice) for survivors of violence and trafficking **Targets:  Value:** 0 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 2 **Notes:** Yr 2022 target is 1. Accumulative value is 2. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** User registries Quantitative calculation based on technical progress reports of implementing partner  **Indicator 3.1.1E:** 2.2.2: Number of referral mechanisms for follow-up services for women migrants by front line service providers. **Targets:  Value:** 2 **Notes:** Yr 2020 target is 2. **Target Year:** 2020 **Value:** 3 **Notes:** Yr 2021 target is 1. Accumulative Yr 2020-2021 target is 3. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** User registries Quantitative calculation based on technical progress reports of implementing partner  **Indicator 3.1.1F:** 2.4.3: Number of joint task forces (linking, for example, criminal justice, labour, immigration and violence against women) established on women’s protection/trafficking. **Targets:  Value:** 1 **Notes:** Yr 2020 target is 1. **Target Year:** 2020 **Value:** 2 **Notes:** Yr 2021 target is 1. Accumulative Yr 2020-2021 target is 2. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2019 **Source:** User registries Quantitative calculation based on technical progress reports of implementing partner | 0.00 (core)  350,000.00 (non-core) | 0.00 (core)  376,532.00 (non-core) | 0.00 (core)  380,000.00 (non-core) | 0.00 (core)  350,000.00 (non-core) | 0.00 (core)  1,456,532.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 0.00 (core)  350,000.00 (non-core) | 0.00 (core)  376,532.00 (non-core) | 0.00 (core)  380,000.00 (non-core) | 0.00 (core)  350,000.00 (non-core) | 0.00 (core)  1,456,532.00 (non-core) |
| **Total Resources for impact area 3** | | | 0.00 (core)  350,000.00 (non-core) | 0.00 (core)  376,532.00 (non-core) | 0.00 (core)  380,000.00 (non-core) | 0.00 (core)  350,000.00 (non-core) | 0.00 (core)  1,456,532.00 (non-core) |
| **Impact2 More women have increased economic opportunities** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: By 2021, inclusive systems, structures and processes advance sustainable people-centred, equitable development for all people in Thailand. Related national development priorities:** | | | | | |
|  |  |  | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 2.1 More women lead, participate and have access to business opportunities to advance sustainable and inclusive growth  Related SP Outcome/Output:**   **Indicator 2.1B:** Number of Collective approaches and/ or practices to challenges of global and/ or mutual concern which have been developed/ embraced/ implemented. **Targets:  Value:** 1 **Notes:** On-going established approach throughout the programme period **Target Year:** 2021 **Value:** 0 **Target Year:** 2019 **Value:** 1 **Notes:** On-going established approach throughout the programme period **Target Year:** 2020 **Value:** 1 **Notes:** On-going established approached throughout the programme period **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2018 **Source:**  Programme progress and Evaluation Reports | **Output 2.1.1 Knowledge: Women’s networks, public institutions and the private sector in the EU and Asia share expertise and knowledge to advance an enabling business environment for women’s economic empowerment** | **Indicator 2.1.1A:** Percentage of participants targeted by outreach and advocacy events who acknowledge having engaged further on the topic on their own initiative as a result of their exposure to an event **Targets:  Value:** 70% **Notes:** no implementation in 2019 **Target Year:** 2019 **Value:** 70% **Notes:** End of programme March 2022 **Target Year:** 2022 **Value:** 70% **Target Year:** 2020 **Value:** 70% **Target Year:** 2021 **Value:** 70% **Target Year:** 2022 **Baseline:  Value:** 0% **Year:** 2018 **Source:** Online and offline Surveys | 0.00 (core)  89,380.00 (non-core) | 0.00 (core)  120,000.00 (non-core) | 0.00 (core)  120,000.00 (non-core) | 0.00 (core)  34,200.00 (non-core) | 0.00 (core)  363,580.00 (non-core) |
| **Output 2.1.2 Capacity development and technical assistance: Women-owned business and entrepreneurs have increased capacity to engage with governments and private sector companies in policies and dialogues for advancement of women’s economic empowerment** | **Indicator 2.1.2A:** Number of processes related to state level and sub-state level (bilateral, regional, multi-lateral) and non-state partnership strategies and policy dialogues which have been influenced. **Targets:  Value:** 1 **Target Year:** 2019 **Value:** 1 **Notes:** End of programme in March 2022 **Target Year:** 2022 **Value:** 1 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Baseline:  Value:** 0 **Year:** 2018 **Source:** Project progress report, evaluation report and other credible international regional report/research | 0.00 (core)  56,181.00 (non-core) | 0.00 (core)  80,000.00 (non-core) | 0.00 (core)  80,000.00 (non-core) | 0.00 (core)  32,000.00 (non-core) | 0.00 (core)  248,181.00 (non-core) |
| **Output 2.1.3 Advocacy and representation: More private sector companies implement the WEPs, including the gender-sensitive business culture and practices in EU and the country** | **Indicator 2.1.3A:** Number of WEPs signatories **Targets:  Value:** 6 **Notes:** 6 signatories in Thailand as of Nov 19 **Target Year:** 2019 **Value:** 120 **Notes:** \*Baseline of signatories for Asia Pacific is 588 in 2018 and forThailand is 6 \*No evidence of action plans of signatories. **Target Year:** 2022 **Value:** 20 **Notes:** \*Baseline of signatories for Asia Pacific is 588 in 2018 and forThailand is 6 \*No evidence of action plans of signatories. **Target Year:** 2020 **Value:** 70 **Notes:** \*Baseline of signatories for Asia Pacific is 588 in 2018 and forThailand is 6 \*No evidence of action plans of signatories. **Target Year:** 2021 **Baseline:  Value:** 6 **Year:** 2018 **Notes:** 6 signatories in Thailand as of Nov 19 \*Baseline of signatories for Asia Pacific is 588 in 2018 and forThailand is 6 \*No evidence of action plans of signatories. **Source:** http://weprinciples.org/Site/Companies/#search | 0.00 (core)  56,181.00 (non-core) | 0.00 (core)  80,000.00 (non-core) | 0.00 (core)  80,000.00 (non-core) | 0.00 (core)  33,000.00 (non-core) | 0.00 (core)  249,181.00 (non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | | | 0.00 (core)  201,742.00 (non-core) | 0.00 (core)  280,000.00 (non-core) | 0.00 (core)  280,000.00 (non-core) | 0.00 (core)  99,200.00 (non-core) | 0.00 (core)  860,942.00 (non-core) |
| **Total Resources for impact area 2** | | | 0.00 (core)  201,742.00 (non-core) | 0.00 (core)  280,000.00 (non-core) | 0.00 (core)  280,000.00 (non-core) | 0.00 (core)  99,200.00 (non-core) | 0.00 (core)  860,942.00 (non-core) |