

UN Women Strategic Note 2018-2022

**UN WOMEN Ukraine COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/11/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact4 Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action.** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNPF Pillar 3: Democratic governance, rule of law and civic participation; UNPF Pillar 4: Human security, social cohesion and recovery with a particular focus on eastern Ukraine Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 4.1 More commitments on Women, Peace and Security are implemented by national and local institutions and more gender equality advocates influence recovery, justice and security processes  Related SP Outcome/Output:**   **Indicator 4.1A:** Number of national security sector institutions which implement measures in line with WPS commitments **Targets:  Value:** 1 **Target Year:** 2018 **Value:** 1 **Target Year:** 2019 **Value:** 1 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 5 **Notes:** 5 is the cumulative target for 2018-2022 Ukraine SN. In 2022 the CO intends to work with at least 3 institutions. **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2017 **Note:** MIA **Source:** UN Women annual report   **Indicator 4.1B:** Percentage of the provisions of the NAP 1325 implemented by line ministries and local authorities **Targets:  Value:** 30% **Target Year:** 2018 **Value:** 60% **Target Year:** 2019 **Value:** 90% **Target Year:** 2020 **Value:** 0% **Target Year:** 2021 **Value:** 20% **Notes:** The target for 2022 is to have 20% of the new NAP1325 implemented. However it is not certain if this data will be available. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Note:** Assessment conducted in 2017 **Source:** Annual reports on implementation of the NAP | **Output 4.1.2 GE advocates and women peace activists have capacity for evidence-based advocacy for increased access to and participation in justice , security and recovery** | **Indicator 4.1.2A:** Number of WPS advocacy initiatives aimed at increased access to and participation in justice, security and recovery, led by GE advocates and women peace activists with UN Women support **Targets:  Value:** 1 **Target Year:** 2018 **Value:** 1 **Target Year:** 2019 **Value:** 1 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 5 **Notes:** 5 is the cumulative target for 2018-2022 Ukraine SN (1 per year). The target for 2022 only is at least 1 advocacy initiative. **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2017 **Notes:** Invisible Battalion **Source:** UN Women reports, partners' reports | 0.00 (core)  312,788.00 (non-core) | 0.00 (core)  508,241.00 (non-core) | 0.00 (core)  703,475.00 (non-core) | 0.00 (core)  429,242.00 (non-core) | 0.00 (core)  334,031.00 (non-core) | 0.00 (core)  2,287,777.00 (non-core) |
| **Output 4.1.3 Government at all levels better implement and monitor WPS commitments in sustainable and inclusive ways.** | **Indicator 4.1.3A:** Government institutions supported by the project, demonstrate improved performance to implement and monitor WPS commitments in sustainable and inclusive ways. **Targets:  Value:** 0 **Target Year:** 2021 **Value:** 2 **Notes:** 2 is the cumulative target from 2021-2022. By 2022 the target is to see improvement in 2 out of 10 indicators of improved performance. By 2024 the target is to see improvement in 7 out of 10 indicators. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2020 **Notes:** \*Measured using a UN Women developed matrix comprising of 10 indicators aligned to the second NAP 1325 M&E framework. The matrix will track progress towards tangible results and indications of improved performance. **Source:** UN Women reports, partners' reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  748,685.00 (non-core) | 0.00 (core)  748,685.00 (non-core) |
| **Output 4.1.4 Women and their organizations meaningfully participate in conflict prevention, resolution, and recovery.** | **Indicator 4.1.4A:** Number of local and regional plans that incorporate gender considerations and recommendations from local women’s groups. **Targets:  Value:** 0 **Target Year:** 2021 **Value:** 4 **Notes:** 4 is the cumulative target from 2021-2022. By 2022 the target is to have at least 4 plans that incorporate recommendations. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2021 **Source:** UN Women reports, partner reports | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 0.00 (core)  723,821.00 (non-core) | 0.00 (core)  925,749.00 (non-core) | 0.00 (core)  1,649,570.00 (non-core) |
| **Total Resources for outcome 4.1 (core and non-core)** | | | 0.00 (core)  312,788.00 (non-core) | 0.00 (core)  508,241.00 (non-core) | 0.00 (core)  703,475.00 (non-core) | 0.00 (core)  1,153,063.00 (non-core) | 0.00 (core)  2,008,465.00 (non-core) | 0.00 (core)  4,686,032.00 (non-core) |
| **Total Resources for impact area 4** | | | 0.00 (core)  312,788.00 (non-core) | 0.00 (core)  508,241.00 (non-core) | 0.00 (core)  703,475.00 (non-core) | 0.00 (core)  1,153,063.00 (non-core) | 0.00 (core)  2,008,465.00 (non-core) | 0.00 (core)  4,686,032.00 (non-core) |
| **Impact1 Women lead, participate in and benefit equally from governance systems** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNPF Pillar 1: Sustainable economic growth, environment and employment; UNPF Pillar 3: Democratic governance, rule of law and civic participation  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 1.1 Women, particularly those facing multiple forms of discrimination, increasingly participate in and benefit from gender-responsive reforms and justice  Related SP Outcome/Output:**   **Indicator 1.1A:** Number of sectoral reforms that include gender equality provisions **Targets:  Value:** 1 **Target Year:** 2018 **Value:** 1 **Target Year:** 2019 **Value:** 1 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 5 **Notes:** 5 is the cumulative target for 2018-2022 Ukraine SN (1 per year). In 2022 the target will be 1. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** National Reforms Concepts; Partners Reports  **Indicator 1.1B:** Share of women in the police **Targets:  Value:** 25% **Target Year:** 2018 **Value:** 25% **Target Year:** 2019 **Value:** 26% **Target Year:** 2020 **Value:** 30% **Target Year:** 2021 **Value:** 30% **Target Year:** 2022 **Baseline:  Value:** 21.8% **Year:** 2017 **Source:** National SDG report, Annual reports of the national mechanism on gender equality,   **Indicator 1.1C:** Share of women in the armed forces **Targets:  Value:** 10% **Target Year:** 2018 **Value:** 10% **Target Year:** 2019 **Value:** 14% **Target Year:** 2020 **Value:** 20% **Target Year:** 2021 **Value:** 22% **Target Year:** 2022 **Baseline:  Value:** 8.5% **Year:** 2017 **Note:** Source - Ministry of Defense **Source:** National SDG report, Annual reports of the national mechanism on gender equality   **Indicator 1.1D:** Share of women in the parliament **Targets:  Value:** 12% **Target Year:** 2018 **Value:** 20% **Target Year:** 2019 **Value:** 20,52% **Target Year:** 2020 **Value:** 30% **Target Year:** 2021 **Value:** 30% **Target Year:** 2022 **Baseline:  Value:** 12% **Year:** 2017 **Source:** Inter-Parliamentary Union Database   **Indicator 1.1E:** Share of women in the government **Targets:  Value:** 12.5% **Target Year:** 2018 **Value:** 33% **Target Year:** 2019 **Value:** 13,6% **Target Year:** 2020 **Value:** 30% **Target Year:** 2021 **Value:** 30% **Target Year:** 2022 **Baseline:  Value:** 33% **Year:** 2020 **Source:** National SDG report, Annual reports of the national mechanism on gender equality   **Indicator 1.1F:** Share of women in the local councils **Targets:  Value:** 14% **Target Year:** 2018 **Value:** 15% **Notes:** The data is udpated for regional councils since no data avaliable for local councils. **Target Year:** 2019 **Value:** 30% **Target Year:** 2020 **Value:** 30% **Target Year:** 2021 **Value:** 30% **Target Year:** 2022 **Baseline:  Value:** 14% **Year:** 2017 **Source:** Central Election Commission   **Indicator 1.1G:** Number of normative acts which were revised or adopted to provide men and women with equal rights and opportunities and to prevent discrimination against women and girls **Targets:  Value:** 1 **Target Year:** 2018 **Value:** 0 **Target Year:** 2019 **Value:** 1 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 5 **Notes:** 5 is the cumulative target for 2018-2022 Ukraine SN (1 per year). In 2022 the target will be 1. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Note:** No data as per SDG (2017 SDG baseline) **Source:** Parliament of Ukraine | **Output 1.1.1 National and local institutions have increased capacity to formulate, implement and monitor policies, reforms and plans with specific commitments to advance GEWE** | **Indicator 1.1.1A:** Number of local institutions with increased in-house technical capacity on gender-responsive planning and budgeting **Targets:  Value:** 5 **Target Year:** 2018 **Value:** 7 **Target Year:** 2019 **Value:** 5 **Target Year:** 2020 **Value:** 5 **Target Year:** 2021 **Value:** 25 **Notes:** 25 is the cumulative target for 2018-2022 Ukraine SN (5 per year). In 2022 the CO intends to work with at least 25 local institutions. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Partners’ reports  **Indicator 1.1.1B:** Number of line ministries, which apply knowledge and tools provided by UN Women in annual planning and budgeting **Targets:  Value:** 0 **Target Year:** 2018 **Value:** 6 **Target Year:** 2019 **Value:** 2 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Value:** 3 **Notes:** 3 is the cumulative target for 2018-2022 Ukraine SN. In 2022 the CO intends to work with at least 1 line ministry. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** Partner's Report | 0.00 (core)  1,743,074.00 (non-core) | 0.00 (core)  2,214,210.00 (non-core) | 0.00 (core)  1,371,399.00 (non-core) | 0.00 (core)  2,179,139.00 (non-core) | 0.00 (core)  1,796,365.00 (non-core) | 0.00 (core)  9,304,187.00 (non-core) |
| **Output 1.1.3 Women and GE advocates have enhanced capacity to participate in decision making and demand accountability for GEWE commitments and to access justice for violations of these rights** | **Indicator 1.1.3A:** Number of advocacy initiatives by gender advocates to demand for gender equality allocations **Targets:  Value:** 3 **Target Year:** 2018 **Value:** 3 **Target Year:** 2019 **Value:** 3 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Value:** 15 **Notes:** 15 is the cumulative target for 2018-2022 Ukraine SN (3 per year). In 2022 the CO intends to support at least 3 advocacy initiatives. **Target Year:** 2022 **Baseline:  Value:** 3 **Year:** 2017 **Source:** UN Women reports; regional and local strategies, plans, programmes  **Indicator 1.1.3B:** Number of Knowledge resources developed by UN Women applied by gender equality advocates (annually) **Targets:  Value:** 1 **Target Year:** 2018 **Value:** 1 **Target Year:** 2019 **Value:** 1 **Target Year:** 2020 **Value:** 1 **Target Year:** 2021 **Value:** 5 **Notes:** 5 is the cumulative target for 2018-2022 Ukraine SN (1 per year). In 2022 the CO intends to develop 1 knowledge product. **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2017 **Source:** UN Women reports | 0.00 (core)  786,544.00 (non-core) | 0.00 (core)  398,412.00 (non-core) | 0.00 (core)  224,434.00 (non-core) | 0.00 (core)  309,568.00 (non-core) | 0.00 (core)  691,005.00 (non-core) | 0.00 (core)  2,409,963.00 (non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | | | 0.00 (core)  2,529,618.00 (non-core) | 0.00 (core)  2,612,622.00 (non-core) | 0.00 (core)  1,595,833.00 (non-core) | 0.00 (core)  2,488,707.00 (non-core) | 0.00 (core)  2,487,370.00 (non-core) | 0.00 (core)  11,714,150.00 (non-core) |
| **Total Resources for impact area 1** | | | 0.00 (core)  2,529,618.00 (non-core) | 0.00 (core)  2,612,622.00 (non-core) | 0.00 (core)  1,595,833.00 (non-core) | 0.00 (core)  2,488,707.00 (non-core) | 0.00 (core)  2,487,370.00 (non-core) | 0.00 (core)  11,714,150.00 (non-core) |
| **Impact3 All women and girls live a life free from all forms of violence** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: UNPF Pillars 3: Democratic governance, rule of law and civic participation; UNPF Pillar 4: Human security, social cohesion and recovery with a particular focus on eastern Ukraine  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2018** | **Year 2019** | **Year 2020** | **Year 2021** | **Year 2022** | **Total** |
| **Outcome 3.1 Transformative changes in social norms, attitudes and behaviors are achieved at community and individual levels to prevent GBV  Related SP Outcome/Output:**   **Indicator 3.1A:** Number of local plans developed by local authorities that include specific measures to address sexual harassment **Targets:  Value:** 0 **Target Year:** 2018 **Value:** 1 **Target Year:** 2019 **Value:** 1 **Target Year:** 2020 **Value:** 4 **Target Year:** 2021 **Value:** 10 **Notes:** 10 is the cumulative target for 2018-2022 Ukraine SN (1 for 2019, 3 per year from 2020). In 2022 the target will be 2. **Target Year:** 2022 **Baseline:  Value:** 1 **Year:** 2019 **Source:** UN Women reports, national and local authorities’ reports  **Indicator 3.1B:** Share of women survivors of physical or sexual violence who sought help **Targets:  Value:** 32% **Target Year:** 2018 **Value:** 32% **Target Year:** 2019 **Value:** 50% **Target Year:** 2020 **Value:** 50% **Target Year:** 2021 **Value:** 50% **Notes:** The target for 2022 is 50%. However it is not certain if this data will be available. **Target Year:** 2022 **Baseline:  Value:** 32% **Year:** 2017 **Source:** UNFPA survey (DHS-based), OSCE-led survey on violence against women   **Indicator 3.1C:** Proportion of women and girls subjected to physical, sexual or psychological violence in the last 12 months, by form of violence:  - any form **Targets:  Value:** 17% **Target Year:** 2018 **Value:** 17% **Target Year:** 2019 **Value:** 15% **Target Year:** 2020 **Value:** 15% **Target Year:** 2021 **Value:** 15% **Notes:** The target for 2022 is 15%. However it is not certain if this data will be available. **Target Year:** 2022 **Baseline:  Value:** 34% **Year:** 2018 **Note:** based on the OSCE- led Survey Violence Against Women report (2019) https://www.osce.org/secretariat/440312 **Source:** UNFPA survey (DHS-based)   **Indicator 3.1D:** Proportion of women and girls subjected to physical, sexual or psychological violence in the last 12 months, by form of violence: - physical **Targets:  Value:** 11% **Notes:** Physical and / or sexual violence based on the OSCE-led survey on violence against women, 2019https://www.osce.org/files/f/documents/1/3/440312\_0.pdf . No country level data is available for physical violence. **Target Year:** 2018 **Value:** 8.8% **Notes:** No official data is currently available. **Target Year:** 2019 **Value:** 6% **Notes:** No official data is currently available. **Target Year:** 2020 **Value:** 6% **Target Year:** 2021 **Value:** 6% **Notes:** The target for 2022 is 6%. However it is not certain if this data will be available. **Target Year:** 2022 **Baseline:  Value:** 11% **Year:** 2018 **Note:** Physical and / or sexual violence based on the OSCE-led survey on violence against women, 2019https://www.osce.org/files/f/documents/1/3/440312\_0.pdf . No country level data is available for physical violence. **Source:** UNFPA survey (DHS-based), OSCE-led survey on violence against women  **Indicator 3.1E:** Proportion of women and girls subjected to sexual violence in the last 12 months, by form of violence: - sexual **Targets:  Value:** 11% **Notes:** Data on physical and / or sexual violence (OSCE-led survey on violence against women https://www.osce.org/files/f/documents/1/3/440312\_0.pdf) , no official country-wide data on sexual violence is available **Target Year:** 2018 **Value:** 2% **Notes:** No official country-wide data is available **Target Year:** 2019 **Value:** 1% **Notes:** No official country-wide data is available **Target Year:** 2020 **Value:** 1% **Target Year:** 2021 **Value:** 1% **Notes:** The target for 2022 is 1%. However it is not certain if this data will be available. **Target Year:** 2022 **Baseline:  Value:** 2% **Year:** 2020 **Note:** No official data is currently available. **Source:** UNFPA survey(DHS-based), OSCE-led survey on violence against women  **Indicator 3.1F:** Proportion of women and girls subjected to psychological violence in the last 12 months, by form of violence: - psychological **Targets:  Value:** 20% **Notes:** Data only available for intimate partner psychological violence, OSCE-led survey on violence against women (https://www.osce.org/files/f/documents/1/3/440312\_0.pdf). **Target Year:** 2018 **Value:** 14% **Notes:** No official country-wide data is currently available **Target Year:** 2019 **Value:** 10% **Notes:** No official country-wide data is currently available **Target Year:** 2020 **Value:** 10% **Target Year:** 2021 **Value:** 10% **Notes:** The target for 2022 is 10%. However it is not certain if this data will be available. **Target Year:** 2022 **Baseline:  Value:** 14% **Year:** 2017 **Source:** UNFPA survey(DHA-based), OSCE-led survey on violence against women | **Output 3.1.1 Women, girls, men and boys at community level are mobilized in favor of respectful non-violent relationships, gender equality and safety in public spaces** | **Indicator 3.1.1A:** Number of recommendations addressing GBV and security risks in public space provided by women for regional/local strategies, plans and programs (annually) **Targets:  Value:** 0 **Target Year:** 2018 **Value:** 5 **Target Year:** 2019 **Value:** 5 **Target Year:** 2020 **Value:** 5 **Target Year:** 2021 **Value:** 20 **Notes:** 20 is the cumulative target for 2018-2022 Ukraine SN (5 per year). In 2022 the CO intends to support at least 5 sets of recommendations **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2018 **Source:** UN Women reports; regional and local strategies and programs; list of submitted recommendations   **Indicator 3.1.1B:** Number of media representatives with increased knowledge on gender-sensitive and human rights-based reporting (annually) **Targets:  Value:** 20 **Target Year:** 2018 **Value:** 26 **Target Year:** 2019 **Value:** 20 **Target Year:** 2020 **Value:** 20 **Target Year:** 2021 **Value:** 80 **Notes:** 80 is the cumulative target for 2018-2022 Ukraine SN (20 per year). In 2022 the CO intends to work with at least 20 media representatives. **Target Year:** 2022 **Baseline:  Value:** 71 **Year:** 2017 **Notes:** 2016-2017 UNDP-UNW JP EU programme **Source:** Capacity assessment and training reports  **Indicator 3.1.1C:** Percent of initiatives from the Government Strategic Plan on communication and advocacy implemented per year **Targets:  Value:** 30% **Target Year:** 2018 **Value:** 60% **Notes:** Communication Strategy is not yet approved **Target Year:** 2019 **Value:** 100% **Target Year:** 2020 **Value:** 100% **Notes:** The Government Communication Strategy was approved in September 2020. The Action Plan will be developed by the Government in close consultations with development partners and CSOs by the end of 2020. **Target Year:** 2021 **Value:** 20% **Notes:** As of October 2021, the Action Plan has still not been approved. Therefore the initial 100% target by 2022 is no longer realistic. A tentative 20% target has been put for 2022 instead. **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Notes:** Strategic plan will be developed end of 2017 **Source:** Government Reports, UN Women Reports | 0.00 (core)  446,672.00 (non-core) | 0.00 (core)  735,477.00 (non-core) | 0.00 (core)  966,799.00 (non-core) | 0.00 (core)  555,856.00 (non-core) | 0.00 (core)  343,774.00 (non-core) | 0.00 (core)  3,048,578.00 (non-core) |
| **Output 3.1.2 Local authorities and law enforcement have capacity to integrate comprehensive GBV prevention interventions in regional and local planning and programming** | **Indicator 3.1.2A:** Number of GBV prevention interventions implemented jointly by law enforcement, authorities, schools and communities (annually) **Targets:  Value:** 2 **Target Year:** 2018 **Value:** 2 **Target Year:** 2019 **Value:** 2 **Target Year:** 2020 **Value:** 2 **Target Year:** 2021 **Value:** 10 **Notes:** 10 is the cumulative target for 2018-2022 Ukraine SN (2 per year). In 2022 the CO intends to support at least 2 interventions. **Target Year:** 2022 **Baseline:  Value:** 2 **Year:** 2017 **Source:** UN Women project reports, field visits reports  **Indicator 3.1.2B:** Number of changes introduced in the regional and community level plans and programs to prevent GBV **Targets:  Value:** 0 **Target Year:** 2018 **Value:** 3 **Target Year:** 2019 **Value:** 3 **Target Year:** 2020 **Value:** 3 **Target Year:** 2021 **Value:** 12 **Notes:** 12 is the cumulative target for 2018-2022 Ukraine SN (3 per year). In 2022 the CO intends to work towards at least 3 changes introduced into gbv plans/programs **Target Year:** 2022 **Baseline:  Value:** 0 **Year:** 2017 **Source:** UN Women reports, regional and community level plans and programs | 0.00 (core)  265,614.00 (non-core) | 0.00 (core)  284,480.00 (non-core) | 0.00 (core)  386,510.00 (non-core) | 0.00 (core)  236,314.00 (non-core) | 0.00 (core)  305,967.00 (non-core) | 0.00 (core)  1,478,885.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 0.00 (core)  712,286.00 (non-core) | 0.00 (core)  1,019,957.00 (non-core) | 0.00 (core)  1,353,309.00 (non-core) | 0.00 (core)  792,170.00 (non-core) | 0.00 (core)  649,741.00 (non-core) | 0.00 (core)  4,527,463.00 (non-core) |
| **Total Resources for impact area 3** | | | 0.00 (core)  712,286.00 (non-core) | 0.00 (core)  1,019,957.00 (non-core) | 0.00 (core)  1,353,309.00 (non-core) | 0.00 (core)  792,170.00 (non-core) | 0.00 (core)  649,741.00 (non-core) | 0.00 (core)  4,527,463.00 (non-core) |