

UN Women Strategic Note 2022-2026

**UN WOMEN Viet Nam COUNTRY OFFICE**

**SN REPORT 2022**

**The report includes:**

**Development results framework (DRF)**

Report Date: 2/11/2022

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact1 Climate Change Response, Disaster Resilience and Environmental Sustainability** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: SN Outcome 1 [CF Outcome 2] Climate Change Response, Disaster Resilience and Environmental Sustainability People in Viet Nam, especially those at risk of being left behind, will benefit from and contribute to safer and cleaner environment resulting from Viet Nam’s effective and gender responsive mitigation and adaptation to climate change, disaster risk reduction and resilience building, promotion of circular economy, the provision of clean and renewable energy, and the sustainable management of natural resources.  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2022** | **Year 2023** | **Year 2024** | **Year 2025** | **Year 2026** | **Total** |
| **Outcome 1.1 SN Outcome 1 [CF Outcome 2] Climate Change Response, Disaster Resilience and Environmental Sustainability By 2026, people in Viet Nam, especially those at risk of being left behind, will benefit from and contribute to safer and cleaner environment resulting from Viet Nam’s effective and gender responsive mitigation and adaptation to climate change, disaster risk reduction and resilience building, promotion of circular economy, the provision of clean and renewable energy, and the sustainable management of natural resources.  Related SP Outcome/Output:**   **Indicator 1.1A:** Indicator 1.1 [SP Outcome indicator 0.1.4]: Number of gender-responsive national and/or local (multi)sectoral Humanitarian Action, DRR and/or climate change strategies, policies and/or action plans adopted to advance commitments under the Sendai Framework on GEWE and Human Rights. **Targets:  Value:** 3 **Target Year:** 2022 **Value:** 4 **Target Year:** 2023 **Value:** 4 **Target Year:** 2024 **Value:** 5 **Target Year:** 2025 **Value:** 6 **Target Year:** 2026 **Baseline:  Value:** 3 **Year:** 2021 **Source:** Government report | **Output 1.1.1 SN Output 1.1: State and non-state actors have enhanced capacities to develop and implement gender responsive humanitarian, disaster risk reduction and climate change in line with the Sendai Framework on DRR and other relevant global frameworks. [revision from the CF Output 2.1: Enhanced capacity and gender-responsive policies to identify and reduce climate risks, respond to disasters and build resilience of vulnerable populations]** | **Indicator 1.1.1A:** SN output indicator 1.1.A (SP Output indicator 0.1.d): Number of state and non-state partners that have increased capacity/knowledge with UN-Women’s support to promote/influence non-discriminatory gender-responsive legislation, strategies, policies and Action Plans in humanitarian, disaster risk reduction and climate change. **Targets:  Value:** 3 **Notes:** Remain as baseline **Target Year:** 2022 **Value:** 4 **Notes:** Additional 1 in 2023 **Target Year:** 2023 **Value:** 4 **Target Year:** 2024 **Value:** 5 **Notes:** Additional 1 in 2025 **Target Year:** 2025 **Value:** 6 **Notes:** Additional 1 in 2026 **Target Year:** 2026 **Baseline:  Value:** 3 **Year:** 2021 **Notes:** 3 (VNDMA-MARD, DCC-MONRE, VWU) **Source:** - Activity reports  - Evaluation reports - Government report   **Indicator 1.1.1B:** SN output indicator 1.1.B (SP Output indicator 0.5.c): Number of dialogues, mechanisms, platforms and/or coalitions created and sustained that enable meaningful and safe participation and engagement by gender equality advocates and civil society organizations working on gender equality and women's empowerment, especially women’s organizations, in decision-making **Targets:  Value:** 1 **Notes:** 1 in 2022 **Target Year:** 2022 **Value:** 2 **Notes:** Additional 1 on 2023 **Target Year:** 2023 **Value:** 3 **Notes:** Additional 1 on 2024 **Target Year:** 2024 **Value:** 4 **Notes:** Additional 1 on 2025 **Target Year:** 2025 **Value:** 5 **Notes:** Additional 1 on 2026 **Target Year:** 2026 **Baseline:  Value:** 0 **Year:** 2021 **Source:** CSO's network report  **Indicator 1.1.1C:** SN output indicator 1.1.C (SP Output indicator 0.5.d): Number of civil society organizations working on gender equality and women's empowerment, especially women’s organizations, that have strengthened capacity to exercise their leadership role towards the achievement of gender equality and women’s empowerment **Targets:  Value:** 3 **Notes:** Additional 1 in 2022 **Target Year:** 2022 **Value:** 3 **Target Year:** 2023 **Value:** 4 **Notes:** Additional 1 in 2024 **Target Year:** 2024 **Value:** 5 **Notes:** Additional 1 in 2025 **Target Year:** 2025 **Value:** 6 **Notes:** Additional 1 in 2026 **Target Year:** 2026 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** SRD and CECR **Source:** CSO's network report  **Indicator 1.1.1D:** SN output indicator 1.1.D (SP Output indicator 0.6.c) : Number of gender statistics and sex-disaggregated data collection initiatives, including in emerging areas conducted or analyzed **Targets:  Value:** 1 **Notes:** Remain as 2021 **Target Year:** 2022 **Value:** 1 **Target Year:** 2023 **Value:** 1 **Target Year:** 2024 **Value:** 2 **Notes:** Additional 1 in 2025 **Target Year:** 2025 **Value:** 3 **Notes:** Additional 1 in 2026 **Target Year:** 2026 **Baseline:  Value:** 1 **Year:** 2021 **Notes:** Social population data for disaster monitoring **Source:** Government partner's report  **Indicator 1.1.1E:** SN output indicator 1.1.E [draft CF output 2.1 indicator]: Number of gender responsive policies and innovative solutions developed with UN Women’s support in the areas of environmental protection, reducing environmental pollution, disaster risk reduction, green growth and climate change **Targets:  Value:** 3 **Notes:** Remain as 2021 **Target Year:** 2022 **Value:** 4 **Notes:** Additional 1 in 2023 **Target Year:** 2023 **Value:** 4 **Target Year:** 2024 **Value:** 5 **Notes:** Additional 1 in 2025 **Target Year:** 2025 **Value:** 6 **Notes:** Additional 1 in 2026 **Target Year:** 2026 **Baseline:  Value:** 3 **Year:** 2021 **Notes:** (NDC, NAP, NSCC) **Source:** Government report | 84,007.00 (core)  444,217.00 (non-core) | 80,000.00 (core)  368,000.00 (non-core) | 110,000.00 (core)  366,000.00 (non-core) | 110,000.00 (core)  340,000.00 (non-core) | 110,000.00 (core)  340,000.00 (non-core) | 494,007.00 (core)  1,858,217.00 (non-core) |
| **Total Resources for outcome 1.1 (core and non-core)** | | | 84,007.00 (core)  444,217.00 (non-core) | 80,000.00 (core)  368,000.00 (non-core) | 110,000.00 (core)  366,000.00 (non-core) | 110,000.00 (core)  340,000.00 (non-core) | 110,000.00 (core)  340,000.00 (non-core) | 494,007.00 (core)  1,858,217.00 (non-core) |
| **Total Resources for impact area 1** | | | 84,007.00 (core)  444,217.00 (non-core) | 80,000.00 (core)  368,000.00 (non-core) | 110,000.00 (core)  366,000.00 (non-core) | 110,000.00 (core)  340,000.00 (non-core) | 110,000.00 (core)  340,000.00 (non-core) | 494,007.00 (core)  1,858,217.00 (non-core) |
| **Impact2 Women's Economic Empowerment** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: SN Outcome 2 (CF Outcome 3). Shared Prosperity through Economic Transformation  By 2026, people in Viet Nam, especially those at risk of being left behind, will contribute to and benefit equitably from more sustainable, inclusive and gender-responsive economic transformation based on innovation, entrepreneurship, enhanced productivity, competitiveness, and decent work.  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2022** | **Year 2023** | **Year 2024** | **Year 2025** | **Year 2026** | **Total** |
| **Outcome 2.1 SN Outcome 2 (CF Outcome 3). Shared Prosperity through Economic Transformation   By 2026, people in Viet Nam, especially those at risk of being left behind, will contribute to and benefit equitably from more sustainable, inclusive and gender-responsive economic transformation based on innovation, entrepreneurship, enhanced productivity, competitiveness, and decent work.  Related SP Outcome/Output:**   **Indicator 2.1A:** Indicator 2.1 (SN Outcome Indicator 2.1B)  CF Indicator 3.2) Proportion of informal employment in non-agriculture employment, by sex (VSDG8.3.1)\_Total **Targets:  Value:** Total: 56.%; Female: 51%; Male: 60% **Target Year:** 2022 **Value:** Total: 55.5%; Female: 50.5%; Male: 59.5% **Target Year:** 2023 **Baseline:  Value:** 56.2% **Year:** 2020 **Note:** Total: 56.2%; Female: 51.1%; Male: 60.5% **Source:** Labour Force Survey   **Indicator 2.1B:** SN Outcome indicator 2.1B (SP Outcome Indicator 0.2.4] Number of innovative financings instruments introduced that include gender equality objectives **Targets:  Value:** 2 **Target Year:** 2026 **Baseline:  Value:** 0 **Year:** 2021 **Source:** Government reports and UN Women reports   **Indicator 2.1C:** SN Outcome indicator 2.1C [SP Outcome Indicator 0.2.2]: The incorporation of gender equality targets within national investment and financial framework **Targets:  Value:** Yes **Target Year:** 2022 **Baseline:  Value:** No **Year:** 2021 **Source:** Governmental and UN Women reports   **Indicator 2.1D:** Indicator 2.1A (SN Outcome Indicator 2.1B) CF Indicator 3.2) Proportion of informal employment in non-agriculture employment, by sex (VSDG8.3.1)\_female **Targets:  Value:** 50.5% **Notes:** Total: 55.5%; Female: 50.5%; Male: 59.5% **Target Year:** 2023 **Value:** 51% **Notes:** Total: 56.%; Female: 51%; Male: 60% **Target Year:** 2022 **Baseline:  Value:** 51.1% **Year:** 2020 **Note:** Total: 56.2%; Female: 51.1%; Male: 60.5% **Source:** Labour Force Survey   **Indicator 2.1E:** Indicator 2.1A\_female (SN Outcome Indicator 2.1B) CF Indicator 3.2) Proportion of informal employment in non-agriculture employment, by sex (VSDG8.3.1)\_Male **Targets:  Value:** 60% **Notes:** Total: 56.%; Female: 51%; Male: 60% **Target Year:** 2022 **Value:** 59.5 **Notes:** Total: 55.5%; Female: 50.5%; Male: 59.5% **Target Year:** 2023 **Baseline:  Value:** 60.5 **Year:** 2020 **Note:** Total: 56.2%; Female: 51.1%; Male: 60.5% **Source:** Labor Force survey | **Output 2.1.1 Private sector actors are equipped with sustainable, inclusive and responsible business models and practices aligned with the Women’s Economic Empowerment Principles, to advance the economic empowerment of women and to promote women-led/owned SMEs.   [Revision from the CF output 3.3] Sustainable, inclusive and responsible business models and practices including MSMEs, and cooperatives are promoted to increase productivity, trade development and innovation, and improve working conditions and compliance, with special focus on economic empowerment of the poor, ethnic minorities and women.** | **Indicator 2.1.1A:** SN Output indicator 2.1A [SP Output indicator 0.1.f] Number of actors with increased capacities /knowledge, to design and implement sustainable, and gender-responsive business models and practices to support women’s economic empowerment and promote women-led enterprises. **Targets:  Value:** 4 **Notes:** Remain (EDA, TAC of MPI, Legal Dept of MOLISA, VWEC) **Target Year:** 2022 **Value:** 5 **Notes:** Additional 1 in 2023 **Target Year:** 2023 **Value:** 5 **Target Year:** 2024 **Value:** 6 **Notes:** Additional 1 in 2025 **Target Year:** 2025 **Value:** 7 **Notes:** Additional 1 in 2026 **Target Year:** 2026 **Baseline:  Value:** 4 **Year:** 2021 **Notes:** (EDA, TAC of MPI, Legal Dept of MOLISA, VWEC) **Source:** Activity reports, Evaluation reports  **Indicator 2.1.1B:** SN Output indicator 2.1B [SP Output indicator SP 0.4.c] Number of companies/organisations with increased capacities to deliver and/or monitor the quality of their services, resources and goods to support sustainable and gender-responsive approaches to women's economic empowerment and to promote women-led enterprises. **Targets:  Value:** 150 **Notes:** additional 30 in 2022 **Target Year:** 2022 **Value:** 180 **Notes:** additional 30 in 2023 **Target Year:** 2023 **Value:** 210 **Notes:** additional 30 in 2024 **Target Year:** 2024 **Value:** 240 **Notes:** additional 30 in 2025 **Target Year:** 2025 **Value:** 270 **Notes:** additional 30 in 2026 **Target Year:** 2026 **Baseline:  Value:** 120 **Year:** 2021 **Notes:** 120 WEPs signatories companies/organisations **Source:** Activity reports  Evaluation reports   **Indicator 2.1.1C:** SN Output indicator 2.1C [SP Output indicator SP 0.4.d] Number of women entrepreneurs, women-owned SMEs accessing information, goods, resources and/or services through UN-Women-supported platforms and programmes to increase their productivity, sustainability and, resilience. **Targets:  Value:** 2395 **Notes:** Additional 200 in 2022 **Target Year:** 2022 **Value:** 2595 **Notes:** additional 200 in 2023 **Target Year:** 2023 **Value:** 2795 **Notes:** additional 200 in 2024 **Target Year:** 2024 **Value:** 2995 **Notes:** additional 200 in 2025 **Target Year:** 2025 **Value:** 3195 **Notes:** additional 200 in 2026 **Target Year:** 2026 **Baseline:  Value:** 2195 **Year:** 2021 **Source:** Activity reports  Evaluation reports | 0.00 (core)  131,000.00 (non-core) | 0.00 (core)  200,000.00 (non-core) | 60,000.00 (core)  100,000.00 (non-core) | 50,000.00 (core)  130,000.00 (non-core) | 30,000.00 (core)  130,000.00 (non-core) | 140,000.00 (core)  691,000.00 (non-core) |
| **Output 2.1.2 Government partners accountability to gender equality and women’s empowerment and women-owned micro business and cooperatives (particularly micro business, cooperatives owned/led by poor women or ethnic minority groups) demonstrate increased innovative capacities, and higher productivity and profitability, and sustaining resilient livelihood models through UN Women’s support.   [Revision from the CF output 3.3]  Sustainable, inclusive and responsible business models and practices including MSMEs, and cooperatives are promoted to increase productivity, trade development and innovation, and improve working conditions and compliance, with special focus on economic empowerment of the poor, ethnic minorities and women.** | **Indicator 2.1.2A:** SN Output indicator 2.2A [SP Output indicator 0.1.f] Number of government institutions that have increased capacity/knowledge with UN Women’s support to support women-owned enterprises, women-led cooperatives to develop, implement and adopt resilient livelihood and business models. **Targets:  Value:** 2 **Notes:** Zero additional government institution (either Department of Cooperative and Rural Development or Department of Crop Production (DCRD and DoCP under MARD) **Target Year:** 2022 **Value:** 4 **Notes:** One additional government institutions including the Department of Cooperative and Rural Development and the Department of Crop Production **Target Year:** 2026 **Value:** 2 **Notes:** Zero additional government institutions including the Department of Cooperative and Rural Development and the Department of Crop Production **Target Year:** 2023 **Value:** 3 **Notes:** One additional government institutions including the Department of Cooperative and Rural Development and the Department of Crop Production **Target Year:** 2024 **Value:** 3 **Notes:** Zero additional government institutions including the Department of Cooperative and Rural Development and the Department of Crop Production **Target Year:** 2025 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** 2 (VWU, NAEC of MARD) **Source:** Activity reports, Evaluation reports  **Indicator 2.1.2B:** SN Output indicator 2.2B [SP Output indicator SP 0.4.d] Number of women’s women-led cooperatives developed, implemented, adopted resilient livelihood, business models by accessing information, resources and/or services through UN-Women-supported platforms and programmes in women’s economic empowerment. **Targets:  Value:** 600 **Notes:** Additional 77 women-led cooperatives **Target Year:** 2022 **Value:** 700 **Notes:** Additional 100 women-led cooperatives **Target Year:** 2023 **Value:** 800 **Notes:** Additional 100 women-led cooperatives **Target Year:** 2024 **Value:** 900 **Notes:** Additional 100 women-led cooperatives **Target Year:** 2025 **Value:** 1023 **Notes:** Additional 123 women-led cooperatives **Target Year:** 2026 **Baseline:  Value:** 523 **Year:** 2021 **Notes:** Baseline number: 523 women-led cooperatives **Source:** Activity reports, evaluation reports, VWU, "Vietnam Cooperative Alliance" and DCRD, White Book  **Indicator 2.1.2C:** SN Output indicator 2.2D [SP Output indicator SP 0.4.d] Number of resilient livelihood models developed, adopted by micro-business and cooperatives and sustained by women’s own-micro business, women-led cooperatives through accessing information, goods, resources and/or services through UN-Women-supported platforms and programmes in women’s economic empowerment. **Targets:  Value:** 7 **Notes:** Additional one climate-resilient models.  Activity reports and evaluation reports, VWU, NAEC, DCRD and DoCP(Department of Crop Production) of MARD **Target Year:** 2026 **Value:** 5 **Notes:** Additional one climate-resilient model.  Activity reports and evaluation reports, VWU, NAEC, DCRD, and DoCP(Department of Crop Production) of MARD **Target Year:** 2024 **Value:** 6 **Notes:** Additional one climate-resilient model. Activity reports and evaluation reports, VWU, NAEC, DCRD and DoCP(Department of Crop Production) of MARD **Target Year:** 2025 **Value:** 3 **Notes:** Additional Zero climate-resilient model. Activity reports and evaluation reports, VWU, NAEC, DCRD, and DoCP(Department of Crop Production) of MARD **Target Year:** 2022 **Value:** 4 **Notes:** Additional one climate-resilient model. Activity reports and evaluation reports, VWU, NAEC, DCRD and DoCP(Department of Crop Production) of MARD **Target Year:** 2023 **Baseline:  Value:** 3 **Year:** 2021 **Notes:** Two climate-resilient models: i) Lotus plantation in inefficient rice cultivation field and ii) chicken raised with biosecurity techniques for livelihood security improvement **Source:**  Activity reports and evaluation reports, VWU, NAEC, DCRD and DoCP(Department of Crop Production) of  **Indicator 2.1.2D:** SN Output indicator 2.2C [SP Output indicator SP 0.4.d] Number of women’s own micro-business, developed, implemented, adopted resilient livelihood, business models by accessing information, resources and/or services through UN-Women-supported platforms and programmes in women’s economic empowerment. **Targets:  Value:** 285789 **Notes:** Additional 100 women’s own micro-business, women-led cooperatives developed, implemented, adopted resilient LLH, business models **Target Year:** 2022 **Value:** 286689 **Notes:** Additional 240 women’s own micro-business, women-led cooperatives developed, implemented, adopted resilient LLH, business models **Target Year:** 2026 **Value:** 286009 **Notes:** Additional 220 women’s own micro-business, women-led cooperatives developed, implemented, adopted resilient LLH, business models **Target Year:** 2023 **Value:** 286229 **Notes:** Additional 220 women’s own micro-business, women-led cooperatives developed, implemented, adopted resilient LLH, business models **Target Year:** 2024 **Value:** 285449 **Notes:** Additional 220 women’s own micro-business, women-led cooperatives developed, implemented, adopted resilient LLH, business models **Target Year:** 2025 **Baseline:  Value:** 285,689 **Year:** 2021 **Notes:** Baseline: VWU, Vietnam Cooperative Alliance and DCRD, White book MPI **Source:** Activity reports, evaluation reports, VWU, "Vietnam Cooperative Alliance" and DCRD, White book MPI | 11,200.00 (core)  712,476.00 (non-core) | 14,000.00 (core)  150,000.00 (non-core) | 60,000.00 (core)  110,000.00 (non-core) | 50,000.00 (core)  130,000.00 (non-core) | 30,000.00 (core)  130,000.00 (non-core) | 165,200.00 (core)  1,232,476.00 (non-core) |
| **Output 2.1.3 Evidence-based options and mechanisms are promoted to expand public and private finance for achieving gender equality agenda under SDGs (Revision from the CF Output 3.5: Evidence-based options and mechanisms are promoted to expand public and private finance for achieving SDGs)** | **Indicator 2.1.3A:** SN Output indicator 2.3A [SP Output indicator 0.2.c] Number of national partners that have increased capacities to apply gender responsive budgeting tools in the budget cycle. **Targets:  Value:** 4 **Notes:** 4 (+1 in 2022) **Target Year:** 2022 **Value:** 4  **Notes:** 4 (+0 in 2023) **Target Year:** 2023 **Value:** 5 **Notes:** 5 (+1 in 2024) **Target Year:** 2024 **Value:** 5 **Notes:** 5 (+0 in 2025) **Target Year:** 2025 **Value:** 6 **Notes:** 6 (+1 in 2026) **Target Year:** 2026 **Baseline:  Value:** 3 **Year:** 2021 **Notes:** Baseline: 3 [HCM DOLISA, CEMA, People Council HCM city] **Source:** Gov report   **Indicator 2.1.3B:** SN Output indicator 2.3B [SP Output indicator 0.2.d] Number of tools introduced to key national partners in the Government of Viet Nam to implement and monitor innovative financing policies and programmes to advance gender equality. **Targets:  Value:** 3 **Notes:** 3 (+1 in 2022) **Target Year:** 2022 **Value:** 4 **Notes:** 4 (+ 1 in 2023) **Target Year:** 2023 **Value:** 4 **Notes:** 4 (0 in 2024) **Target Year:** 2024 **Value:** 4 **Notes:** 4 (0 in 2025) **Target Year:** 2025 **Value:** 5 **Notes:** 5 (+1 in 2026) **Target Year:** 2026 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** Baseline: 2 [GRB in transport sector, GRB in poverty reduction] **Source:** National reports | 0.00 (core)  140,000.00 (non-core) | 0.00 (core)  90,000.00 (non-core) | 60,000.00 (core)  60,000.00 (non-core) | 50,000.00 (core)  80,000.00 (non-core) | 50,000.00 (core)  80,000.00 (non-core) | 160,000.00 (core)  450,000.00 (non-core) |
| **Total Resources for outcome 2.1 (core and non-core)** | | | 11,200.00 (core)  983,476.00 (non-core) | 14,000.00 (core)  440,000.00 (non-core) | 180,000.00 (core)  270,000.00 (non-core) | 150,000.00 (core)  340,000.00 (non-core) | 110,000.00 (core)  340,000.00 (non-core) | 465,200.00 (core)  2,373,476.00 (non-core) |
| **Total Resources for impact area 2** | | | 11,200.00 (core)  983,476.00 (non-core) | 14,000.00 (core)  440,000.00 (non-core) | 180,000.00 (core)  270,000.00 (non-core) | 150,000.00 (core)  340,000.00 (non-core) | 110,000.00 (core)  340,000.00 (non-core) | 465,200.00 (core)  2,373,476.00 (non-core) |
| **Impact3 Governance and participation to public life** | | **Related UN-Women SP Impact Area:  Related UNDAF/ CCPD priority: SN Outcome 3 (CF Outcome 4) Governance and Access to Justice:    By 2026, people in Viet Nam, especially those at risk of being left behind, will have benefited from and have contributed to a more just, safe and inclusive society based on improved governance, more responsive institutions, strengthened rule of law and the protection of and respect for human rights, gender equality, and freedom from all forms of violence and discrimination in line with international standards.  Related national development priorities:** | | | | | | |
|  |  |  | **Year 2022** | **Year 2023** | **Year 2024** | **Year 2025** | **Year 2026** | **Total** |
| **Outcome 3.1 SN Outcome 3 (CF Outcome 4) Governance and Access to Justice   By 2026, people in Viet Nam, especially those at risk of being left behind, will have benefited from and have contributed to a more just, safe and inclusive society based on improved governance, more responsive institutions, strengthened rule of law and the protection of and respect for human rights, gender equality, and freedom from all forms of violence and discrimination in line with international standards.  Related SP Outcome/Output:**   **Indicator 3.1A:** SN Outcome indicator 3.1A [CF outcome indicator 4.1]: Rate of female deputies in elected bodies (National Assembly and People's Council) (VSDG5.5.1, VSDG5.5.4) **Targets:  Value:** more than 30.2% **Target Year:** 2022 **Baseline:  Value:** 30.26% **Year:** 2021 **Note:** National Assembly female Delegates (2021): 30.26% People's Council Deputies (2021):  - Provincial level: 29.00% - District level: 29.08% - Commune level: 28.98% **Source:** National Assembly report, the government report  **Indicator 3.1B:** SN Outcome indicator 3.1B [CF outcome indicator 1.13] Proportion of time spent on unpaid domestic and care work (VSDG 5.4.1) **Targets:  Value:** Reduce the average number of hours spent by women in unpaid housework and family care work, as compared to that of men, to 1.7 times by 2025 and 1.4 times by 2030 **Notes:** National strategy on Gender Equality **Target Year:** 2026 **Baseline:  Value:** Male 8.9 h/week, Female 18.9h/week (2.1 times as compared with that of male) **Year:** 2020 **Note:** Male 8.9 h/week Female 18.9h/week, 2.1 times as compared with that of male (2019 LFS/VSDG report 2020) **Source:** Labour Force Survey   **Indicator 3.1C:** SN Outcome indicator 3.1C [CF outcome indicator 4.2] Sex ratio at birth (SRB) (VSDG51/SDG 5.1.1) **Targets:  Value:** 110.0 **Notes:** Population Change Survey, GSO **Target Year:** 2026 **Baseline:  Value:** 112.1 **Year:** 2020 **Note:** Population Change Survey, GSO **Source:** Population Change Survey, GSO  **Indicator 3.1D:** SN Outcome indicator 3.1D [CF outcome indicator 4.3] Proportion of women aged 20–24 years being married or in a union before the age of 18.(VSDG 55/SDG 5.3.1) **Targets:  Value:** 6% **Notes:** 2026, Viet Nam Population Strategy to 2030, aiming at reducing 50% of couples married before 18 or child marriage by 2030) **Target Year:** 2026 **Baseline:  Value:** 9.1% **Year:** 2019 **Note:** Baseline: 9.1% (2019, Population Census. GSO) **Source:** Population Census. GSO  **Indicator 3.1E:** SN Outcome indicator 3.1E [SP Outcome Indicator SDG 0.1.4]: Number of laws that were adopted, revised or repealed to advance gender equality and women’s empowerment **Targets:  Value:** 4 **Notes:** GEL, DVL, Law on Civil Defence/ Emergency State, Gender Affirmation Law) **Target Year:** 2022 **Baseline:  Value:** 4 **Year:** 2021 **Note:** Baseline: State budget law, Election law, NSGE 2021-2030, the Labour Code 2019. **Source:** Government report   **Indicator 3.1F:** SN Outcome indicator 3.1F [SP Outcome Indicator SDG 0.1.5]: Number of national and/or local (multi)sectoral strategies, policies and/or action plans that are adopted with a focus on gender equality **Targets:  Value:** 2 **Notes:** Gov report **Target Year:** 2026 **Baseline:  Value:** 2 **Year:** 2021 **Note:** Baseline: Master Plan on Social economic development for the EM regions, the Action Plan of HCM city on safe cities for women and girls **Source:** Gov report   **Indicator 3.1G:** SN Outcome indicator 3.1G [CF Outcome indicator 4.12] Percentage of GBV victims seeking assistance from any supporting services (linked with VSDG 16.2.3) **Targets:  Value:** 50% **Notes:** Target: 50% (2026, MOLISA’s M&E framework) Source: MOLISA’s M&E Framework of the National Programme on GBV 2021-2025. (national GBV database to be developed) **Target Year:** 2026 **Baseline:  Value:** 9.6% **Year:** 2019 **Note:** Baseline: 9.6% (2019, VAW study by GSO/MOLISA **Source:** Gov report | **Output 3.1.1 SN Output 3.1 [CF Output 4.3]: The social, institutional and legal environment is enhanced to accelerate the achievement of gender equality, empowerment, participation and decision-making of women and to eliminate all forms of discrimination against women, girls and LGBTIQ persons).** | **Indicator 3.1.1A:** SN Output Indicator 3.1A: (SP Output indicator 0.1.f) Number of institutions that have increased capacities to review, plan, design and implement institutional reforms/ strategies/ policies to support the operationalisation of the Government’s normative commitments on GEWE (CEDAW, BPFA, SDGs and UNSCR). **Targets:  Value:** 8 **Notes:** 8 (+1 in 2022) **Target Year:** 2022 **Value:** 10 **Notes:** 10 (+2 in 2023) **Target Year:** 2023 **Value:** 12  **Notes:** 12 (+2 in 2024) **Target Year:** 2024 **Value:** 14 **Notes:** 14 (+2 in 2025) **Target Year:** 2025 **Value:** 16 **Notes:** 16 (+2 in 2026) . Note: 9 additional [MPI, MOLISA, VWU, DOLISA HCM, DNWU, CEMA, MPS, MOD,NA for the period 2022-2026, total 16 by 2026. **Target Year:** 2026 **Baseline:  Value:** 7 **Year:** 2022 **Notes:** Baseline (2021) 7 [MARD, MOLISA, VWU, CEMA, MOD, MPS, MOJ] **Source:** Gov and partner's reports   **Indicator 3.1.1B:** SN Output Indicator 3.1B (SP Output indicator 0.1.d) Number of government partners that have increased capacities to promote/influence gender-responsive legislation and its implementation. **Targets:  Value:** 9 **Notes:** 9 (+2 in 2022) **Target Year:** 2022 **Value:** 10 **Notes:** 10 (+1 in 2023) **Target Year:** 2023 **Value:** 11 **Notes:** 11 (+ 1 in 2024) **Target Year:** 2024 **Value:** 13 **Notes:** 13 (+2 in 2025) **Target Year:** 2025 **Value:** 15 **Notes:** 15 (+2 in 2026) **Target Year:** 2026 **Baseline:  Value:** 7 **Year:** 2022 **Notes:** Value: 7 [MARD, MOLISA, VWU, CEMA, VCP, VWEC, ISDS] **Source:** Gov report   **Indicator 3.1.1C:** SN Output Indicator 3.1C (SP Output indicator 0.1.h) Number of multi-stakeholder dialogue processes facilitated/supported by UN Women, to promote engagement of the government with civil society and other partners to advance national commitments on gender equality and women’s empowerment. **Targets:  Value:** 4 **Notes:** 4 (+ 2 in 2022) **Target Year:** 2022 **Value:** 6 **Notes:** 6 (+2 in 2023) **Target Year:** 2023 **Value:** 8 **Notes:** 8 (+2 in 2024) **Target Year:** 2024 **Value:** 10 **Notes:** 10 (+2 in 2025) **Target Year:** 2025 **Value:** 12 **Notes:** 12 (+2 in 2026) **Target Year:** 2026 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** Baseline: 2 annually **Source:** Gov and UN reports  **Indicator 3.1.1D:** SN Output Indicator 3.1D (SP Output indicator 0.3.b) Number of evidence and/or practice-based standardised approaches or models for social norms and individual behaviour change that are available to partners. **Targets:  Value:** 3 **Notes:** 3 (0 in 2022) **Target Year:** 2022 **Value:** 4 **Notes:** 4 (+1 in 2023 **Target Year:** 2023 **Value:** 5 **Notes:** 5 (+1 in 2024 **Target Year:** 2024 **Value:** 5 **Notes:** 5 (0 in 2025) **Target Year:** 2025 **Value:** 6 **Notes:** 6 (+1 in 2026 **Target Year:** 2026 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** Baseline (2021): 3 (HeForShe, Generation Equality) **Source:** Government reports, CSOs reports, One UN report, UN Women report   **Indicator 3.1.1E:** SN Output Indicator 3.1E (SP Output indicator 0.5.c) Number of dialogues, mechanisms, platforms and/or coalitions created and sustained that enable meaningful and safe participation and engagement by gender equality advocates and civil society organisations working on gender equality and women’s empowerment, especially women’s organisations, in decision- making. **Targets:  Value:** 1 **Target Year:** 2022 **Value:** 2 **Notes:** 2 (+1 in 2023) **Target Year:** 2023 **Value:** 3 **Notes:** 3 (+1 in 2024) **Target Year:** 2024 **Value:** 4 **Notes:** 4 (+1 in 2025) **Target Year:** 2025 **Value:** 5 **Notes:** 5 (+1 in 2026) **Target Year:** 2026 **Baseline:  Value:** 0 **Year:** 2021 **Notes:** Baseline: 0 **Source:**  UN Women annual reports, Government reports, One UN report on the implementation of the UNSDCF  **Indicator 3.1.1F:** SN Output Indicator 3.1F (SP Output indicator 0.5.d) Number of civil society organisations working on gender equality and women’s empowerment, especially women’s organisations, that have strengthened capacities to exercise their leadership role towards the achievement of gender equality and women’s empowerment. **Targets:  Value:** 1 **Notes:** 4 (+1 in 2022) **Target Year:** 2022 **Value:** 4 **Notes:** 4 (0 in 2023) **Target Year:** 2023 **Value:** 5 **Notes:** 5 (+1 in 2025) **Target Year:** 2024 **Value:** 6 **Notes:** 6 (+1 in 2025) **Target Year:** 2025 **Value:** 7 **Notes:** 7 (+1 in 2026) **Target Year:** 2026 **Baseline:  Value:** 3 **Year:** 2021 **Notes:** Baseline: at least 5 during 2017-2021 period (ISDS, LIGHT, CSAGA, CEPEW and CCIPH) **Source:** UN Women and government reports, CSO report, One UN report. | 273,953.00 (core)  515,735.00 (non-core) | 275,548.00 (core)  414,680.00 (non-core) | 50,000.00 (core)  215,000.00 (non-core) | 60,000.00 (core)  215,000.00 (non-core) | 50,000.00 (core)  190,000.00 (non-core) | 709,501.00 (core)  1,550,415.00 (non-core) |
| **Output 3.1.2 SN Output 3.2  State and non-state actors are equipped with knowledge, skills and tools to support the transformation of social norms and practices and actions (polices and laws) for the elimination gender-based violence and all forms of abuse, exploitation and discrimination against vulnerable groups.   [Revision from the CF Output 4.4] Socio cultural attitudes and practices, accountability and legal and policy frameworks are transformed to eliminate gender-based violence and all forms of abuse, exploitation and discrimination against vulnerable groups** | **Indicator 3.1.2A:** SN Output Indicator 3.2A (SP Output indicator 0.1.f) Number of revised/new/improved laws/policies to prevent and respond to GBV adopted and implemented with support of UN Women **Targets:  Value:** 3 **Notes:** +1 in 2022 **Target Year:** 2022 **Value:** 4 **Notes:** +1 in 2023 **Target Year:** 2023 **Value:** 5 **Notes:** +1 in 2024 **Target Year:** 2024 **Value:** 5 **Notes:** 5 (+0 in 2025) **Target Year:** 2025 **Value:** 5 **Notes:** 5 (+0 in 2025) Note: 3 for the period 2022-2026 and total 5 by 2026. **Target Year:** 2026 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** NP on GBV prevention and response 2021-2025, Directive 39 on safe cities for women and children in Da Nang City **Source:** Government reports, UN Women Report, One UN Report  **Indicator 3.1.2B:** SN Output Indicator 3.2B (SP Output indicator  0.3.f) Number of evidence based VAW prevention strategies/ interventions designed and implemented with with support of UN Women. **Targets:  Value:** 6 **Notes:** +1 in 2022 **Target Year:** 2022 **Value:** 7 **Notes:** +1 in 2023 **Target Year:** 2023 **Value:** 7 **Notes:** +0 in 2024 **Target Year:** 2024 **Value:** 7 **Notes:** +0 in 2025 **Target Year:** 2025 **Value:** 6 **Notes:** +0 in 2026 Note: 2 for the period 2022-2026 and total 7 by 2026. **Target Year:** 2026 **Baseline:  Value:** 5 **Year:** 2021 **Notes:** Evidence based VAW prevention strategies/ interventions: community mobilization, men engagement, youth engagement -change makers, CWR, 16 DOA **Source:** Government reports, One UN Reports, UN Women reports, CSOs reports  **Indicator 3.1.2C:** SN Output Indicator 3.2C (SP Output indicator 0.4.a) Number of SOPs/ Guidelines/Coordination and advisory structures in place with UN Women support to improve the provision of essential services, goods and/or resources for women with support of UN Women. **Targets:  Value:** 10 **Notes:** +3 in 2022 **Target Year:** 2022 **Value:** 12 **Notes:** +2 in 2023 **Target Year:** 2023 **Value:** 14 **Notes:** +2 in 2024 **Target Year:** 2024 **Value:** 15 **Notes:** +1 in 2025 **Target Year:** 2025 **Value:** 15 **Notes:** (+ 0 in 2026)  Note: 8 for the period 2022-2026 and total 15 by 2026. **Target Year:** 2026 **Baseline:  Value:** 7 **Year:** 2021 **Notes:** (MOJ-3 departments, MOLISA, MPS, SPP Ben Tre, CWD) **Source:** Governments reports, UN Women reports, One UN Reports  **Indicator 3.1.2D:** SN Output Indicator 3.2D (SP Output indicator 0.4.e.): Number of provinces with multi stakeholder initiatives in place to prevent and respond to sexual violence including sexual harassment in public and/or private spaces with support of UN Women **Targets:  Value:** 3 **Notes:** +1 in 2022 **Target Year:** 2022 **Value:** 4 **Notes:** +1 in 2023 **Target Year:** 2023 **Value:** 5 **Notes:** +1 in 2024 **Target Year:** 2024 **Value:** 5 **Notes:** 0 in 2025 **Target Year:** 2025 **Value:** 5 **Notes:** + 0 in 2026 Note: 3 for the period 2022-2026 and total 5 by 2026. **Target Year:** 2026 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** Da Nang and Ho Chi Minh City **Source:** Government reports, One UN reports, Un Women reports | 0.00 (core)  1,058,837.00 (non-core) | 0.00 (core)  506,884.00 (non-core) | 0.00 (core)  580,000.00 (non-core) | 20,000.00 (core)  110,000.00 (non-core) | 70,000.00 (core)  150,000.00 (non-core) | 90,000.00 (core)  2,405,721.00 (non-core) |
| **Output 3.1.3 SN Output 3.3: UN Women effectively supports accountability of the UN for the commitments on GEWE.** | **Indicator 3.1.3A:** SN Output indicator 3.3A:Number of inter-agency products or services with a focus on gender equality and women’s empowerment developed and made available by UN Women (independently or jointly with others. **Targets:  Value:** 4 **Notes:** 4 (+2 in 2022) **Target Year:** 2022 **Value:** 6 **Notes:** 6 (+2 in 2023) **Target Year:** 2023 **Value:** 8 **Notes:** 8 (+2 in 2024) **Target Year:** 2024 **Value:** 10 **Notes:** 10 (+2 in 2025) **Target Year:** 2025 **Value:** 12 **Notes:** 12 (+2 in 2026) **Target Year:** 2026 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** Baseline: 2 annually in the year 2021) **Source:** Source: GTG report, One UN report, UN Women report  **Indicator 3.1.3B:** SN Output indicator 3.3B: Number of joint UN actions in support of GEWE initiated/coordinated by UN Women Viet Nam **Targets:  Value:** 4 **Notes:** 4 (+2 in 2022) **Target Year:** 2022 **Value:** 6 **Notes:** 6 (+2 in 2023) **Target Year:** 2023 **Value:** 8 **Notes:** 8 (+4 in 2024) **Target Year:** 2024 **Value:** 10 **Notes:** 10 (+6 in 2025) **Target Year:** 2025 **Value:** 12 **Notes:** 12 (+8 in 2026) **Target Year:** 2026 **Baseline:  Value:** 2 **Year:** 2021 **Notes:** Baseline: 2 joint actions in 2021 (IWD event and 16 days of activism) **Source:** One UN report, UN Women report, GTG reports  **Indicator 3.1.3C:** SN Output indicator 3.3C: SN Output indicator 3.3C: Number of the capacity support and quality assurance measures introduced to facilitate the development of the gender responsive Joint Programmes. **Targets:  Value:** 2 **Notes:** 2 (+1 in 2022) **Target Year:** 2022 **Value:** 3 **Notes:** 3 (+1 in 2023) **Target Year:** 2023 **Value:** 4 **Notes:** 4 (+1 in 2024) **Target Year:** 2024 **Value:** 5 **Notes:** 5 (+1 in 2025) **Target Year:** 2025 **Value:** 5 **Notes:** 6 (+1 in 2026) **Target Year:** 2025 **Baseline:  Value:** 1 **Year:** 2021 **Notes:** Baseline: 1 joint programme in 2021 **Source:**  One UN report, GTG report and UN Women report  **Indicator 3.1.3D:** SN Output indicator 3.3D: Number of inputs and/or actions led by the UNCT to inform/support government accountabilities on normative frameworks (CEDAW, CSW, BfPA, SDG, SG reports, etc.), with UN Women's support **Targets:  Value:** 4 **Notes:** 4 (+2 in 2022) **Target Year:** 2022 **Value:** 6 **Notes:** 6 (+2 in 2023) **Target Year:** 2023 **Value:** 8 **Notes:** 8 (+2 in 2024) **Target Year:** 2024 **Value:** 10 **Notes:** 10 (+2 in 2025) **Target Year:** 2025 **Value:** 12 **Notes:** 12 (+2 in 2026) **Target Year:** 2026 **Baseline:  Value:** 6 **Year:** 2021 **Notes:** 6 during the period 2017-2021 **Source:** Source: One UN report and annual UN Women VCO report | 24,046.00 (core)  0.00 (non-core) | 24,046.00 (core)  0.00 (non-core) | 60,000.00 (core)  0.00 (non-core) | 60,000.00 (core)  0.00 (non-core) | 0.00 (core)  0.00 (non-core) | 168,092.00 (core)  0.00 (non-core) |
| **Total Resources for outcome 3.1 (core and non-core)** | | | 297,999.00 (core)  1,574,572.00 (non-core) | 299,594.00 (core)  921,564.00 (non-core) | 110,000.00 (core)  795,000.00 (non-core) | 140,000.00 (core)  325,000.00 (non-core) | 120,000.00 (core)  340,000.00 (non-core) | 967,593.00 (core)  3,956,136.00 (non-core) |
| **Total Resources for impact area 3** | | | 297,999.00 (core)  1,574,572.00 (non-core) | 299,594.00 (core)  921,564.00 (non-core) | 110,000.00 (core)  795,000.00 (non-core) | 140,000.00 (core)  325,000.00 (non-core) | 120,000.00 (core)  340,000.00 (non-core) | 967,593.00 (core)  3,956,136.00 (non-core) |